## Task Instructions
The Agency Preparedness Activity Tracker (PAT) includes a list of the implementation tasks agencies need to complete to prepare for FLIPS Go-Live.
Each of the PAT Tracker's columns and what they represent are listed below with a brief description. These tasks can be filtered in numerous ways to account for variables that better align for specific agencies.
Task ID | Represents the number of a given task. There are 12 tasks in total.
Task Name | Summarizes in a few words what a task will entail.
Date Released | Displays when an actual PAT task has been released.
Pilot vs. Nonpilot | Differentiates between Pilot and Nonpilot agencies.
Phase | Represents the number for which phase a certain task exists in.
Task Overview | Describes what will occur within a given task.
Task Status | Gauges the completion level of a task (Not Started, In Progress, or Finished).
Start Date | Displays the official start of a task.
End Date | Displays the offical end of a task.
Comments/Updates | Used for expressing additional information about a specific task.

## PAT Tasks
Task ID | Task Name | Date Released | Pilot vs. Nonpilot | Phase | Task Overview | Task Status | Start Date | End Date | Comments/Updates
1 | Identify Change Support Network Members |  | Pilot | 1 | Return a list of agency personnel that will support the CSN. | In Progress | 2025-09-08 | 2025-09-24
1 | Identify Change Support Network Members |  | Nonpilot | 1 | Return a list of agency personnel that will support the CSN. | In Progress | 2025-09-08 | 2025-09-24
2 | Review and confirm policy changes and determine procedure updates that must be implemented to support the transition to and usages of FLIPS |  | Pilot | 2 | Return a list of polcies and procedures in a Word document that the agency will change. | Not Started | TBD | TBD
2 | Review and confirm policy changes and determine procedure updates that must be implemented to support the transition to and usages of FLIPS |  | Nonpilot | 2 | Return a list of polcies and procedures in a Word document that the agency will change. | Not Started | TBD | TBD
3 | Identify agency personnel that require access to FLIPS |  | Pilot | 2 | Access Control form will be supplied to agencies to request user access to FLIPS. | Not Started | TBD | TBD
3 | Identify agency personnel that require access to FLIPS |  | Nonpilot | 2 | Access Control form will be supplied to agencies to request user access to FLIPS. | Not Started | TBD | TBD
4 | Confirm firewalls allow connection with FLIPS |  | Pilot | 2 | Confirm agency is prepared for firewall connection with FLIPS. | Not Started | TBD | TBD
4 | Confirm firewalls allow connection with FLIPS |  | Nonpilot | 2 | Confirm agency is prepared for firewall connection with FLIPS. | Not Started | TBD | TBD
5 | FLIPS Training Delivery |  | Pilot | 2 | Actively particpate in training and report progress. | Not Started | TBD | TBD
5 | FLIPS Training Delivery |  | Nonpilot | 2 | Actively particpate in training and report progress. | Not Started | TBD | TBD
6 | User Acceptance Testing |  | Pilot | 2 | End-user validation of FLIPS functionality and performance. | Not Started | TBD | TBD
6 | User Acceptance Testing |  | Nonpilot | 2 | End-user validation of FLIPS functionality and performance. | Not Started | TBD | TBD
7 | Review Go-Live Toolkit |  | Pilot | 2 | Acknowledge receipt of the Go0Live Toolkit (e.g., schedule, escalation, path of issues, job aids). | Not Started | TBD | TBD
7 | Review Go-Live Toolkit |  | Nonpilot | 2 | Acknowledge receipt of the GoLive Toolkit (e.g., schedule, escalation, path of issues, job aids). | Not Started | TBD | TBD
8 | Confirmation of Readiness |  | Pilot | 3 | Confirm agency is prepared for the implementation of FLIPS. | Not Started | TBD | TBD
8 | Confirmation of Readiness |  | Nonpilot | 3 | Confirm agency is prepared for the implementation of FLIPS. | Not Started | TBD | TBD | Deploy weekly check-list
9 | Monitor FLIPS Go-Live |  | Pilot | 3 | Provide Go-Live Successes and CSN Direction and Feedback | Not Started | TBD | TBD
9 | Monitor FLIPS Go-Live |  | Nonpilot | 3 | Provide Go-Live Successes and CSN Direction and Feedback | Not Started | TBD | TBD
10 | Share Success and Challenges |  | Pilot | 4 | Provide implementation challenges and success in an Excel format. | Not Started | TBD | TBD
10 | Share Success and Challenges |  | Nonpilot | 4 | Provide implementation challenges and success in an Excel format. | Not Started | TBD | TBD
11 | Retire CSN |  | Pilot | 4 | Communicate to agency contacts at the end of implemetation and the transition to operational support. | Not Started | TBD | TBD
11 | Retire CSN |  | Nonpilot | 4 | Communicate to agency contacts at the end of implemetation and the transition to operational support. | Not Started | TBD | TBD