## Task Instructions
The Agency Preparedness Activity Tracker (PAT) includes a list of the implementation tasks agencies need to complete to prepare for FLIPS Go-Live.
Each of the PAT Tracker's columns and what they represent are listed below with a brief description. These tasks can be filtered in numerous ways to account for variables that better align for specific agencies.
Task ID | Represents the number of a given task. There are 12 tasks in total.
Task Name | Summarizes in a few words what a task will entail.
Date Released | Displays when an actual PAT task has been released.
Pilot vs. Nonpilot | Differentiates between Pilot and Nonpilot agencies.
Phase | Represents the number for which phase a certain task exists in.
Task Overview | Describes what will occur within a given task.
Task Status | Gauges the completion level of a task (Not Started, In Progress, or Finished).
Start Date | Displays the official start of a task.
End Date | Displays the offical end of a task.
Comments/Updates | Used for expressing additional information about a specific task.

## PAT Tasks
Task ID | Task Name | Date Released | Pilot vs. Nonpilot | Phase | Task Overview | Task Status | Start Date | End Date | Comments/Updates
1 | Identify Change Support Network Members |  | Pilot | 1 | Return a list of agency personnel that will support the CSN. | Not Started | 2025-09-08 | 2025-09-24
1 | Identify Change Support Network Members |  | Nonpilot | 1 | Return a list of agency personnel that will support the CSN. | Not Started | 2025-09-08 | 2025-09-24
2 | Review and confirm policy changes and determine procedure updates that must be implemented to support the transition to and usages of FLIPS |  | Pilot | 2 | Return a list of polcies and procedures in a Word document that the agency will change. | Not Started | 2025-10-03 | 2025-10-03
2 | Review and confirm policy changes and determine procedure updates that must be implemented to support the transition to and usages of FLIPS |  | Nonpilot | 2 | Return a list of polcies and procedures in a Word document that the agency will change. | Not Started | 2025-10-03 | 2025-10-03
3 | Identify agency personnel that require access to FLIPS |  | Pilot | 2 | Access Control form will be supplied to agencies to request user access to FLIPS. | Not Started | 2025-10-24 | 2025-11-17
3 | Identify agency personnel that require access to FLIPS |  | Nonpilot | 2 | Access Control form will be supplied to agencies to request user access to FLIPS. | Not Started | 2026-01-06 | 2026-01-28
4 | Inform agency personnel of EFT registration process changes |  | Pilot | 2 | EFT registration processes are changing effective October of 2025. Agencies will notify agency personnel of the process change. | Not Started | 2025-09-15 | 2025-09-15
4 | Inform agency personnel of EFT registration process changes |  | Nonpilot | 2 | EFT registration processes are changing effective October of 2025. Agencies will notify agency personnel of the process change. | Not Started | 2025-09-15 | 2025-09-15
5 | Confirm firewalls allow connection with FLIPS |  | Pilot | 2 | Confirm agency is prepared for firewall connection with FLIPS. | Not Started | 2025-10-28 | 2025-11-19
5 | Confirm firewalls allow connection with FLIPS |  | Nonpilot | 2 | Confirm agency is prepared for firewall connection with FLIPS. | Not Started | 2025-10-28 | 2025-11-19
6 | FLIPS Training Delivery |  | Pilot | 2 | Actively particpate in training and report progress. | Not Started | 2025-12-01 | 2025-12-30
6 | FLIPS Training Delivery |  | Nonpilot | 2 | Actively particpate in training and report progress. | Not Started | 2026-01-29 | 2026-02-27
7 | User Acceptance Testing |  | Pilot | 2 | End-user validation of FLIPS functionality and performance. | Not Started | 2025-12-04 | 2025-12-19
7 | User Acceptance Testing |  | Nonpilot | 2 | End-user validation of FLIPS functionality and performance. | Not Started | 2025-12-04 | 2025-12-19
8 | Review Go-Live Toolkit |  | Pilot | 2 | Acknowledge receipt of the Go0Live Toolkit (e.g., schedule, escalation, path of issues, job aids). | Not Started | 2025-12-01 | 2025-12-31
8 | Review Go-Live Toolkit |  | Nonpilot | 2 | Acknowledge receipt of the GoLive Toolkit (e.g., schedule, escalation, path of issues, job aids). | Not Started | 2026-02-25 | 2026-03-13
9 | Confirmation of Readiness |  | Pilot | 3 | Confirm agency is prepared for the implementation of FLIPS. | Not Started | 2026-01-05 | 2026-01-19
9 | Confirmation of Readiness |  | Nonpilot | 3 | Confirm agency is prepared for the implementation of FLIPS. | Not Started | 2026-03-18 | 2026-04-01 | Deploy weekly check-list
10 | Monitor FLIPS Go-Live |  | Pilot | 3 | Provide Go-Live Successes and CSN Direction and Feedback | Not Started | 2026-01-19 | 2026-03-16
10 | Monitor FLIPS Go-Live |  | Nonpilot | 3 | Provide Go-Live Successes and CSN Direction and Feedback | Not Started | 2026-04-01 | 2026-05-05
11 | Share Success and Challenges |  | Pilot | 4 | Provide implementation challenges and success in an Excel format. | Not Started | 2026-05-05 | 2026-05-27
11 | Share Success and Challenges |  | Nonpilot | 4 | Provide implementation challenges and success in an Excel format. | Not Started | 2026-05-05 | 2026-05-27
12 | Retire CSN |  | Pilot | 4 | Communicate to agency contacts at the end of implemetation and the transition to operational support. | Not Started | 2026-06-03 | 2026-06-03
12 | Retire CSN |  | Nonpilot | 4 | Communicate to agency contacts at the end of implemetation and the transition to operational support. | Not Started | 2026-06-03 | 2026-06-03