## Success Factors
Measures / Internal Factors and Success Criteria
# | Phase | Internal Factors | Success Criteria Tracking | Success Criteria | Internal Factor Status (In-Progress, Complete) | Success (Pass/Fail) | Internal Factor Date Start | Internal Factor End Date | Overall Status (On Track/ Delayed / Critically Delayed)
1 | Remediation | Agency Business System (ABS) Development |  | 100% Development Complete |  |  | 2024-09-01 | 2024-06-01
2 | Remediation | Unit Testing ABS (Agency Internal Testing with Applicable Areas) |  | 100% Unit Testing Complete |  |  | 2025-01-01 | 2025-06-01
3 | Remediation | Florida PALM Configured Interface Values Provided to Agencies and Interface Error File Formats Provided to Agencies for Testing |  | 85-100% Configurations Complete |  |  | 2025-05-01 | 2025-07-01
4 | Remediation | Interface File Testing with Florida PALM |  | 25-50% Successful With No Show Stopper Bugs |  |  | 2025-06-01 | 2025-08-01
5 | Remediation | Test Tier 2 Agency ABS Interface Testing (i.e. test information from Tier 1 ABS going to Tier 2 Agency ABS) |  | 100% Testing Complete |  |  | 2025-08-01 | 2025-11-01
| SG | Stage Gate 3 - Ready to begin UAT - July 30, 2025
6 | Training | SMEs (Subject Matter Experts) Trained on Florida PALM User Interface / System |  | 100% SME's Trained |  |  | 2025-08-01 | 2025-11-01
7 | Training | Identified SMEs Completed UAT (User Acceptance Testing) Prerequisite Training |  | 100% SMEs Completed |  |  | 2025-06-01 | 2025-07-01
8 | Training | Version One SME UAT User Guide Complete |  | 100% Complete |  |  | 2025-07-01 | 2025-08-01
9 | Training | End Users Training on Florida PALM User Interfaces and System |  | At Least 50-75% End Users Have Tested in Every Applicable Area |  |  | 2025-10-01 | 2025-12-01
10 | Training | Florida PALM Users Know How To Access Florida PALM |  | 50-75% of the Users Can Access Florida PALM |  |  | 2025-08-12 | 2025-12-01
11 | UAT | Regardless of Go-Live date, UAT Must Start in August 2025 |  | 50-75% System Ready for UAT - Focus on Understanding Florida PALM Process and Data Flow for Each Module |  |  | 2025-08-01 | 2026-05-01
12 | UAT | Complete Interface File Testing with Florida PALM |  | 90% Successful With No Show Stopper Bugs |  |  | 2025-08-25 | 2025-10-26
13 | UAT | SMEs Successful Completion of Florida PALM UAT |  | 100% SME's Have Completed UAT in Florida PALM |  |  | 2025-08-01 | 2025-11-01
14 | UAT | All DFS Accounting and Auditing UAT Scenarios Tested |  | 100% DFS A&A Scenarios Tested Successfully |  |  | 2025-08-01 | 2026-05-01
15 | UAT | All DFS Treasury UAT Scenarios Tested |  | 100% DFS Treasury Scenarios Tested Successfully |  |  | 2025-08-01 | 2026-05-01
16 | Training | All Agency Users are Trained on Enterprise Owned ABS for Florida PALM Changes (STMS, Pcard Works, MFMP, FACTS, and People First) |  | 80% Applicable Agency Staff Trained |  |  | 2025-09-01 | 2025-12-01
17 | Training | All Agency Users are Trained on Agency Owned ABS for Florida PALM Changes |  | 50-75% Applicable Agency Staff Trained |  |  | 2025-09-01 | 2025-12-01
18 | UAT | Begin End Users Florida PALM UAT |  | 50-75% End Users Have Started UAT |  |  | 2025-12-01 | 2026-05-01
19 | UAT | All Tier 1 and Tier 2 Identified Processes Tested in Florida PALM |  | 100% Processes Tested Successfully |  |  | 2025-08-01 | 2025-11-01
20 | UAT | All Identified Test Cases Tier 1 and Tier 2 Tests Successful in Florida PALM |  | 100% of the Test Cases are Tested Successfully |  |  | 2025-08-01 | 2025-11-01
21 | UAT | Test FYE (Fiscal Year-End) Processes in Florida PALM UAT |  | 100% YE Testing Complete |  |  | 2026-01-01 | 2026-04-01
| SG | Stage Gate 4 - Continue Deployment - January 30, 2026
22 | UAT | Show Stopper Bugs (i.e., Bills cannot be paid, Employees not paid, Revenue not recorded) |  | 100% Critical Bugs are Resolved |  |  | 2026-01-01 | 2026-04-01
23 | UAT | Complete End User Florida PALM UAT |  | 75% End Users Have Completed UAT |  |  | 2025-12-01 | 2026-05-01
24 | Florida PALM Training | Create, Update and Execute Agency Specific Training Based on Florida PALM Training |  | 100% SME's Complete Florida PALM training 25-50% End Users Complete Training |  |  | 2025-12-01 | 2026-05-01
25 | UAT | Orchestrated FYE Closing with DFS Accounting and Auditing/Florida PALM/Agencies |  | 75-100% FYE Tasks Completed Successfully |  |  | 2026-04-01 | 2026-05-01
| SG | Stage Gate 5 - Agency Readiness - May 2026
26 | Go-Live Measures | Tier 1 and Tier 2 - To-Be Documentation of Processes Updated for Florida PALM User Interface / Processes |  | 75% Complete |  |  | 2025-08-01 | 2025-12-01
27 | Go-Live Measures | Complete Florida PALM Training for All End Users |  | 90% Complete |  |  | 2025-08-01 | 2026-05-01
28 | Go-Live Measures | Complete Florida PALM Configuration |  | 90% Correct Configuration |  |  | 2025-01-01 | 2026-05-01
29 | Go-Live Measures | Complete Florida PALM Conversion Mapping and Data Cleansing |  | 90% Correct Conversion |  |  | 2025-08-01 | 2026-05-01
30 | Go-Live Measures | Florida PALM Role Mapping Accurate and Complete |  | 90% Complete |  |  | 2026-05-01 | 2026-07-01
31 | Go-Live Measures | Deployment Plan / Technical Plan |  | 95% Identified and Documented |  |  | 2026-01-01 | 2026-05-26
32 | Go-Live Measures | Readiness Implementation Plan - Business Plan / Coordination Between Florida PALM, Enterprise Agencies, DFS, and all State Agencies Must Create a Template of Activities Based on Go-Live Timeframe (July 2026) |  | 100% Activities Identified and Implementation Plan Complete |  |  | 2026-01-01 | 2026-05-26
33 | Go-Live Measures | Chief of Finance Must Be Able to Guide and Direct Resources to the Right Module / Process / SME for Assistance / Training / Guidance |  | 100% Complete |  |  | 2026-02-01 | 2026-04-01
34 | Go-Live Measures | Create Agency Functional Help Desk |  | 100% Setup of Help Desk |  |  | 2026-01-01 | 2026-12-01
| SG | Stage Gate 6 - Deployment Readiness - June 17, 2026
35 | Go-Live Measures | Deploy Strike Teams to Assist Applicable Areas |  | 90% Ready |  |  | 2026-05-01 | 2026-07-01
36 | Go-Live Measures | Agency Dedicated Training Room |  | 100% Ready for Users |  |  | 2026-04-01 | 2026-12-01
37 | Go-Live Measures | Confirm Final Import of Configurations, Conversions, and Balances to Include LAS/PBS Appropriations for 2026-2027 |  | 100% Complete |  |  | 2026-04-01 | 2026-07-01
38 | Go-Live Measures | Agency Deploys in Accordance with the Readiness Implementation and Technical Deployment Plan |  | 100% Complete |  |  | 2026-07-01 | 2026-09-01
| SG | Stage Gate 7 - Confirm Deployment - July 2026
39 | Post Deploy | Hypercare |  |  |  |  | 2026-07-01 | 2026-12-01
| SG | Stage Gate 8 - Go-Live - July 2026
Note
All dates are pending based on the final dates published by Florida PALM Project
Each success factor is a snapshot based on the information we have from Florida PALM Project
|  | On Track | In-Progress
|  | Delayed | Complete
Critically Delayed
DRAFT

## Business Process Tiers
Florida PALM Business Processes Tiering
Business Process Grouping | Business Process | Associated Process Module | Module | Tier Level
Account Management and Financial Reporting (AMFR) | 10.1.1 Agency Add or Modify ChartField Values | GL | General Ledger | T1
Account Management and Financial Reporting (AMFR) | 10.1.2 Enterprise Add or Modify Statewide ChartField Values | GL | General Ledger | E | Tier | Definition
Account Management and Financial Reporting (AMFR) | 10.1.3 Enterprise Add or Modify Fund Values | GL | General Ledger | E | T1 | Priority
Account Management and Financial Reporting (AMFR) | 10.1.4 Enterprise Add or Modify Budgetary ChartField Values | GL | General Ledger | E | T2 | Secondary
Account Management and Financial Reporting (AMFR) | 10.1.5 Enterprise Set Up and Maintain Trees and/or Combination Edits | GL | General Ledger | E | T3 | Not Priority
Account Management and Financial Reporting (AMFR) | 10.1.6 Agency Set Up and Maintain SpeedKeys | GL | General Ledger | T1 | T4 | Monthly/Quarterly
Account Management and Financial Reporting (AMFR) | 10.2.1 Source Module Journal Entry | GL | General Ledger | T1 | T5 | Year End
Account Management and Financial Reporting (AMFR) | 10.2.2 Edit Check | GL | General Ledger | T1 | E | Enterprise
Account Management and Financial Reporting (AMFR) | 10.2.3 Agency Create and Approve Journals | GL | General Ledger | T2
Account Management and Financial Reporting (AMFR) | 10.2.4 Enterprise Create and Approve Journals | GL | General Ledger | E
Account Management and Financial Reporting (AMFR) | 10.3.1 Perform Month End Close | GL | General Ledger | T3
Account Management and Financial Reporting (AMFR) | 10.4 Close General Ledger and Consolidate Results | GL | General Ledger | T5
Payroll (PR) | 100.1 Set Up and Maintain Positions | PAY | Payroll | T1
Payroll (PR) | 100.2.1 Personal Data | PAY | Payroll | T1
Payroll (PR) | 100.2.2 Payroll Data | PAY | Payroll | T1
Payroll (PR) | 100.2.3 Retirement Data | PAY | Payroll | T1
Payroll (PR) | 100.2.4 Deferred Compensation | PAY | Payroll | T1
Payroll (PR) | 100.2.5 Garnishments | PAY | Payroll | T1
Payroll (PR) | 100.3.1 Create, Load, and Manage Paysheets | PAY | Payroll | T1
Payroll (PR) | 100.3.2 Calculate Payroll | PAY | Payroll | T1
Payroll (PR) | 100.3.3 Update Paysheets | PAY | Payroll | T1
Payroll (PR) | 100.3.4 Confirm Payroll | PAY | Payroll | T1
Payroll (PR) | 100.3.5 Manage ACH Feeds | PAY | Payroll | T1
Payroll (PR) | 100.3.6 Distribute Payroll Warrants | PAY | Payroll | T1
Payroll (PR) | 100.4.1 Off-Cycle Processing | PAY | Payroll | T1
Payroll (PR) | 100.4.2 Beneficiary Payments | PAY | Payroll | T1
Payroll (PR) | 100.4.3 Online Check | PAY | Payroll | T1
Payroll (PR) | 100.5.1 Validate SSA Information | PAY | Payroll | T1
Payroll (PR) | 100.5.2 Manage Stale Payroll Warrants | PAY | Payroll | T1
Payroll (PR) | 100.5.3 Run Outbound Miscellaneous Interfaces | PAY | Payroll | T1
Payroll (PR) | 100.6.1 Record Overpayments and Recovery | PAY | Payroll | T1
Payroll (PR) | 100.6.2 Manage ACH Returns and Reissued Warrants | PAY | Payroll | T1
Payroll (PR) | 100.6.3 Reverse Unreconciled Warrants | PAY | Payroll | T1
Payroll (PR) | 100.6.4 Adjust Retirement Earnings and Contributions | PAY | Payroll | T1
Payroll (PR) | 100.6.5 Record Non-Cash, Fringe, and Other Adjustments | PAY | Payroll | T1
Payroll (PR) | 100.7.1 Set Up Position Distributions | PAY | Payroll | T1
Payroll (PR) | 100.7.2 Generate Payroll Accounting Distributions | PAY | Payroll | T1
Payroll (PR) | 100.7.3 Process Redistributions | PAY | Payroll | T1
Payroll (PR) | 100.8.1 Process Daily Payroll Tax Data | PAY | Payroll | T1
Payroll (PR) | 100.8.2 Reconcile Monthly Payroll Taxes | PAY | Payroll | T1
Payroll (PR) | 100.8.3 Prepare Quarterly Payroll Taxes | PAY | Payroll | T1
Payroll (PR) | 100.8.4 Produce Employee W-2 Forms | PAY | Payroll | T1
Payroll (PR) | 100.8.5 Produce Employee W-2c Forms | PAY | Payroll | T1
Payroll (PR) | 100.8.6 Maintain Fiscal Year End Updates | PAY | Payroll | T1
Payroll (PR) | 100.8.7 Process Year End Off-Cycles | PAY | Payroll | T1
Payroll (PR) | 100.8.8 Reset Employee W-4 Exempt Status | PAY | Payroll | T1
Inter/IntraUnit (IU) | 110.1.1 Create and Maintain Inter/IntraUnit Encumbrances | IU | Inter/Intra Unit | T1
Inter/IntraUnit (IU) | 110.1.2 Monitor Inter/IntraUnit Encumbrances | IU | Inter/Intra Unit | T1
Inter/IntraUnit (IU) | 110.2.1 Create and Maintain Inter/IntraUnit Accruals | IU | Inter/Intra Unit | T2
Inter/IntraUnit (IU) | 110.2.2 Monitor Inter/IntraUnit Accruals | IU | Inter/Intra Unit | T4
Inter/IntraUnit (IU) | 110.3.1 Agency Record Inter/IntraUnit Transactions | IU | Inter/Intra Unit | T3
Inter/IntraUnit (IU) | 110.3.2 Enterprise Record Inter/IntraUnit Transactions | IU | Inter/Intra Unit | E
Inter/IntraUnit (IU) | 110.3.3 Process GR Service Charge | IU | Inter/Intra Unit | T4
Inter/IntraUnit (IU) | 110.3.4 Manage Trust Fund Loans | IU | Inter/Intra Unit | T3
Inter/IntraUnit (IU) | 110.3.5 Inter/IntraUnit Reclassifications | IU | Inter/Intra Unit | T3
Inter/IntraUnit (IU) | 110.4.1 Inter/IntraUnit Period Close | IU | Inter/Intra Unit | T4
Inter/IntraUnit (IU) | 110.4.2 Inter/IntraUnit Carry Forward Process | IU | Inter/Intra Unit | T5
System Access Controls | 120.1.1 Interface File Error Handling | N/A | N/A | T1
System Access Controls | 120.1.2 Spreadsheet Upload Error Handling | N/A | N/A | T3
Budget Management and Cash Control (BMCC) | 20.1.1 Enterprise Post Appropriations | KK | Commitment Control | E
Budget Management and Cash Control (BMCC) | 20.1.2 Manage Agency Allotments | KK | Commitment Control | T1
Budget Management and Cash Control (BMCC) | 20.1.3 Enterprise Budget Ledger Reconciliation | KK | Commitment Control | E
Budget Management and Cash Control (BMCC) | 20.1.4 Agency Estimated Revenue | KK | Commitment Control | T5
Budget Management and Cash Control (BMCC) | 20.2.1 Manage Budget Checking | KK | Commitment Control | T1
Budget Management and Cash Control (BMCC) | 20.2.2 Manage Cash Checking | KK | Commitment Control | T1
Budget Management and Cash Control (BMCC) | 20.2.3 Invested Balance Checking | KK | Commitment Control | T3
Budget Management and Cash Control (BMCC) | 20.3.1 Carry Forward | KK | Commitment Control | T5
Budget Management and Cash Control (BMCC) | 20.3.2 Certified Forward | KK | Commitment Control | T5
Budget Management and Cash Control (BMCC) | 20.3.3 Continuing Appropriations | KK | Commitment Control | T5
Disbursements Management (DM) | 30.1.1 Add and Update Suppliers Online | AP | Accounts Payable | E
Disbursements Management (DM) | 30.1.2 Import Suppliers | AP | Accounts Payable | E
Disbursements Management (DM) | 30.1.5 Manage Supplier Banks | AP | Accounts Payable | E
Disbursements Management (DM) | 30.2.1 Create and Maintain Encumbrances | PO | Purchasing | T2
Disbursements Management (DM) | 30.2.2 Monitor Encumbrances | PO | Purchasing | T2
Disbursements Management (DM) | 30.2.3 Establish Enterprise Encumbrances | PO | Purchasing | E
Disbursements Management (DM) | 30.3.1 Process Vouchers | AP | Accounts Payable | T1
Disbursements Management (DM) | 30.3.2 Voucher Matching | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.3.3 Review and Approve Vouchers | AP | Accounts Payable | T1
Disbursements Management (DM) | 30.3.5 Enterprise Process Vouchers | AP | Accounts Payable | E
Disbursements Management (DM) | 30.3.6 Prompt Payment Interest Calculation | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.3.7 Process Carry Forward Vouchers | AP | Accounts Payable | T5
Disbursements Management (DM) | 30.4.1 Process Pay Cycle | AP | Accounts Payable | T1
Disbursements Management (DM) | 30.4.2 Process Warrant Payments | AP | Accounts Payable | T1
Disbursements Management (DM) | 30.5.1 Record Manual Payments | AP | Accounts Payable | T1
Disbursements Management (DM) | 30.5.2 Manage ACH/EFT Notifications | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.5.3 Manage Stale Payments | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.5.4 Cancel and Reissue Payments | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.6 Manage Tax Reporting | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.7 Manage Accounts Payable Transactions | AP | Accounts Payable | T3
Asset Accounting and Management (AAM) | 40.1.1 Import Asset Add | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.1.2 Online Asset Add | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.1.3 Work in Progress | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.1.4 Leases | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.1 Deploy and Maintain Assets | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.2 InterUnit Asset Transfer | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.3 IntraUnit Asset Transfer | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.4 Asset Disposal | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.5 Physical Inventory | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.6 Asset Mass Transfer | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.3 Set Up and Maintain Asset Controls | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.4 Asset Management Pre-Period Close | AM | Asset Management | T3
Revenue Accounting (RA) | 50.1 Set Up and Maintain Customer | AR | Accounts Receivable | T3
Accounts Receivables (AR) | 60.1.1 Record AR | AR | Accounts Receivable | T5
Accounts Receivables (AR) | 60.1.2 Refund AR | AR | Accounts Receivable | T5
Accounts Receivables (AR) | 60.1.3 Write-Off AR | AR | Accounts Receivable | T5
Accounts Receivables (AR) | 60.1.4 AR Period Close | AR | Accounts Receivable | T5
Accounts Receivables (AR) | 60.2.1 Direct Journal Deposits | AR | Accounts Receivable | T1
Accounts Receivables (AR) | 60.2.2 AR Deposits | AR | Accounts Receivable | T5
Accounts Receivables (AR) | 60.2.3 Returned Items | AR | Accounts Receivable | T1
Accounts Receivables (AR) | 60.2.4 Manage Electronic Receipts Data | AR | Accounts Receivable | T1
Banking | 70.1 Manage Banking Relationships | TM | Treasury Management | T3
Banking | 70.2 Manage and Reconcile Bank Statements | TM | Treasury Management | T3
Banking | 70.4 Process Bank Cash Transfers | TM | Treasury Management | T3
Banking | 70.5 Reconcile Book to Bank Balances | TM | Treasury Management | T3
Banking | 70.6 Create and Maintain Deals | TM | Treasury Management | T3
Banking | 70.7 Manage Investment Pools | TM | Treasury Management | T3
Projects Management (PM) | 90.1.1 Add or Modify Project | PC | Project Costing | T3
Projects Management (PM) | 90.1.2 Add or Modify PC Activity | PC | Project Costing | T3
Projects Management (PM) | 90.1.3 Define Project Budget | PC | Project Costing | T3
Projects Management (PM) | 90.1.4 Add or Modify PC Chartfields | PC | Project Costing | T3
Projects Management (PM) | 90.1.5 Monitor and Closeout Project | PC | Project Costing | T3
Projects Management (PM) | 90.1.6 FCO Certified Forward Request | PC | Project Costing | T3
Projects Management (PM) | 90.1.7 Manager Transaction Review for Pcard Process | PC | Project Costing | T3
Projects Management (PM) | 90.1.8 Maintain Projects | PC | Project Costing | T3
Grants Management (GM) | 90.2.1 Add or Modify Grant | Grants | Custom Grant Page | T1
Grants Management (GM) | 90.2.2 Add or Modify ALN/CSFA | Grants | Custom Grant Page | T1
Grants Management (GM) | 90.2.3 Monitor and Closeout Grant | Grants | Custom Grant Page | T3
Grants Management (GM) | 90.2.4 Monitor CMIA | Grants | Custom Grant Page | T3
Contracts Management (CM) | 90.3.1 Add or Modify Contract | Grants | Custom Contract Page | T1
Contracts Management (CM) | 90.3.2 Monitor and Closeout Contract | Grants | Custom Contract Page | T3
DRAFT