## Success Factors
Measures / Internal Factors and Success Criteria
Number | Phase | Internal Factors | Success Criteria Tracking | Success Criteria | Internal Factor Status (In-Progress, Complete) | Success (Pass/Fail) | Internal Factor Date Start | Internal Factor End Date | Overall Status (On Track/ Delayed / Critically Delayed)
1 | Remediation | Agency Business System (ABS) Development |  | 100% Development Complete |  |  | 2024-09-01 | 2024-06-01
2 | Remediation | Unit Testing ABS (Agency Internal Testing with Applicable Areas) |  | 100% Unit Testing Complete |  |  | 2025-01-01 | 2025-06-01
3 | Remediation | PALM Configured Interface Values Provided to Agencies and Interface Error File Formats Provided to Agencies for Testing |  | 85-100% Configurations Complete |  |  | 2025-05-01 | 2025-07-01
4 | Remediation | Interface File Testing with PALM |  | 25-50% Successful With No Show Stopper Bugs |  |  | 2025-06-01 | 2025-08-01
5 | Remediation | Test Tier 2 Agency ABS Interface Testing (i.e. test information from Tier 1 ABS going to Tier 2 Agency ABS) |  | 100% Testing Complete |  |  | 2025-08-01 | 2025-11-01
| SG | Stage Gate 3 - Ready to begin UAT - July 30, 2025
6 | Training | SMEs Trained on PALM User Interface / System |  | 100% SME's are Trained |  |  | 2025-08-01 | 2025-11-01
7 | Training | Identified SMEs Completed UAT Prerequisite Training |  | 100% SMEs are Trained |  |  | 2025-06-01 | 2025-07-01
8 | Training | Version One SME UAT User Guide Complete |  | 100% Complete |  |  | 2025-07-01 | 2025-08-01
9 | Training | End Users Training on PALM User Interfaces and System |  | At Least 50-75% End Users Have Tested in Every Applicable Area |  |  | 2025-10-01 | 2025-12-01
10 | Training | PALM Users Know How To Access PALM |  | 50-75% of the Users Can Access PALM |  |  | 2025-08-12 | 2025-12-01
11 | UAT | Regardless of Go-Live date, UAT Must Start in August 2025 |  | 50-75% System Ready for UAT - Focus on Understanding PALM Process and Data Flow for Each Module |  |  | 2025-08-01 | 2026-05-01
12 | UAT | Complete Interface File Testing with PALM |  | 90% Successful With No Show Stopper Bugs |  |  | 2025-08-25 | 2025-10-26
13 | UAT | SMEs Successful Completion of PALM UAT |  | 100% SME's Have Completed UAT in PALM |  |  | 2025-08-01 | 2025-11-01
14 | UAT | All DFS A&A UAT Scenarios Tested |  | 100% DFS A&A Scenarios Tested Successfully |  |  | 2025-08-01 | 2026-05-01
15 | UAT | All DFS Treasury UAT Scenarios Tested |  | 100% DFS Treasury Scenarios Tested Successfully |  |  | 2025-08-01 | 2026-05-01
16 | Training | All Agency Users are Trained on Enterprise Owned ABS for PALM Changes (STMS, Pcard Works, MFMP, FACTS, and People First) |  | 80% Applicable Agency Staff Trained |  |  | 2025-09-01 | 2025-12-01
17 | Training | All Agency Users are Trained on Agency Owned ABS for PALM Changes |  | 50-75% Applicable Agency Staff Trained |  |  | 2025-09-01 | 2025-12-01
18 | UAT | Begin End Users PALM UAT |  | 50-75% End Users Have Started UAT |  |  | 2025-12-01 | 2026-05-01
19 | UAT | All Tier 1 and Tier 2 Identified Processes Tested in PALM |  | 100% Processes Tested Successfully |  |  | 2025-08-01 | 2025-11-01
20 | UAT | All Identified Test Cases Tier 1 and Tier 2 Tests Successful in PALM |  | 100% of the Test Cases are Tested Successfully |  |  | 2025-08-01 | 2025-11-01
21 | UAT | Test FYE Processes in PALM UAT |  | 100% YE Testing Complete |  |  | 2026-01-01 | 2026-04-01
| SG | Stage Gate 4 - Continue Deployment - January 30, 2026
22 | UAT | Show Stopper Bugs (i.e., Bills cannot be paid, Employees not paid, Revenue not recorded) |  | 100% Critical Bugs are Resolved |  |  | 2026-01-01 | 2026-04-01
23 | UAT | Complete End User PALM UAT |  | 75% End Users Have Completed UAT |  |  | 2025-12-01 | 2026-05-01
24 | PALM Training | Create, Update and Execute Agency Specific Training Based on PALM Training |  | 100% SME's Complete PALM training 25-50% End Users Complete Training |  |  | 2025-12-01 | 2026-05-01
25 | UAT | Orchestrated FYE Closing with DFS A&A/PALM/Agencies |  | 75-100% FYE Tasks Completed Successfully |  |  | 2026-04-01 | 2026-05-01
| SG | Stage Gate 5 - Agency Readiness - May 2026
26 | Go-Live Measures | Tier 1 and Tier 2 - To-Be Documentation of Processes Updated for PALM User Interface / Processes |  | 75% Complete |  |  | 2025-08-01 | 2025-12-01
27 | Go-Live Measures | Complete PALM Training for All End Users |  | 90% Complete |  |  | 2025-08-01 | 2026-05-01
28 | Go-Live Measures | Complete PALM Configuration |  | 90% Correct Configuration |  |  | 2025-01-01 | 2026-05-01
29 | Go-Live Measures | Complete PALM Conversion Mapping and Data Cleansing |  | 90% Correct Conversion |  |  | 2025-08-01 | 2026-05-01
30 | Go-Live Measures | PALM Role Mapping Accurate and Complete |  | 90% Complete |  |  | 2026-05-01 | 2026-07-01
31 | Go-Live Measures | Deployment Plan / Technical Plan |  | 95% Identified and Documented |  |  | 2026-01-01 | 2026-05-26
32 | Go-Live Measures | Readiness Implementation Plan - Business Plan / Coordination Between PALM, Enterprise Agencies, DFS, and all State Agencies Must Create a Template of Activities Based on Go-Live Timeframe (July 2026) |  | 100% Activities Identified and Implementation Plan Complete |  |  | 2026-01-01 | 2026-05-26
33 | Go-Live Measures | Chief of Finance Must Be Able to Guide and Direct Resources to the Right Module / Process / SME for Assistance / Training / Guidance |  | 100% Complete |  |  | 2026-02-01 | 2026-04-01
34 | Go-Live Measures | Create Agency Functional Help Desk |  | 100% Setup of Help Desk |  |  | 2026-01-01 | 2026-12-01
| SG | Stage Gate 6 - Deployment Readiness - June 17, 2026
35 | Go-Live Measures | Deploy Strike Teams to Assist Applicable Areas |  | 90% Ready |  |  | 2026-05-01 | 2026-07-01
36 | Go-Live Measures | Agency Dedicated Training Room |  | 100% Ready for Users |  |  | 2026-04-01 | 2026-12-01
37 | Go-Live Measures | Confirm Final Import of Configurations, Conversions, and Balances to Include LAS/PBS Appropriations for 2026-2027 |  | 100% Complete |  |  | 2026-04-01 | 2026-07-01
38 | Go-Live Measures | Agency Deploys in Accordance with the Readiness Implementation and Technical Deployment Plan |  | 100% Complete |  |  | 2026-07-01 | 2026-09-01
| SG | Stage Gate 7 - Confirm Deployment - July 2026
39 | Post Deploy | Hypercare |  |  |  |  | 2026-07-01 | 2026-12-01
| SG | Stage Gate 8 - Go-Live - July 2026
Notes
All dates are pending based on the final dates published by PALM Project
Each success factor is a snapshot based on the information we have from PALM Project
Please refer to the Success Factors Explanation Tab for further clarification of the phases.
|  | On Track | In-Progress
|  | Delayed | Complete
Critically Delayed

## Business Process Tiers
PALM Business Processes
Business Process Grouping | Business Process | Associated Process Module | Module | Tier Level | Tier | Definition
Account Management and Financial Reporting (AMFR) | 10.1.1 Agency Add or Modify ChartField Values | GL | General Ledger | T1 | T1 | Priority
Account Management and Financial Reporting (AMFR) | 10.1.2 Enterprise Add or Modify Statewide ChartField Values | GL | General Ledger | E | T2 | Secondary
Account Management and Financial Reporting (AMFR) | 10.1.3 Enterprise Add or Modify Fund Values | GL | General Ledger | E | T3 | Not Priority
Account Management and Financial Reporting (AMFR) | 10.1.4 Enterprise Add or Modify Budgetary ChartField Values | GL | General Ledger | E | T4 | Monthly/Quarterly
Account Management and Financial Reporting (AMFR) | 10.1.5 Enterprise Set Up and Maintain Trees and/or Combination Edits | GL | General Ledger | E | T5 | Year End
Account Management and Financial Reporting (AMFR) | 10.1.6 Agency Set Up and Maintain SpeedKeys | GL | General Ledger | T1 | E | Enterprise
Account Management and Financial Reporting (AMFR) | 10.2.1 Source Module Journal Entry | GL | General Ledger | T1
Account Management and Financial Reporting (AMFR) | 10.2.2 Edit Check | GL | General Ledger | T1
Account Management and Financial Reporting (AMFR) | 10.2.3 Agency Create and Approve Journals | GL | General Ledger | T2
Account Management and Financial Reporting (AMFR) | 10.2.4 Enterprise Create and Approve Journals | GL | General Ledger | E
Account Management and Financial Reporting (AMFR) | 10.3.1 Perform Month End Close | GL | General Ledger | T3
Account Management and Financial Reporting (AMFR) | 10.4 Close General Ledger and Consolidate Results | GL | General Ledger | T5
Payroll (PR) | 100.1 Set Up and Maintain Positions | PAY | Payroll | T1
Payroll (PR) | 100.2.1 Personal Data | PAY | Payroll | T1
Payroll (PR) | 100.2.2 Payroll Data | PAY | Payroll | T1
Payroll (PR) | 100.2.3 Retirement Data | PAY | Payroll | T1
Payroll (PR) | 100.2.4 Deferred Compensation | PAY | Payroll | T1
Payroll (PR) | 100.2.5 Garnishments | PAY | Payroll | T1
Payroll (PR) | 100.3.1 Create, Load, and Manage Paysheets | PAY | Payroll | T1
Payroll (PR) | 100.3.2 Calculate Payroll | PAY | Payroll | T1
Payroll (PR) | 100.3.3 Update Paysheets | PAY | Payroll | T1
Payroll (PR) | 100.3.4 Confirm Payroll | PAY | Payroll | T1
Payroll (PR) | 100.3.5 Manage ACH Feeds | PAY | Payroll | T1
Payroll (PR) | 100.3.6 Distribute Payroll Warrants | PAY | Payroll | T1
Payroll (PR) | 100.4.1 Off-Cycle Processing | PAY | Payroll | T1
Payroll (PR) | 100.4.2 Beneficiary Payments | PAY | Payroll | T1
Payroll (PR) | 100.4.3 Online Check | PAY | Payroll | T1
Payroll (PR) | 100.5.1 Validate SSA Information | PAY | Payroll | T1
Payroll (PR) | 100.5.2 Manage Stale Payroll Warrants | PAY | Payroll | T1
Payroll (PR) | 100.5.3 Run Outbound Miscellaneous Interfaces | PAY | Payroll | T1
Payroll (PR) | 100.6.1 Record Overpayments and Recovery | PAY | Payroll | T1
Payroll (PR) | 100.6.2 Manage ACH Returns and Reissued Warrants | PAY | Payroll | T1
Payroll (PR) | 100.6.3 Reverse Unreconciled Warrants | PAY | Payroll | T1
Payroll (PR) | 100.6.4 Adjust Retirement Earnings and Contributions | PAY | Payroll | T1
Payroll (PR) | 100.6.5 Record Non-Cash, Fringe, and Other Adjustments | PAY | Payroll | T1
Payroll (PR) | 100.7.1 Set Up Position Distributions | PAY | Payroll | T1
Payroll (PR) | 100.7.2 Generate Payroll Accounting Distributions | PAY | Payroll | T1
Payroll (PR) | 100.7.3 Process Redistributions | PAY | Payroll | T1
Payroll (PR) | 100.8.1 Process Daily Payroll Tax Data | PAY | Payroll | T1
Payroll (PR) | 100.8.2 Reconcile Monthly Payroll Taxes | PAY | Payroll | T1
Payroll (PR) | 100.8.3 Prepare Quarterly Payroll Taxes | PAY | Payroll | T1
Payroll (PR) | 100.8.4 Produce Employee W-2 Forms | PAY | Payroll | T1
Payroll (PR) | 100.8.5 Produce Employee W-2c Forms | PAY | Payroll | T1
Payroll (PR) | 100.8.6 Maintain Fiscal Year End Updates | PAY | Payroll | T1
Payroll (PR) | 100.8.7 Process Year End Off-Cycles | PAY | Payroll | T1
Payroll (PR) | 100.8.8 Reset Employee W-4 Exempt Status | PAY | Payroll | T1
Inter/IntraUnit (IU) | 110.1.1 Create and Maintain Inter/IntraUnit Encumbrances | IU | Inter/Intra Unit | T1
Inter/IntraUnit (IU) | 110.1.2 Monitor Inter/IntraUnit Encumbrances | IU | Inter/Intra Unit | T1
Inter/IntraUnit (IU) | 110.2.1 Create and Maintain Inter/IntraUnit Accruals | IU | Inter/Intra Unit | T2
Inter/IntraUnit (IU) | 110.2.2 Monitor Inter/IntraUnit Accruals | IU | Inter/Intra Unit | T4
Inter/IntraUnit (IU) | 110.3.1 Agency Record Inter/IntraUnit Transactions | IU | Inter/Intra Unit | T3
Inter/IntraUnit (IU) | 110.3.2 Enterprise Record Inter/IntraUnit Transactions | IU | Inter/Intra Unit | E
Inter/IntraUnit (IU) | 110.3.3 Process GR Service Charge | IU | Inter/Intra Unit | T4
Inter/IntraUnit (IU) | 110.3.4 Manage Trust Fund Loans | IU | Inter/Intra Unit | T3
Inter/IntraUnit (IU) | 110.3.5 Inter/IntraUnit Reclassifications | IU | Inter/Intra Unit | T3
Inter/IntraUnit (IU) | 110.4.1 Inter/IntraUnit Period Close | IU | Inter/Intra Unit | T4
Inter/IntraUnit (IU) | 110.4.2 Inter/IntraUnit Carry Forward Process | IU | Inter/Intra Unit | T5
System Access Controls | 120.1.1 Interface File Error Handling | N/A | N/A | T1
System Access Controls | 120.1.2 Spreadsheet Upload Error Handling | N/A | N/A | T3
Budget Management and Cash Control (BMCC) | 20.1.1 Enterprise Post Appropriations | KK | Commitment Control | E
Budget Management and Cash Control (BMCC) | 20.1.2 Manage Agency Allotments | KK | Commitment Control | T1
Budget Management and Cash Control (BMCC) | 20.1.3 Enterprise Budget Ledger Reconciliation | KK | Commitment Control | E
Budget Management and Cash Control (BMCC) | 20.1.4 Agency Estimated Revenue | KK | Commitment Control | T5
Budget Management and Cash Control (BMCC) | 20.2.1 Manage Budget Checking | KK | Commitment Control | T1
Budget Management and Cash Control (BMCC) | 20.2.2 Manage Cash Checking | KK | Commitment Control | T1
Budget Management and Cash Control (BMCC) | 20.2.3 Invested Balance Checking | KK | Commitment Control | T3
Budget Management and Cash Control (BMCC) | 20.3.1 Carry Forward | KK | Commitment Control | T5
Budget Management and Cash Control (BMCC) | 20.3.2 Certified Forward | KK | Commitment Control | T5
Budget Management and Cash Control (BMCC) | 20.3.3 Continuing Appropriations | KK | Commitment Control | T5
Disbursements Management (DM) | 30.1.1 Add and Update Suppliers Online | AP | Accounts Payable | E
Disbursements Management (DM) | 30.1.2 Import Suppliers | AP | Accounts Payable | E
Disbursements Management (DM) | 30.1.5 Manage Supplier Banks | AP | Accounts Payable | E
Disbursements Management (DM) | 30.2.1 Create and Maintain Encumbrances | PO | Purchasing | T2
Disbursements Management (DM) | 30.2.2 Monitor Encumbrances | PO | Purchasing | T2
Disbursements Management (DM) | 30.2.3 Establish Enterprise Encumbrances | PO | Purchasing | E
Disbursements Management (DM) | 30.3.1 Process Vouchers | AP | Accounts Payable | T1
Disbursements Management (DM) | 30.3.2 Voucher Matching | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.3.3 Review and Approve Vouchers | AP | Accounts Payable | T1
Disbursements Management (DM) | 30.3.5 Enterprise Process Vouchers | AP | Accounts Payable | E
Disbursements Management (DM) | 30.3.6 Prompt Payment Interest Calculation | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.3.7 Process Carry Forward Vouchers | AP | Accounts Payable | T5
Disbursements Management (DM) | 30.4.1 Process Pay Cycle | AP | Accounts Payable | T1
Disbursements Management (DM) | 30.4.2 Process Warrant Payments | AP | Accounts Payable | T1
Disbursements Management (DM) | 30.5.1 Record Manual Payments | AP | Accounts Payable | T1
Disbursements Management (DM) | 30.5.2 Manage ACH/EFT Notifications | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.5.3 Manage Stale Payments | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.5.4 Cancel and Reissue Payments | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.6 Manage Tax Reporting | AP | Accounts Payable | T3
Disbursements Management (DM) | 30.7 Manage Accounts Payable Transactions | AP | Accounts Payable | T3
Asset Accounting and Management (AAM) | 40.1.1 Import Asset Add | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.1.2 Online Asset Add | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.1.3 Work in Progress | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.1.4 Leases | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.1 Deploy and Maintain Assets | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.2 InterUnit Asset Transfer | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.3 IntraUnit Asset Transfer | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.4 Asset Disposal | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.5 Physical Inventory | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.2.6 Asset Mass Transfer | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.3 Set Up and Maintain Asset Controls | AM | Asset Management | T3
Asset Accounting and Management (AAM) | 40.4 Asset Management Pre-Period Close | AM | Asset Management | T3
Revenue Accounting (RA) | 50.1 Set Up and Maintain Customer | AR | Accounts Receivable | T3
Accounts Receivables (AR) | 60.1.1 Record AR | AR | Accounts Receivable | T5
Accounts Receivables (AR) | 60.1.2 Refund AR | AR | Accounts Receivable | T5
Accounts Receivables (AR) | 60.1.3 Write-Off AR | AR | Accounts Receivable | T5
Accounts Receivables (AR) | 60.1.4 AR Period Close | AR | Accounts Receivable | T5
Accounts Receivables (AR) | 60.2.1 Direct Journal Deposits | AR | Accounts Receivable | T1
Accounts Receivables (AR) | 60.2.2 AR Deposits | AR | Accounts Receivable | T5
Accounts Receivables (AR) | 60.2.3 Returned Items | AR | Accounts Receivable | T1
Accounts Receivables (AR) | 60.2.4 Manage Electronic Receipts Data | AR | Accounts Receivable | T1
Banking | 70.1 Manage Banking Relationships | TM | Tresury Management | T3
Banking | 70.2 Manage and Reconcile Bank Statements | TM | Tresury Management | T3
Banking | 70.4 Process Bank Cash Transfers | TM | Tresury Management | T3
Banking | 70.5 Reconcile Book to Bank Balances | TM | Tresury Management | T3
Banking | 70.6 Create and Maintain Deals | TM | Tresury Management | T3
Banking | 70.7 Manage Investment Pools | TM | Tresury Management | T3
Projects Management (PM) | 90.1.1 Add or Modify Project | PC | Project Costing | T3
Projects Management (PM) | 90.1.2 Add or Modify PC Activity | PC | Project Costing | T3
Projects Management (PM) | 90.1.3 Define Project Budget | PC | Project Costing | T3
Projects Management (PM) | 90.1.4 Add or Modify PC Chartfields | PC | Project Costing | T3
Projects Management (PM) | 90.1.5 Monitor and Closeout Project | PC | Project Costing | T3
Projects Management (PM) | 90.1.6 FCO Certified Forward Request | PC | Project Costing | T3
Projects Management (PM) | 90.1.7 Manager Transaction Review for Pcard Process | PC | Project Costing | T3
Projects Management (PM) | 90.1.8 Maintain Projects | PC | Project Costing | T3
Grants Management (GM) | 90.2.1 Add or Modify Grant | Grants | Custom Grant Page | T1
Grants Management (GM) | 90.2.2 Add or Modify ALN/CSFA | Grants | Custom Grant Page | T1
Grants Management (GM) | 90.2.3 Monitor and Closeout Grant | Grants | Custom Grant Page | T3
Grants Management (GM) | 90.2.4 Monitor CMIA | Grants | Custom Grant Page | T3
Contracts Management (CM) | 90.3.1 Add or Modify Contract | Grants | Custom Contract Page | T1
Contracts Management (CM) | 90.3.2 Monitor and Closeout Contract | Grants | Custom Contract Page | T3

## Success Factors Explanations
Internal Factors and Success Criteria Explanations
Remediation Phase (Prior to Stage Gate 3): Agencies should be working to complete preparation tasks prior to PALM Training and UAT.
Training/UAT Phase (Prior to Stage Gate 4): Agency SMEs should be focusing on tasks related to the Training/UAT Phase. This phase is also where the intention is to develop agency specific processes and work through most, if not all bugs in preparation for full end-user UAT.
UAT/PALM Training (Prior to Stage Gate 5): All agency end-users should be focusing on tasks related to the Training/UAT Phase.
Go-Live Measures Phase (Prior to Stage Gate 6): Agencies have been trained, participated in UAT, worked through agency processes and prepared as much as possible for GoLive. In addition, agencies should have identified any outstanding issues and developed mitigation strategies, as applicable.
Go-Live Measures Phase (Prior to Stage Gate 7): Agencies have staff/teams in place to deploy to offices/areas which are experiencing difficulties in transitioning to the new system. In addition, dedicated training facilities are available for staff to receive additional training and assistance from SMEs. Agency SMEs will also confirm configurations, conversions and balances are accurate for Go-Live.
Post Deploy Phase (Prior to Stage Gate 8): All agency processes, all business owners, and techical staff are fully supporting the system and end-users with ongoing operations.