## Slide 2: Executive Steering Committee
Department of Financial Services
March 27, 2023
Notes: Steven
Hello! Let’s get started with a roll call.
Jamie Grant
Hunter Jones
Mike Jones
Matt Kirkland
Angie Martin
Mark Merry
Tomy Mollas
Robin Naitove
Cliff Nilson
Jennifer Pelham
Shannon Segers
Christina Smith
Lynn Smith
Scott Stewart
Dan Zimmerman

## Slide 3: Project Risks/Issues and Budget
Tommy Werner

## Slide 4: Florida PALM Project Update Budget – Fiscal Year 22-23
FY 2022-2023 Spend Plan Summary As of February 28, 2023
Category | Projected FYTD | Incurred FYTD | Released FYTD | Release Remaining
FLAIR System Replacement | $16,737,026 | $16,737,026 | $20,100,103 | $3,363,077
CMS Remediation and Stabilization | $1,000,000 | $1,000,000 | $1,000,000 | $0
Production Support | $5,530,850 | $5,530,850 | $6,131,839 | $600,989
Oracle Software and Maintenance | $1,113,203 | $1,113,203 | $1,114,424 | $1,221
Operational Project Administration | $56,138 | $56,138 | $135,620 | $79,482
Staff Augmentation | $652,510 | $652,510 | $1,076,300 | $423,790
Information Warehouse Assessment | $487,096 | $487,096 | $500,000 | $12,904
Facilities and Maintenance | $634,975 | $634,975 | $714,420 | $79,445
Revert/Appropriate from FY 21-22 | $7,262,254 | $7,262,254 | $8,392,500 | $1,130,246
Implementation Services | $0 | $0 | $1,035,000 | $1,035,000
Contingency | $0 | $0 | $0 | $0
Settlement Agreement | $5,991,399 | $5,991,399 | $5,991,399 | $0
Salaries & Benefits | $3,877,451 | $3,877,451 | $6,525,356 | $2,647,905
HR Transfer and Risk Management Insurance | $19,269 | $19,269 | $23,377 | $4,108
Total: | $26,625,145 | $26,625,145 | $32,640,235 | $6,015,090
Notes: Tommy
General
  We added a baseline adjustment to free up funds to purchase Oracle Time and Labor module in FY 22-23
  Budget amendment has been submitted for a Q4 release

## Slide 5: Florida PALM Project Update Risks and Issues 22-23
Since the last ESC meeting, no Risks or Issues have been opened or closed
Issue 27 – Schedule delays prevented a fully committed Project schedule
There are no open Risks with a score of 15 or greater
Notes: Tommy
*This slide may changed based on Risk conversation on 3/14/23
ISSUES
    Issue 27 will remain open until the Project Schedule is updated after the execution of A8
    Q3 tasks have been added to the schedule
RISKS
    There are no Risks with a score of 15 or greater
    This slide may changed based on Risk conversation on 3/14/23

## Slide 6: Independent Validation and Verification (IV&V)
Content provided by
Public Consulting Group

## Slide 7
The Florida PALM IV&V Team received the following Amendment 8 Attachments for review on these dates:
IV&V Update Amendment 8 Attachments Reviewed in 2023
Attachments | Description | IV&V Received Dates
5.1 | Business Requirements | 03/06/23
5.2 | Customizations | 03/06/23
8 | Deliverable Acceptance Criteria | 03/13/23
2 | Payment Schedule | 03/14/23

## Slide 8
IV&V received and reviewed the Amendment 8 Business Requirements, Customizations, Deliverable Acceptance Criteria, and Payment Schedule Attachments.
IV&V discussed questions and feedback on the documents with Florida PALM Project Team representatives on 3/22/23 and 3/23/23.
Additionally, IV&V discussed responses to the Florida PALM Project Team comments on the first IV&V review of the Statement of Work and Definitions.
Initial review of all Amendment 8 Attachments is now complete, although further review may be conducted upon Florida PALM Project Team request.
IV&V Update Amendment 8 Attachments Reviewed in 2023

## Slide 9
IV&V reviewed the Agency Status Reports to improve them as a tool of Agency communication with the Florida Legislature and ESC and discussed the context of their implementation and usage with the Florida PALM Project Team.
IV&V reviewed industry best practices and leveraged our experience in what has worked in similar projects in other states.
IV&V shared final results and recommendations with the Florida PALM Project Team in the 3/17/23 IV&V Weekly Status Report.
IV&V Update Florida PALM Project Agency Status Reports

## Slide 10: IV&V Update Open Findings
IV&V currently has no Open Findings.

## Slide 11
The final version of the Comprehensive Assessment was submitted to the Florida PALM Distribution List on 3/7/23 and included a recommended timeline for implementation of IV&V recommendations as well as comments and feedback from DFS.
The Comprehensive Assessment Team presented the assessment at a hearing before the House State Administration & Technology Appropriations Subcommittee along with the Florida PALM Project Team on 3/7/23.
IV&V Update Florida PALM Comprehensive Assessment

## Slide 12: Project Update
Jimmy Cox, Nikki Klein,
Deana Metcalf

## Slide 13: Florida PALM Project Update Readiness Activities
March 21 Town Hall
RW Task to Update Current State Agency Business System Inventory and Documentation
January
February
March
April
May
June
July
August
September
October
November
December
Complete FLAIR Data Elements Inventory
Complete Reports Inventory
Update Current State Agency Business System Inventory and Documentation
Document Current Agency Business Processes
Complete Data Security
and Access Survey
2023
Notes: Nikki
Town Hall was held on March 21 with ## in attendance represent ## agencies. Topics included:
  Recap of the Personalized Agency Working Sessions
  Overview of the timeline and with expectations of agencies and their end users along the implementation journey
  the most recent RW task for agencies to Update Current State Agency Business System Inventory and Documentation – We had an agency share their approach to completing the task
  the importance of Communication for successful transformation. An agency shared how the communicated with their field offices for a successful implementation of Pcard Works
  Some Florida PALM fundamentals
RW Task 326 Update Current State Agency Business System Inventory and Documentation was released. Agencies will use this information to help with their Transformation Plan and to prioritize their remediation work.

## Slide 14: Florida PALM Project Update Project and Agency Activities
14
Agency Activity
Project Activity
Legend
Notes: Speaker – Angie
This image takes the Implementation Timeline and overlays agency activity phases
This is a high level depiction of agency activities in yellow with Project activities in blue.
<<NEXT SLIDE>>

## Slide 15: Florida PALM Project Update Project Change Requests
Project Change Requests
  PCR97 – GLE011 Zero Dollar Budget Journals
  PCR98 – GLR150 Balance Summary Register Report
Notes: PCR 97 – Auto create zero dollar budget journals, to support posting of Investment activities to the GL. Currently where a zero dollar budget journal is needed, this must be manually created by Treasury staff members.
PCR 98 – Modifications are primarily based on using the new reporting categorization that was created under PCR 92. This supports providing treasury with the applicable information needed to complete meet the requirements for this portion of the Governors report.

## Slide 16: Florida PALM Project Update
Legislative Session Updates
Amendment 8 Review

## Slide 17: SSI Contract Approval Approach and Ground Rules
Start with discussion of changes to previously reviewed attachments
Members provide feedback as each document is discussed
Move to discussion of remaining attachments, beginning with Project team overview and summary
Audience attendees may be asked to leave the meeting for discussion of confidential or proprietary information

## Slide 18: SSI Contract Approval Cadence for the Week
Attachments Previously Reviewed
  Attachment 6 - Definitions
  Contract Document
  Attachment 1 – Statement of Work
  Attachment 10 – Service Level Agreement
Remaining Attachments
  Attachment 5.1 – Business Requirements
  Attachment 5.2 – Customizations
  Attachment 8 – Deliverable Acceptance Criteria
  Attachment 2 – Payment Schedule
Vote on Amendment 8 package (Contract and all Attachments)

## Slide 19: Upcoming
Jimmy Cox
Notes: Meetings through Friday…

## Slide 20: Florida PALM Project Update Upcoming Meetings
3/28 – 3/31 Amendment 8 Discussions

## Slide 21: Contact Information
FloridaPALM@MyFloridaCFO.com
MyFloridaCFO.com/FloridaPALM