## Monthly Summary
Department of Financial Services
Florida PALM FY 2023 - 2024 Spend Plan Summary FYTD | [31 empty] | ``
As of May 31, 2024
| Annual |  |  |  |  | July 2023 |  |  |  | August 2023 |  |  |  | September 2023 |  |  |  | Q2 Baseline Adjustment | October 2023 |  |  |  | November 2023 |  |  |  | December 2023 |  |  |  | Q3 Baseline Adjustment | January 2024 |  |  |  | February 2024 |  |  |  | March 2024 |  |  |  | Q4 Baseline Adjustment | April 2024 |  |  |  | May 2024 |  |  |  | June 2024 |  |  | CF 2023-24 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 0 | 0 | 0 | 43227717.965 | 0 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| Appropriated | Released | Unreleased | Projected | Release Remaining
FLAIR System Replacement (100781) | 44440408 | 43537735 | 902673 | 43227717.965 | 5410135.54 | 1318418.8608 | 1182932.44 |  | 429853.44 | 4873634.4258 | 4331673.82 |  | 851326.02 | 887276.8608 | 2405994.26 |  | 4269691.06 | 841270.3725 | 2754648.1225 | 2626462.64 |  | 3076890.74 | 4851894.055 | 4572518.11 |  | 1583128.9 | 3180346.4875 | 3388470.42 |  | 4213918.64 | -199437.495 | 1493340.5225 | 1320913.78 |  | 4900831.24 | 4345465.3675 | 4291776.99 |  | 499446.9 | 8029291.79 | 7924052.64 |  | 5053809.02 | -331354.27 | 4747950.7633 | 2317811.26 |  | 8965847.23 | 1699789.6583 | 3764993.1 |  | 1693655.8 | 4735182.4433 | 0 | 0 | 0 | 0 | 38492535.5217 | 38127599.46 | 35538398.99 | 5100118.505 | 11.8%
SSI Implementation Services (FP004) |  |  |  | 29745300 |  | 0 | 0 | 3 | 0 | 3415500 | 3415500 |  | 0 | 0 | 1500000 |  | 3415500 | 1500000 | 1448400 | 1448400 |  | 1500000 | 3415500 | 3415500 |  | 1448400 | 2310500 | 2310500 |  | 3415500 | 0 | 0 | 0 |  | 2310500 | 3415500 | 3415500 |  | 0 | 7024400 | 7024400 |  | 3415500 | 0 | 3250000 | 1000000 | 2 | 8024400 | 550000 | 2800000 | 3 | 550000 | 3415500 | 0 | 0 | 0 | 0 | 26329800 | 26329800 | 24079800 | 3415500 | 11.48%
Facilities and Maintenance (FP004) |  |  |  | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 0 | 0 | 0 | 0 | 381051 | 381051 | 381051 | 34641 | 8.333%
Production Support (FP004) |  |  |  | 8752151 |  | 1068287 | 1034011 |  | 390692 | 664400 | 664400 |  | 643319 | 664400 | 664400 |  | 664400 | -34276 | 805457 | 785758 |  | 1450158 | 664400 | 664400 |  | 0 | 664400 | 664400 |  | 664400 | -19699 | 805457 | 805457 |  | 1469857 | 664400 | 664400 |  | 0 | 664400 | 664400 |  | 1328800 | 0 | 811725 | 811725 |  | 811725 | 664400 | 551900 | 5 | 551900 | 664400 | 0 | 0 | 0 | 0 | 8087751 | 7975251 | 7975251 | 776900 | 8.877%
Production Support Administration |  |  |  | 47904.26 |  | 2405.2 | 2384.34 |  | 2384.34 | 2405.2 | 0.1 | 2 | 0.1 | 2405.2 | 4768.8 | 3 | 4768.8 | -62.36 | 2405.2 | 2384.15 |  | 2384.15 | 7405.2 | 2383.44 | 2 | 0.18 | 20405.2 | 2284.07 | 2 | 2383.44 | -23163.94 | 21738.64 | 21716.88 |  | 6745.34 | 2405.2 | 2383.44 |  | 2383.44 | 2405.2 | 2383.44 |  | 19638.87 | -65.28 | 2405.2 | 2383.44 |  | 0.18 | 2405.2 | 2971.52 |  | 2971.52 | 2405.2 | 0 | 0 | 0 | 0 | 45499.06 | 46043.62 | 43660.36 | 1860.64 | 3.884%
Oracle Software and Maintenance (FP005) |  |  |  | 2123515.755 |  | 9749.8308 | 0 | 2 | 0 | 597217.3958 | 0 | 2 | 0 | 9749.8308 | 0 | 2 | 0 | -616717.0575 | 321911.8525 | 321911.9 |  | 0 | 597217.395 | 343867.57 | 2 | 0 | 9749.8308 | 241860 | 3 | 37782.98 | -21239.6083 | 354061.7325 | 321916.11 |  | 869856.49 | 77811.5875 | 15755.58 |  | 321911.9 | 10981.83 | 57579.29 | 3 | 67919.94 | -47604.17 | 354061.73 | 324853.48 |  | 0 | 77765.465 | 89105.8 | 3 | 330178.5 | 388798.11 | 0 | 0 | 0 | 0 | 1734717.645 | 1716849.73 | 1627649.81 | 406666.025 | 19.15%
Project Administration |  |  |  | 150000 |  | 63935.83 | 2136.1 | 2 | 2136.1 | 3910.83 | 70252.72 | 3 | 63605.92 | 40680.83 | 67224.46 | 2 | 73871.26 | 31085.79 | -38766.93 | -115622.41 |  | -115622.41 | 4050.46 | 116.1 | 2 | 97.72 | 5250.4567 | 10370.35 | 3 | 10211.22 | -75669.9467 | 66592.15 | 6062.79 | 2 | 6006.41 | 8587.58 | 18276.97 | 3 | 18330.56 | 13587.58 | 4568.91 | 2 | 4749.21 | -59858.64 | 51451.6533 | 6318.34 | 2 | 6061.05 | 26600.4033 | 49917.49 | 6 | 49917.49 | 8561.9533 | 0 | 0 | 0 | 0 | 141438.0467 | 119621.82 | 119364.53 | 30378.18 | 20.25%
Additional Facilities |  |  |  | 84649.95 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 10756.18 | 0 |  | 0 | -10756.18 | 10756.18 | 0 | 2 | 0 | 63137.59 | 29637.29 | 2 | 29637.29 | 10756.18 | 0 | 0 | 0 | 0 | 73893.77 | 29637.29 | 29637.29 | 55012.66 | 64.99%
ERP and OC Support Services |  |  |  | 1701785 |  | 139400 | 109760 | 1 | 0 | 155560 | 146880 | 1 | 109760 | 135400 | 134960 |  | 76510 | -38760 | 180600 | 148990 | 2 | 205330 | 128680 | 111610 | 1 | 99990 | 135400 | 124415 |  | 49000 | -59665 | 210850 | 131120 | 2 | 203225 | 142120 | 140820 |  | 122180 | 142120 | 136080 |  | 182560 | -87070 | 232910 | 137890 | 1 | 89020 | 148840 | 149340 |  | 144410 | 135400 | 0 | 0 | 0 | 0 | 1566385 | 1471865 | 1281985 | 229920 | 13.51%
QA Support Services |  |  |  | 206720 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 126000 | 0 | 1 | 0 | -126000 | 0 | 0 |  | 0 | 132000 | 57480 | 1 | 0 | 74720 | 0 | 0 | 0 | 0 | 132000 | 57480 | 0 | 149240 | 72.19%
IT Service Management Implementation and Software (100777) | 2000000 | 2000000 | 0 | 818477.35 | 1304572.67 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13147.67 | 0 |  | 0 | 813420 | 665806.67 |  | 13147.67 | 27887 | 8738.94 |  | 652659 | -179909.06 | 37125.82 | 9238.82 |  | 0 | 11642.9 | 11642.9 |  | 17977.76 | 95163.02 | 0 | 0 | 0 | 0 | 723314.33 | 695427.33 | 683784.43 | 123050.02 | 15.03%
ITSM Implementation |  |  |  | 154175.45 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13147.67 | 0 |  | 0 | 0 | 13147.67 | 3 | 13147.67 | 27887 | 8738.94 | 2 | 0 | -19148.06 | 37125.82 | 9238.82 | 2 | 0 | 0 | 0 |  | 17977.76 | 95163.02 | 0 | 0 | 0 | 0 | 59012.43 | 31125.43 | 31125.43 | 123050.02 | 79.81%
ITSM Software |  |  |  | 664301.9 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 813420 | 652659 | 2 | 0 | 0 | 0 |  | 652659 | -160761 | 0 | 0 |  | 0 | 11642.9 | 11642.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 664301.9 | 664301.9 | 652659 | 0 | 0%
Contingency (100819) | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
DMS IV&V Transfer (100821) | 6053061 | 6053061 | 0 | 6053061 | 0 | 6053061 | 6053061 |  | 6053061 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6053061 | 6053061 | 6053061 | 0 | 0%
Salaries & Benefits (010000) | 9743087 | 9743087 | 0 | 7380813.25 | 3216246.96 | 754567.06 | 496925.61 |  | 496925.61 | 754567.06 | 530433.8 |  | 530433.8 | 754567.06 | 492961.02 |  | 492961.02 | -743380.75 | 754567.06 | 605694.6 |  | 81645.96 | 754567.06 | 510087.05 |  | 1034135.69 | 754567.06 | 545810.22 |  | 545810.22 | -602109.31 | 754567.06 | 629627 |  | 629627 | 754567.06 | 633547.59 |  | 633547.59 | 754567.06 | 672025.18 |  | 672025.18 | -328501.41 | 754567.06 | 706587.76 |  | 706587.76 | 754567.06 | 703140.21 |  | 703140.21 | 754567.06 | 0 | 0 | 0 | 0 | 6626246.19 | 6526840.04 | 6526840.04 | 853973.21 | 11.57%
Risk Management Insurance (103241) | 7978 | 7978 | 0 | 7978 | 0 | 6944 | 0 |  | 0 | 0 | 7978 |  | 7978 | 0 | 0 |  | 0 | 1034 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7978 | 7978 | 7978 | 0 | 0%
DMS HR Transfer (107040) | 24609 | 24609 | 0 | 24609 | 0 | 5818.25 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5818.25 | 11636.5 | 6152.25 |  | 6152.25 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5484.25 | 6152.25 | 6152.25 |  | 6152.25 | 0 | 6152.25 |  | 6152.25 | 0 | 0 |  | 0 | 6152.25 | 6152.25 | 6152.25 |  | 6152.25 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 24609 | 24609 | 24609 | 0 | 0%
Totals | 63769143 | 61366470 | 2402673 | 57512656.565 | 9930955.17 | 8138809.1708 | 7732919.05 |  | 6979840.05 | 5628201.4858 | 4870085.62 |  | 1389737.82 | 1641843.9208 | 2898955.28 |  | 4762652.08 | 93105.3725 | 3520851.6825 | 3238309.49 |  | 3164688.95 | 5606461.115 | 5082605.16 |  | 2617264.59 | 3934913.5475 | 3934280.64 |  | 4759728.86 | -807031.055 | 2267207.5025 | 1956693.03 |  | 5536610.49 | 5913452.4275 | 5597283.5 |  | 1152294.41 | 8811745.85 | 8604816.76 |  | 6378493.2 | -833612.49 | 5545795.8933 | 3039790.09 |  | 9678587.24 | 2465999.6183 | 4479776.21 |  | 2414773.77 | 5584912.5233 | 0 | 0 | 0 | 0 | 51927744.0417 | 51435514.83 | 48834671.46 | 6077141.735 | 10.57%
Running Totals | [5 empty] | 8138809.1708 | 7732919.05 |  | 6979840.05 | 13767010.6567 | 12603004.67 |  | 8369577.87 | 15408854.5775 | 15501959.95 |  | 13132229.95 | 15501959.95 | 19022811.6325 | 18740269.44 |  | 16296918.9 | 24629272.7475 | 23822874.6 |  | 18914183.49 | 28564186.295 | 27757155.24 |  | 23673912.35 | 27757155.24 | 30024362.7425 | 29713848.27 |  | 29210522.84 | 35937815.17 | 35311131.77 |  | 30362817.25 | 44749561.02 | 43915948.53 |  | 36741310.45 | 43915948.53 | 49461744.4233 | 46955738.62 |  | 46419897.69 | 51927744.0417 | 51435514.83 |  | 48834671.46 | 57512656.565 | 51435514.83 | 48834671.46 |  | 48834671.46 |  | Total Incurred/Total Projected FYTD | Total Incurred/Total Projected FYTD |  | 99.05%
Monthly Total Incurred/Total Projected | [5 empty] | 95.01% |  |  |  | 86.53% |  |  |  | 176.6% |  |  |  |  | 91.98% |  |  |  | 90.66% |  |  |  | 99.98% |  |  |  |  | 86.3% |  |  |  | 94.65% |  |  |  | 97.65% |  |  |  |  | 54.81% |  |  |  | 181.7% |  |  |  | 0% | [5 empty] | Total Paid/Total Projected FYTD | Total Paid/Total Projected FYTD |  | 94.04%
Monthly Total Incurred/Total Projected (Variance) | [5 empty] | -4.987% |  |  |  | -13.47% |  |  |  | 76.57% |  |  |  |  | -8.025% |  |  |  | -9.344% |  |  |  | -0.01608% |  |  |  |  | -13.7% |  |  |  | -5.347% |  |  |  | -2.348% |  |  |  |  | -45.19% |  |  |  | 81.66% |  |  |  | -100%
FYTD Total Incurred/Total Projected | [5 empty] | 95.01% |  |  |  | 91.54% |  |  |  | 100.6% |  |  |  |  | 98.51% |  |  |  | 96.73% |  |  |  | 97.17% |  |  |  |  | 98.97% |  |  |  | 98.26% |  |  |  | 98.14% |  |  |  |  | 94.93% |  |  |  | 99.05% |  |  |  | 89.43% | [5 empty] | Total Release/Total Appropriation | Total Release/Total Appropriation |  | 96.23%
FYTD Total Incurred/Total Projected (Variance) | [5 empty] | -4.987% |  |  |  | -8.455% |  |  |  | 0.6042% |  |  |  |  | -1.485% |  |  |  | -3.274% |  |  |  | -2.825% |  |  |  |  | -1.034% |  |  |  | -1.744% |  |  |  | -1.863% |  |  |  |  | -5.067% |  |  |  | -0.9479% |  |  |  | -10.57%
[59 empty] | Total Paid/Total Release | Total Paid/Total Release |  | 79.58%
`
Note on BH11: Werner, Tommy: July

## SSI
|  |  | July 2023 |  |  | August 2023 |  |  | September 2023 |  |  |  | October 2023 |  |  | November 2023 |  |  | December 2023 |  |  |  | January 2024 |  |  | February 2024 |  |  | March 2024 |  |  |  | April 2024 |  |  | May 2024 |  |  | June 2024 |  |  | CF 2022-23
|  | Description | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid | Q2 Baseline Adjustment | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid | Q3 Baseline Adjustment | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | Q4 Baseline Adjustment | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Q1 Projection | Total Projection
Department of Financial Services
Florida PALM FY 2023 - 2024 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
D636 | Completion of Solution Design (Requirements) Segment I | Implementation | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 3415500
D637 | Completion of Solution Design (Requirements) Segment II | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D638 | Updated Data Conversion and Migration Strategy | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
D639 | Development of Standardized Business Process Models – Payroll | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448400 | 1448400 | 0 | 0 | 0 | 1448400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448400
D640 | Development of the Master Data Configuration Workbooks | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310500 | 2310500 | 0 | 0 | 0 | 0 | 2310500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2310500
D641 | Completion of Solution Design (Requirements) Segment III | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3415500
D642 | Updated Technical Architecture Design | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3811500 | 3811500 | 0 | 0 | 0 | 0 | 3811500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3811500
D643 | Updated System Testing Plan | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212900 | 3212900 | 0 | 0 | 0 | 0 | 3212900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3212900
D644 | Completion of Solution Design (Requirements) Segment IV | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3415500 | 0 | 0 | 0 | 0 | 0 | 3415500
D645 | Updated Deployment Strategy | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
D646 | Completion of Build Segment I | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000
D647 | Establish DW/BI Environments | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 550000 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 0 | 0 | 103923 | 415692
Prod Supp | AM Services | Prod Supp | 537195 | 537195 | 0 | 554500 | 554500 | 537195 | 554500 | 554500 | 554500 | 0 | 554500 | 534801 | 1089301 | 554500 | 554500 | 0 | 554500 | 554500 | 554500 | -19699 | 554500 | 554500 | 1109000 | 554500 | 554500 | 0 | 554500 | 554500 | 1109000 | 0 | 554500 | 554500 | 554500 | 554500 | 442000 | 442000 | 554500 | 0 | 0 | 0 | 0 | 1646195 | 6616996
Prod Supp | IM Services | Prod Supp | 106124 | 106124 | 0 | 109900 | 109900 | 106124 | 109900 | 109900 | 109900 | 0 | 109900 | 109900 | 219800 | 109900 | 109900 | 0 | 109900 | 109900 | 109900 | 0 | 109900 | 109900 | 219800 | 109900 | 109900 | 0 | 109900 | 109900 | 219800 | 0 | 109900 | 109900 | 109900 | 109900 | 109900 | 109900 | 109900 | 0 | 0 | 0 | 0 | 325924 | 1315024
Prod Supp | Oracle OCI Costs | Prod Supp | 141057 | 141057 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 141057 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 141057 | 141057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147325 | 147325 | 147325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141057 | 570496
Prod Supp | Support Tools Maintenance | Prod Supp | 45030 | 45030 | 45030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45030 | 45030
Prod Supp | Support Tools Purchase | Prod Supp | 203556 | 169280 | 169280 | 0 | 0 | 0 | 0 | 0 | 0 | -34276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203556 | 169280
Prod Supp | Solution Software Support | Prod Supp | 35325 | 35325 | 35325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35325 | 35325
| Implementation Total: |  | 0 | 0 | 0 | 3415500 | 3415500 | 0 | 0 | 1500000 | 3415500 | 1500000 | 1448400 | 1448400 | 1500000 | 3415500 | 3415500 | 1448400 | 2310500 | 2310500 | 3415500 | 0 | 0 | 0 | 2310500 | 3415500 | 3415500 | 0 | 7024400 | 7024400 | 3415500 | 0 | 3250000 | 1000000 | 8024400 | 550000 | 2800000 | 550000 | 3415500 | 0 | 0 | 0 | 0 | 3415500 | 29745300
| Production Support Facilities: |  | 34641 | 0 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 0 | 0 | 103923 | 415692
| Production Support (No Facilities) Total: |  | 1068287 | 1034011 | 0 | 664400 | 664400 | 643319 | 664400 | 664400 | 664400 | -34276 | 805457 | 785758 | 1450158 | 664400 | 664400 | 0 | 664400 | 664400 | 664400 | -19699 | 805457 | 805457 | 1469857 | 664400 | 664400 | 0 | 664400 | 664400 | 1328800 | 0 | 811725 | 811725 | 811725 | 664400 | 551900 | 551900 | 664400 | 0 | 0 | 0 | 0 | 2397087 | 8752151
Monthly Totals |  |  | 1102928 | 1068652 | 425333 | 4114541 | 4114541 | 677960 | 699041 | 2199041 | 4114541 | 1465724 | 2288498 | 2268799 | 2984799 | 4114541 | 4114541 | 1483041 | 3009541 | 3009541 | 4114541 | -19699 | 840098 | 840098 | 3814998 | 4114541 | 4114541 | 34641 | 7723441 | 7723441 | 4778941 | 0 | 4096366 | 1846366 | 8870766 | 1249041 | 3386541 | 1136541 | 4114541 | 0 | 0 | 0 | 0 | 5916510 | 38913143
| Projected YTD |  | 1102928 |  |  | 5217469 |  |  | 5916510 |  |  | 7382234 | 9670732 |  |  | 13785273 |  |  | 16794814 |  |  | 16775115 | 17615213 |  |  | 21729754 |  |  | 29453195 |  |  | 29453195 | 33549561 |  |  | 34798602 |  |  | 38913143
| Incurred YTD |  |  | 1068652 |  |  | 5183193 |  |  | 7382234 |  |  |  | 9651033 |  |  | 13765574 |  |  | 16775115 |  |  |  | 17615213 |  |  | 21729754 |  |  | 29453195 |  |  |  | 31299561 |  |  | 34686102 |  |  | 34686102 |  | 34686102
| Paid YTD |  |  |  | 425333 |  |  | 1103293 |  |  | 5217834 |  |  |  | 8202633 |  |  | 9685674 |  |  | 13800215 |  |  |  | 17615213 |  |  | 17649854 |  |  | 22428795 |  |  |  | 31299561 |  |  | 32436102 |  |  | 32436102 |  | 32436102
0

## Oracle
Department of Financial Services
Florida PALM FY 2023 - 2024 Oracle Detail FYTD
| Annual |  |  | July 2023 |  |  |  | August 2023 |  |  |  | September 2023 |  |  |  | Q2 Baseline Adjustment | October 2023 |  |  |  | November 2023 |  |  |  | December 2023 |  |  |  | Q3 Baseline Adjustment | January 2024 |  |  |  | February 2024 |  |  |  | March 2024 |  |  |  | Q4 Baseline Adjustment | April 2024 |  |  |  | May 2024 |  |  |  | June 2024 | [5 empty] | Total
Program | Tech Support | Purchase | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  |  | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support | 1287647.41 | 0 | 1287647.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321911.8525 | 321911.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0475 | 321911.9025 | 321911.9 | 0 | 321911.9025 | 0 | 0 | 0 | 321911.9025 | 0 | 0 | 0 | 0 | -0.0025 | 321911.9025 | 321911.9 | 0 | 0 | 0 | 0 | 0 | 321911.9 | 321911.9025 | 0 | 0 | 0 | 0 | 0 | 965735.7025 | 965735.7 | 0
**Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 3401.27 |  | 3401.27 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 850.3175 | 850.32 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.0025 | 850.3175 | 850.32 |  | 850.3175 | 0 | 0 |  | 850.3175 | 0 | 0 |  | 0 | 0.0025 | 850.3175 | 850.32 |  | 0 | 0 | 0 |  | 850.32 | 850.3175 | 0 |  | 0 | 0 | 0 | 2550.9575 | 2550.96 | 0
Oracle Business Intelligence (Analytics) Server Administrator | 1450.58 |  | 1450.58 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 362.645 | 362.65 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.005 | 362.645 | 362.65 |  | 362.645 | 0 | 0 |  | 362.645 | 0 | 0 |  | 0 | 0.005 | 362.645 | 362.65 |  | 0 | 0 | 0 |  | 362.65 | 362.645 | 0 |  | 0 | 0 | 0 | 1087.945 | 1087.95 | 0
Oracle Business Intelligence Management Pack | 2876.25 |  | 2876.25 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 719.0625 | 719.06 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -0.0025 | 719.0625 | 719.06 |  | 719.0625 | 0 | 0 |  | 719.0625 | 0 | 0 |  | 0 | -0.0025 | 719.0625 | 719.06 |  | 0 | 0 | 0 |  | 719.06 | 719.0625 | 0 |  | 0 | 0 | 0 | 2157.1825 | 2157.18 | 0
Oracle Business Intelligence Suite Foundation Edition | 75048.11 |  | 75048.11 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 18762.0275 | 18762.03 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.0025 | 18762.0275 | 18762.03 |  | 18762.0275 | 0 | 0 |  | 18762.0275 | 0 | 0 |  | 0 | 0.0025 | 18762.0275 | 18762.03 |  | 0 | 0 | 0 |  | 18762.03 | 18762.0275 | 0 |  | 0 | 0 | 0 | 56286.0875 | 56286.09 | 0
Oracle Data Integrator Enterprise Edition | 37524.06 |  | 37524.06 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 9381.015 | 9381.02 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.005 | 9381.015 | 9381.02 |  | 9381.015 | 0 | 0 |  | 9381.015 | 0 | 0 |  | 0 | 0.005 | 9381.015 | 9381.02 |  | 0 | 0 | 0 |  | 9381.02 | 9381.015 | 0 |  | 0 | 0 | 0 | 28143.055 | 28143.06 | 0
Oracle Data Visualization | 25016.72 |  | 25016.72 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6254.18 | 6254.18 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6254.18 | 6254.18 |  | 6254.18 | 0 | 0 |  | 6254.18 | 0 | 0 |  | 0 | 0 | 6254.18 | 6254.18 |  | 0 | 0 | 0 |  | 6254.18 | 6254.18 | 0 |  | 0 | 0 | 0 | 18762.54 | 18762.54 | 0
*Oracle Financial Analytics Fusion Edition | 14509.91 |  | 14509.91 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3627.4775 | 3627.48 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.0025 | 3627.4775 | 3627.48 |  | 3627.4775 | 0 | 0 |  | 3627.4775 | 0 | 0 |  | 0 | 0.0025 | 3627.4775 | 3627.48 |  | 0 | 0 | 0 |  | 3627.48 | 3627.4775 | 0 |  | 0 | 0 | 0 | 10882.4375 | 10882.44 | 0
Oracle Managed File Transfer | 20954.23 |  | 20954.23 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5238.5575 | 5238.56 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.0025 | 5238.5575 | 5238.56 |  | 5238.5575 | 0 | 0 |  | 5238.5575 | 0 | 0 |  | 0 | 0.0025 | 5238.5575 | 5238.56 |  | 0 | 0 | 0 |  | 5238.56 | 5238.5575 | 0 |  | 0 | 0 | 0 | 15715.6775 | 15715.68 | 0
Oracle Management Pack for Oracle Data Integrator | 6904.25 |  | 6904.25 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 1726.0625 | 1726.06 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -0.0025 | 1726.0625 | 1726.06 |  | 1726.0625 | 0 | 0 |  | 1726.0625 | 0 | 0 |  | 0 | -0.0025 | 1726.0625 | 1726.06 |  | 0 | 0 | 0 |  | 1726.06 | 1726.0625 | 0 |  | 0 | 0 | 0 | 5178.1825 | 5178.18 | 0
Oracle SOA Management Pack Enterprise Edition | 20265.39 |  | 20265.39 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5066.3475 | 5066.35 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.0025 | 5066.3475 | 5066.35 |  | 5066.3475 | 0 | 0 |  | 5066.3475 | 0 | 0 |  | 0 | 0.0025 | 5066.3475 | 5066.35 |  | 0 | 0 | 0 |  | 5066.35 | 5066.3475 | 0 |  | 0 | 0 | 0 | 15199.0475 | 15199.05 | 0
Oracle SOA Suite for Oracle Middleware | 46609.98 |  | 46609.98 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11652.495 | 11652.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.005 | 11652.495 | 11652.5 |  | 11652.495 | 0 | 0 |  | 11652.495 | 0 | 0 |  | 0 | 0.005 | 11652.495 | 11652.5 |  | 0 | 0 | 0 |  | 11652.5 | 11652.495 | 0 |  | 0 | 0 | 0 | 34957.495 | 34957.5 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 18108.82 |  | 18108.82 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 4527.205 | 4527.21 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.005 | 4527.205 | 4527.21 |  | 4527.205 | 0 | 0 |  | 4527.205 | 0 | 0 |  | 0 | 0.005 | 4527.205 | 4527.21 |  | 0 | 0 | 0 |  | 4527.21 | 4527.205 | 0 |  | 0 | 0 | 0 | 13581.625 | 13581.63 | 0
Oracle WebLogic Suite | 67908.63 |  | 67908.63 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 16977.1575 | 16977.16 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.0025 | 16977.1575 | 16977.16 |  | 16977.1575 | 0 | 0 |  | 16977.1575 | 0 | 0 |  | 0 | 0.0025 | 16977.1575 | 16977.16 |  | 0 | 0 | 0 |  | 16977.16 | 16977.1575 | 0 |  | 0 | 0 | 0 | 50931.4775 | 50931.48 | 0
*PeopleSoft Enterprise Contracts | 51822.24 |  | 51822.24 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12955.56 | 12955.56 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -1.819e-12 | 12955.56 | 12955.56 |  | 12955.56 | 0 | 0 |  | 12955.56 | 0 | 0 |  | 0 | -1.819e-12 | 12955.56 | 12955.56 |  | 0 | 0 | 0 |  | 12955.56 | 12955.56 | 0 |  | 0 | 0 | 0 | 38866.68 | 38866.68 | 0
*PeopleSoft Enterprise eSettlements | 34008.55 |  | 34008.55 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 8502.1375 | 8502.14 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.0025 | 8502.1375 | 8502.14 |  | 8502.1375 | 0 | 0 |  | 8502.1375 | 0 | 0 |  | 0 | 0.0025 | 8502.1375 | 8502.14 |  | 0 | 0 | 0 |  | 8502.14 | 8502.1375 | 0 |  | 0 | 0 | 0 | 25506.4175 | 25506.42 | 0
*PeopleSoft Enterprise Expenses | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 17206.37 | 0 | 0 |  | 17206.37 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 17206.37 | 17206.37 | 0 |  | 0 | 0 | 0 | 51619.11 | 51619.11 | 0
*PeopleSoft Enterprise Financials | 370847.94 |  | 370848.09 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 92711.985 | 92711.98 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -0.005 | 92712.035 | 92711.98 |  | 92712.035 | 0 | 0 |  | 92712.035 | 0 | 0 |  | 0 | -0.055 | 92712.035 | 92711.98 |  | 0 | 0 | 0 |  | 92711.98 | 92712.035 | 0 |  | 0 | 0 | 0 | 278135.995 | 278135.94 | 0
*PeopleSoft Enterprise Grants | 48582.45 |  | 48582.45 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12145.6125 | 12145.62 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.0075 | 12145.6125 | 12145.62 |  | 12145.6125 | 0 | 0 |  | 12145.6125 | 0 | 0 |  | 0 | 0.0075 | 12145.6125 | 12145.62 |  | 0 | 0 | 0 |  | 12145.62 | 12145.6125 | 0 |  | 0 | 0 | 0 | 36436.8525 | 36436.86 | 0
*PeopleSoft Enterprise Human Resources | 46998.39 |  | 46998.39 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11749.5975 | 11749.6 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.0025 | 11749.5975 | 11749.6 |  | 11749.5975 | 0 | 0 |  | 11749.5975 | 0 | 0 |  | 0 | 0.0025 | 11749.5975 | 11749.6 |  | 0 | 0 | 0 |  | 11749.6 | 11749.5975 | 0 |  | 0 | 0 | 0 | 35248.7975 | 35248.8 | 0
*PeopleSoft Enterprise Payroll | 57159.76 |  | 57159.76 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14289.94 | 14289.94 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14289.94 | 14289.94 |  | 14289.94 | 0 | 0 |  | 14289.94 | 0 | 0 |  | 0 | 0 | 14289.94 | 14289.94 |  | 0 | 0 | 0 |  | 14289.94 | 14289.94 | 0 |  | 0 | 0 | 0 | 42869.82 | 42869.82 | 0
*PeopleSoft Enterprise Project Costing | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 17206.37 | 0 | 0 |  | 17206.37 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 17206.37 | 17206.37 | 0 |  | 0 | 0 | 0 | 51619.11 | 51619.11 | 0
*PeopleSoft Enterprise Purchasing | 76113.47 |  | 76113.47 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19028.3675 | 19028.38 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.0125 | 19028.3675 | 19028.38 |  | 19028.3675 | 0 | 0 |  | 19028.3675 | 0 | 0 |  | 0 | 0.0125 | 19028.3675 | 19028.38 |  | 0 | 0 | 0 |  | 19028.38 | 19028.3675 | 0 |  | 0 | 0 | 0 | 57085.1275 | 57085.14 | 0
*PeopleSoft Enterprise Supplier Contract Management | 68825.48 |  | 68825.48 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 17206.37 | 0 | 0 |  | 17206.37 | 0 | 0 |  | 0 | 0 | 17206.37 | 17206.37 |  | 0 | 0 | 0 |  | 17206.37 | 17206.37 | 0 |  | 0 | 0 | 0 | 51619.11 | 51619.11 | 0
*PeopleSoft Enterprise Treasury | 55059.97 |  | 55059.97 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13764.9925 | 13764.99 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -0.0025 | 13764.9925 | 13764.99 |  | 13764.9925 | 0 | 0 |  | 13764.9925 | 0 | 0 |  | 0 | -0.0025 | 13764.9925 | 13764.99 |  | 0 | 0 | 0 |  | 13764.99 | 13764.9925 | 0 |  | 0 | 0 | 0 | 41294.9725 | 41294.97 | 0
Time and Labor Year 1 Support | 176803.62 | 0 | 176803.63 | 0 | 0 | 0 | 0 | 37782.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37782.975 | 0 | 0 | 0 | 0 | 37782.975 | 37782.98 | 0 | 0 | 0 | 0 | 0 | 37782.98 | 0.005 | 0 | 0 | 0 | 0 | 37782.985 | 0 | 0 | 0 | 0 | 37782.98 | 0 | 37782.98 | -0.005 | 0 | 0 | 0 | 0 | 37782.975 | 37782.96 | 0 | 0 | 25671.72 | 0 | 0 | 0 | 0 | 0 | 75565.96 | 113348.92 | 0
*PeopleSoft Enterprise Time and Labor | 176803.62 |  | 176803.63 | 0 | 0 |  | 0 | 37782.975 | 0 |  | 0 | 0 | 0 |  | 0 | -37782.975 | 0 | 0 |  | 0 | 37782.975 | 37782.98 |  | 0 | 0 | 0 |  | 37782.98 | 0.005 | 0 | 0 |  | 0 | 37782.985 | 0 |  | 0 | 0 | 37782.98 |  | 37782.98 | -0.005 | 0 | 0 |  | 0 | 37782.975 | 37782.96 |  | 0 | 25671.72 | 0 |  | 0 | 0 | 0 | 75565.96 | 113348.92 | 0
New License Purchase and Tech Support | 123579.09 | 689082.56 | 1344625.4075 | 9749.8308 | 0 | 0 | 0 | 559434.4208 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | -578934.0825 | 0 | 0 | 0 | 0 | 559434.4208 | 306084.59 | 0 | 0 | 9749.8308 | 241860 | 0 | 0 | -21239.6617 | 32149.83 | 4.21 | 0 | 547944.59 | 40028.6025 | 15755.58 | 0 | 0 | 10981.83 | 19796.31 | 0 | 30136.96 | -47604.1625 | 32149.8308 | 2941.58 | 0 | 0 | 39982.49 | 51322.84 | 0 | 8266.6 | 41214.49 | 0 | 0 | 0 | 0 | 0 | 615650.5208 | 616485.11 | 0
*PeopleSoft Enterprise Financials | 29707.57 | 134665.46 | 291571.0125 | 0 | 0 |  | 0 | 134665.46 | 0 |  | 0 | 0 | 0 |  | 0 | -134665.46 | 0 | 0 |  | 0 | 134665.46 | 134665.46 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 134665.46 | 7426.8925 | 0 |  | 0 | 0 | 7406.6 |  | 7406.6 | -20.2925 | 0 | 0 |  | 0 | 7406.6 | 7406.6 |  | 0 | 7406.6 | 0 |  | 0 | 0 | 0 | 142072.06 | 149478.66 | 0
*PeopleSoft Enterprise Treasury | 4410.73 | 19994 | 43290.0225 | 0 | 0 |  | 0 | 19994 | 0 |  | 0 | 0 | 0 |  | 0 | -19994 | 0 | 0 |  | 0 | 19994 | 19994 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 19994 | 1102.6825 | 0 |  | 0 | 0 | 1099.67 |  | 1099.67 | -3.0125 | 0 | 0 |  | 0 | 1099.67 | 1099.67 |  | 0 | 1099.67 | 0 |  | 0 | 0 | 0 | 21093.67 | 22193.34 | 0
*PeopleSoft Enterprise Expenses | 5513.41 | 24992.5 | 54112.5325 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | -24992.5 | 0 | 0 |  | 0 | 24992.5 | 24992.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 24992.5 | 1378.3525 | 0 |  | 0 | 0 | 1374.59 |  | 1374.59 | -3.7625 | 0 | 0 |  | 0 | 1374.59 | 1374.59 |  | 0 | 1374.59 | 0 |  | 0 | 0 | 0 | 26367.09 | 27741.68 | 0
*PeopleSoft Enterprise eSettlements | 2724.27 | 12349.23 | 26737.9475 | 0 | 0 |  | 0 | 12349.23 | 0 |  | 0 | 0 | 0 |  | 0 | -12349.23 | 0 | 0 |  | 0 | 12349.23 | 12349.23 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 12349.23 | 681.0675 | 0 |  | 0 | 0 | 679.21 |  | 679.21 | -1.8575 | 0 | 0 |  | 0 | 679.21 | 679.21 |  | 0 | 679.21 | 0 |  | 0 | 0 | 0 | 13028.44 | 13707.65 | 0
*PeopleSoft Enterprise Contracts | 4151.28 | 18817.88 | 40743.54 | 0 | 0 |  | 0 | 18817.88 | 0 |  | 0 | 0 | 0 |  | 0 | -18817.88 | 0 | 0 |  | 0 | 18817.88 | 18817.88 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 18817.88 | 1037.82 | 0 |  | 0 | 0 | 1034.98 |  | 1034.98 | -2.84 | 0 | 0 |  | 0 | 1034.98 | 1034.98 |  | 0 | 1034.98 | 0 |  | 0 | 0 | 0 | 19852.86 | 20887.84 | 0
*PeopleSoft Enterprise Grants | 3891.82 | 17641.76 | 38197.075 | 0 | 0 |  | 0 | 17641.76 | 0 |  | 0 | 0 | 0 |  | 0 | -17641.76 | 0 | 0 |  | 0 | 17641.76 | 17641.76 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 17641.76 | 972.955 | 0 |  | 0 | 0 | 970.3 |  | 970.3 | -2.655 | 0 | 0 |  | 0 | 970.3 | 970.3 |  | 0 | 970.3 | 0 |  | 0 | 0 | 0 | 18612.06 | 19582.36 | 0
*PeopleSoft Enterprise Project Costing | 5513.41 | 24992.5 | 54112.5325 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | -24992.5 | 0 | 0 |  | 0 | 24992.5 | 24992.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 24992.5 | 1378.3525 | 0 |  | 0 | 0 | 1374.59 |  | 1374.59 | -3.7625 | 0 | 0 |  | 0 | 1374.59 | 1374.59 |  | 0 | 1374.59 | 0 |  | 0 | 0 | 0 | 26367.09 | 27741.68 | 0
*PeopleSoft Enterprise Supplier Contract Management | 5513.41 | 24992.5 | 54112.5325 | 0 | 0 |  | 0 | 24992.5 | 0 |  | 0 | 0 | 0 |  | 0 | -24992.5 | 0 | 0 |  | 0 | 24992.5 | 24992.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 24992.5 | 1378.3525 | 0 |  | 0 | 0 | 1374.59 |  | 1374.59 | -3.7625 | 0 | 0 |  | 0 | 1374.59 | 1374.59 |  | 0 | 1374.59 | 0 |  | 0 | 0 | 0 | 26367.09 | 27741.68 | 0
*PeopleSoft Enterprise Purchasing | 6097.19 | 27638.76 | 59842.0775 | 0 | 0 |  | 0 | 27638.76 | 0 |  | 0 | 0 | 0 |  | 0 | -27638.76 | 0 | 0 |  | 0 | 27638.76 | 27638.76 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 27638.76 | 1524.2975 | 0 |  | 0 | 0 | 1520.13 |  | 1520.13 | -4.1675 | 0 | 0 |  | 0 | 1520.13 | 1520.13 |  | 0 | 1520.13 | 0 |  | 0 | 0 | 0 | 29158.89 | 30679.02 | 0
HR Analytics | 44660 | 203000 | 439495 | 0 | 0 |  | 0 | 203000 | 0 |  | 0 | 0 | 0 |  | 0 | -203000 | 0 | 0 |  | 0 | 203000 | 0 |  | 0 | 0 | 201550 |  | 0 | -1450 | 0 | 0 |  | 201550 | 11165 | 11085.25 |  | 0 | 0 | 0 |  | 11085.25 | -79.75 | 0 | 0 |  | 0 | 11165 | 11085.25 |  | 0 | 11165 | 0 |  | 0 | 0 | 0 | 212635.25 | 223720.5 | 0
Project Analytics | 8932 | 40600 | 87899 | 0 | 0 |  | 0 | 40600 | 0 |  | 0 | 0 | 0 |  | 0 | -40600 | 0 | 0 |  | 0 | 40600 | 0 |  | 0 | 0 | 40310 |  | 0 | -290 | 0 | 0 |  | 40310 | 2233 | 2217.05 |  | 0 | 0 | 0 |  | 2217.05 | -15.95 | 0 | 0 |  | 0 | 2233 | 2217.05 |  | 0 | 2233 | 0 |  | 0 | 0 | 0 | 42527.05 | 44744.1 | 0
COBOL | 2464 | 22400 | 47264 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 22400 | 0 |  | 0 | 0 | 0 |  | 0 | 1232 | 0 |  | 0 | -23632 | 22400 | 0 |  | 0 | 0 | 21280 |  | 0 | 1232 | 0 |  | 0 | 0 | 0 | 22400
Oracle Autonomous Cloud (OAC) Dev | 0 | 53218.69 | 48783.795 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | -13304.6725 | 0 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | 4434.8908 | 0 |  | 0 | -8869.7817 | 4434.89 | 4.21 |  | 0 | 4434.89 | 2453.28 |  | 0 | 4434.89 | 2961.65 |  | 0 | -7885.53 | 4434.8908 | 2941.58 |  | 0 | 4434.89 | -94.12 |  | 8266.6 | 4434.89 | 0 |  | 0 | 0 | 0 | 9854.0308 | 8266.6 | 0
Oracle Autonomous Cloud (OAC) Test | 0 | 63779.28 | 58464.34 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | -15944.82 | 0 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | -10629.88 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | -15944.82 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 5314.94 | 0 |  | 0 | 0 | 0 | 5314.94 | 0 | 0
Total | 1588030.12 | 689082.56 | 2809076.5975 | 9749.8308 | 0 | 0 | 0 | 597217.3958 | 0 | 0 | 0 | 9749.8308 | 0 | 0 | 0 | -616717.0575 | 321911.8525 | 321911.9 | 0 | 0 | 597217.3958 | 343867.57 | 0 | 0 | 9749.8308 | 241860 | 0 | 37782.98 | -21239.6092 | 354061.7325 | 321916.11 | 0 | 869856.4925 | 77811.5875 | 15755.58 | 0 | 321911.9025 | 10981.83 | 57579.29 | 0 | 67919.94 | -47604.17 | 354061.7333 | 324853.48 | 0 | 0 | 77765.465 | 89105.8 | 0 | 330178.5 | 388798.1125 | 0 | 0 | 0 | 0 | 0 | 1656952.1833 | 1695569.73 | 0
Projected FYTD |  |  |  | 9749.8308 |  |  |  | 606967.2267 |  |  |  | 616717.0575 |  |  |  | 0 | 321911.8525 |  |  |  | 919129.2483 |  |  |  | 928879.0792 |  |  |  | 907639.47 | 1261701.2025 |  |  |  | 1339512.79 |  |  |  | 1350494.62 |  |  |  | 1302890.45 | 1656952.1833 |  |  |  | 1734717.6483 |  |  |  | 2123515.7608
Incurred FYTD |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 321911.9 |  |  |  | 665779.47 |  |  |  | 907639.47 |  |  |  |  | 1229555.58 |  |  |  | 1245311.16 |  |  |  | 1302890.45 |  |  |  |  | 1627743.93 |  |  |  | 1716849.73 |  |  |  | 1716849.73
Paid FYTD | [6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 37782.98 |  |  |  |  | 907639.4725 |  |  |  | 1229551.375 |  |  |  | 1297471.315 |  |  |  |  | 1297471.315 |  |  |  | 1627649.815 |  |  |  | 1627649.815
[16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0

## Footnotes
Department of Financial Services
FY 2023 - 2024 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Incurred amounts were less than anticipated due to financial consequences being applied for D646.
6 | Incurred amounts were greater than anticipated due to additional technology purchased for increased staff levels