## Monthly Summary
Department of Financial Services
Florida PALM FY 2024 - 2025 Spend Plan Summary FYTD
As of January 31, 2025
Annual
| TRUE | TRUE | TRUE |  | TRUE | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  |  | Q2 Basline Adjustment | October 2024 |  |  |  | November 2024 |  |  |  | December 2024 |  |  |  | Q3 Baseline Adjustment | January 2025 |  |  |  | February 2025 |  |  | March 2025 |  |  | April 2025 |  |  | May 2025 |  |  | June 2025 |  |  | CF 2024-25 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 46381361 | 30916123 | 15465238 | 45530078.3522 | 16434025.877 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| Appropriated | Released | Unreleased | Projected | Release Remaining | [12 empty] | Q1 Baseline Adjustment | [12 empty] | Q1 Baseline Adjustment
FLAIR System Replacement (100781) | 46381361 | 30916123 | 15465238 | 45530078.3522 | 16434025.877 | 3724003.7017 | 3754458.96 |  | 3526393.96 | 1038867.7017 | 980185.15 |  | 912032.65 | 1104165.7042 | 956326.57 |  | 931197.19 | -176066.425 | 5078311.7017 | 1166508.099 |  | 1146445.87 | 2289008.2902 | 2151345.867 |  | 2196318.16 | 3073416.3842 | 2957055.409 |  | 973289.149 | -4165827.003 | 10468319.2808 | 2516217.068 |  | 4492107.49 | 4707562.9829 | 0 | 0 | 3239253.8892 | 0 | 0 | 3349874.6092 | 0 | 0 | 3600267.6129 | 0 | 0 | 8198919.9217 | 0 | 0 | 0 | 0 | 22434199.3363 | 14482097.123 | 14177784.469 | 31047981.2287 | 68.19%
SSI Implementation Services (FP004) |  |  |  | 30118027 |  | 2250000 | 2250000 |  | 2250000 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3450000 | 0 | 2 | 0 | 1200000 | 1200000 |  | 1200000 | 2000000 | 2000000 |  | 0 | -3450000 | 8450000 | 1350000 | 2 | 3350000 | 3500000 | 0 | 0 | 2039953 | 0 | 0 | 1630000 | 0 | 0 | 2378840 | 0 | 0 | 6669234 | 0 | 0 | 0 | 0 | 13900000 | 6800000 | 6800000 | 23318027 | 77.42%
Facilities and Maintenance (FP004) |  |  |  | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 242487 | 242487 | 242487 | 173205 | 41.67%
Production Support (FP004) |  |  |  | 9354902 |  | 1134539 | 1225344 | 3 | 1225344 | 686100 | 686100 |  | 686100 | 686100 | 686100 |  | 686100 | 90805 | 873512 | 873512 |  | 873512 | 686100 | 686100 |  | 686100 | 681970 | 686100 |  | 686100 | 4130 | 869382 | 869382 |  | 869382 | 690970 | 0 | 0 | 690970 | 0 | 0 | 878384 | 0 | 0 | 690970 | 0 | 0 | 690970 | 0 | 0 | 0 | 0 | 5712638 | 5712638 | 5712638 | 3642264 | 38.93%
Additional Facilities |  |  |  | 174669.05 |  | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 10756.18 | 0 | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 0 | 10756.18 | 10756.18 |  | 21512.36 | 0 | 10756.18 | 10756.18 |  | 10756.18 | 19745.18 | 0 | 0 | 19745.18 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 0 | 0 | 75293.26 | 75293.26 | 75293.26 | 99375.79 | 56.89%
Production Support Administration |  |  |  | 53599.3 |  | 2403.26 | 2383.44 |  | 2383.44 | 2403.26 | 2383.26 |  | 2383.26 | 2403.26 | 2383.26 |  | 0 | -59.82 | 2383.26 | 2383.26 |  | 2383.26 | 2383.26 | 2383.26 |  | 0 | 2383.26 | 2383.26 |  | 7149.78 | 0 | 27383.26 | 23342.13 |  | 6991.47 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 0 | 0 | 41683 | 37641.87 | 21291.21 | 15957.43 | 29.77%
Oracle Software and Maintenance (FP005) |  |  |  | 1638623.0017 |  | 27839.9317 | 0 | 2 | 0 | 27839.9317 | 0 | 2 | 0 | 27839.9317 | 11802.05 | 2 | 0 | -71717.745 | 395992.6887 | 0 | 2 | 11802.05 | 52855.8402 | 23925.47 | 2 | 7090.84 | 27839.9317 | 19602.82 | 2 | 16834.63 | -433160.1705 | 697386.3233 | 0 | 2 | 19602.82 | 59750.0254 | 0 | 0 | 27839.9317 | 0 | 0 | 356190.0217 | 0 | 0 | 59750.0254 | 0 | 0 | 382376.3342 | 0 | 0 | 0 | 0 | 752716.6633 | 55330.34 | 55330.34 | 1583292.6617 | 96.62%
Project Administration |  |  |  | 210000.0005 |  | 22096.33 | 3269.34 | 2 | 3269.34 | 14735.33 | 15871.21 | 3 | 15871.21 | 87505.3325 | 8724.08 | 2 | 202.51 | -96472.36 | 44898.573 | 15975.159 | 2 | 27771.38 | 12488.01 | 12253.957 |  | 11917.82 | 7778.0125 | 783.149 | 2 | -2556.621 | -36152.3325 | 89210.5175 | 1043.758 | 2 | 1445.02 | 11313.5175 | 0 | 0 | 20593.5175 | 0 | 0 | 10818.5175 | 0 | 0 | 10593.5175 | 0 | 0 | 10593.5175 | 0 | 0 | 0 | 0 | 146087.413 | 57920.653 | 57920.659 | 152079.347 | 72.42%
Support Services |  |  |  | 2566779.5 |  | 159536 | 149537 | 1 | 0 | 180200 | 150249.5 | 1 | 100297 | 180200 | 136177.5 | 1 | 149049.5 | -83972 | 180200 | 144268.5 | 1 | 90197.5 | 222536 | 123830 | 1 | 195448.5 | 229592 | 132285 | 1 | 128300 | -231944.5 | 196160 | 146090 | 1 | 128785 | 295360 | 0 | 0 | 309728 | 0 | 0 | 324096 | 0 | 0 | 309728 | 0 | 0 | 295360 | 0 | 0 | 0 | 0 | 1032507.5 | 982437.5 | 792077.5 | 1584342 | 61.72%
QA Support Services |  |  |  | 997786.5 |  | 82192 | 78528 |  | 0 | 82192 | 80184 |  | 61984 | 74720 | 65742.5 | 1 | 50448 | -14649.5 | 85928 | 84972 |  | 95382.5 | 67248 | 57456 |  | 61120 | 78456 | 70504 |  | 81308 | -18700 | 93400 | 80962 |  | 70504 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 0 | 0 | 530786.5 | 518348.5 | 420746.5 | 479438 | 48.05%
IT Service Management Implementation and Software (100777) | 1304572 | 1304572 | 0 | 879006.82 | 1097388.06 | 38576.48 | 0 |  | 0 | 963.52 | 37612.96 |  | 37612.96 | 20124.28 | 0 |  | 0 | -22051.32 | 149298.91 | 149085.39 |  | 750 | 3333.09 | 750 |  | 19910.76 | 16139.54 | 17920.59 |  | 0 | -1015.56 | 963.52 | 1815 |  | 4776.95 | 668820.28 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 0 | 0 | 206332.46 | 207183.94 | 63050.67 | 671822.88 | 76.43%
ITSM Implementation and Administrative Support |  |  |  | 203493.94 |  | 37612.96 | 0 | 2 | 0 | 0 | 37612.96 | 3 | 37612.96 | 19160.76 | 0 | 2 | 0 | -19160.76 | 148335.39 | 148335.39 |  | 0 | 2369.57 | 0 | 2 | 19160.76 | 15176.02 | 17545.59 | 3 | 0 | 0 | 0 | 0 |  | 2961.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203493.94 | 203493.94 | 59735.67 | 0 | 0%
ITSM Software |  |  |  | 675512.88 |  | 963.52 | 0 | 2 | 0 | 963.52 | 0 | 2 | 0 | 963.52 | 0 | 2 | 0 | -2890.56 | 963.52 | 750 | 2 | 750 | 963.52 | 750 | 2 | 750 | 963.52 | 375 | 2 | 0 | -1015.56 | 963.52 | 1815 | 3 | 1815 | 668820.28 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 0 | 0 | 2838.52 | 3690 | 3315 | 671822.88 | 99.45%
Contingency (100819) | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Salaries & Benefits (010000) | 10220897 | 10220897 | 0 | 9556285.05 | 4821490.86 | 823871.84 | 697273.25 |  | 697273.25 | 823871.83 | 777393.67 |  | 777393.67 | 823871.83 | 768441.69 |  | 768441.69 | -228506.89 | 823871.84 | 791115 |  | 791115 | 823871.83 | 764424.06 |  | 764424.06 | 823871.83 | 814406.38 |  | 814406.38 | -101670.06 | 823871.84 | 786352.09 |  | 786352.09 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 823871.84 | 0 | 0 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 0 | 0 | 5436925.89 | 5399406.14 | 5399406.14 | 4156878.91 | 43.5%
Risk Management Insurance (103241) | 13957 | 13957 | 0 | 13957 | 0 | 7978 | 0 |  | 0 | 0 | 13957 | 5 | 13957 | 0 | 0 |  | 0 | 5979 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13957 | 13957 | 13957 | 0 | 0%
DMS HR Transfer (107040) | 24000 | 24000 | 0 | 24000 | 18000 | 6152.25 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -6152.25 | 12000 | 0 |  | 0 | 0 | 6000 |  | 6000 | 0 | 0 |  | 0 | -6000 | 12000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 6000 | 6000 | 18000 | 75%
Totals | 60944787 | 42479549 | 18465238 | 56003327.2222 | 22370904.797 | 4600582.2717 | 4451732.21 |  | 4223667.21 | 1863703.0517 | 1809148.78 |  | 1740996.28 | 1948161.8142 | 1724768.26 |  | 1699638.88 | -426797.885 | 6063482.4517 | 2106708.489 |  | 1938310.87 | 3116213.2102 | 2922519.927 |  | 2986652.98 | 3913427.7542 | 3789382.379 |  | 1787695.529 | -4274512.623 | 11305154.6408 | 3304384.158 |  | 5283236.53 | 6200255.0929 | 0 | 0 | 4064089.2392 | 0 | 0 | 4180709.9692 | 0 | 0 | 4425102.9629 | 0 | 0 | 9023755.2717 | 0 | 0 | 0 | 0 | 28109414.6863 | 20108644.203 | 19660198.279 | 35894683.0187 | 64.09%
Running Totals | [5 empty] | 4600582.2717 | 4451732.21 |  | 4223667.21 | 6464285.3233 | 6260880.99 |  | 5964663.49 | 8412447.1375 | 7985649.25 |  | 7664302.37 | 7985649.2525 | 14049131.7042 | 10092357.739 |  | 9602613.24 | 17165344.9143 | 13014877.666 |  | 12589266.22 | 21078772.6685 | 16804260.045 |  | 14376961.749 | 16804260.0455 | 32383927.3093 | 20108644.203 |  | 19660198.279 | 38584182.4022 | 20108644.203 | 19660198.279 | 42648271.6414 | 20108644.203 | 19660198.279 | 46828981.6106 | 20108644.203 | 19660198.279 | 51254084.5735 | 20108644.203 | 19660198.279 | 60277839.8452 | 20108644.203 | 19660198.279 |  | 19660198.279
Monthly Total Incurred/Total Projected | [5 empty] | 96.76% |  |  |  | 97.07% |  |  |  | 88.53% |  |  |  |  | 34.74% |  |  |  | 93.78% |  |  |  | 96.83% |  |  |  |  | 29.23% |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Monthly Total Incurred/Total Projected (Variance) | [5 empty] | -3.235% |  |  |  | -2.927% |  |  |  | -11.47% |  |  |  |  | -65.26% |  |  |  | -6.216% |  |  |  | -3.17% |  |  |  |  | -70.77% |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [5 empty] | 96.76% |  |  |  | 96.85% |  |  |  | 94.93% |  |  |  |  | 71.84% |  |  |  | 75.82% |  |  |  | 79.72% |  |  |  |  | 62.09% |  |  |  | 52.12% |  |  | 47.15% |  |  | 42.94% |  |  | 39.23% |  |  | 33.36%
FYTD Total Incurred/Total Projected (Variance) | [5 empty] | -3.235% |  |  |  | -3.147% |  |  |  | -5.073% |  |  |  |  | -28.16% |  |  |  | -24.18% |  |  |  | -20.28% |  |  |  |  | -37.91% |  |  |  | -47.88% |  |  | -52.85% |  |  | -57.06% |  |  | -60.77% |  |  | -66.64%

## Footnotes
Department of Financial Services
FY 2024 - 2025 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Incurred amounts were greater than anticipated due to an additional appropriation to the category.
6

## SSI Detail
|  |  |  | July 2024 |  |  | August 2024 |  |  | September 2024 |  |  | Q2 Baseline Adjustment | October 2024 |  |  | November 2024 |  |  | December 2024 |  |  | Q3 Baseline Adjustment | January 2025 |  |  | February 2025 |  |  | March 2025 |  |  | April 2025 |  |  | May 2025 |  |  | June 2025 |  |  | CF 2024-25
|  | Description | Total Deliverable Cost FY 24-25 | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid |  | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid |  | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Projection | Projection Remaining | Projected FYTD | Total Accepted / Approved | Projected FYTD Pending | Total Paid | Payment Pending
Department of Financial Services
Florida PALM FY 2024 - 2025 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
D648 | Completion of Build Segment II | Implementation | 2250000 | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 2250000 | 2250000 | 0 | 2250000 | 0
D649 | Completion of Build Segment III | Implementation | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2250000 | 2250000 | 0 | 2250000 | 0 | 0
D650 | Completion of Solution Design (Requirements) DW/BI | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000 | 1200000 | 0 | 1200000 | 0
D651 | Completion of Mock Conversion I | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | -1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 1200000 | 0 | 1200000 | 0 | 0
D652 | Completion of System Test Segment I | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000 | 2000000 | 0 | 2000000 | 0
D653 | Completion of Build Segment I DW/BI | Implementation | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 1350000 | 1350000 | 0 | 1350000 | 0
D654 | Completion of Build Segment IV | Implementation | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650000 | 2650000 | 2650000 | 0 | 2650000 | 0 | 0
D655 | Completion of Mock Conversion II (System Test Environment) | Implementation | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 1000000 | 0 | 1000000 | 0 | 0
D656 | Completion of System Test Segment II | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0
D657 | Completion of Mock Conversion III (UAT) | Implementation | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0
D658 | Develop the Deployment and Contingency Plan | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0
D659 | Completion of Build Segment II DW/BI | Implementation | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0
D660 | Payroll Parallel Testing Plan | Implementation | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 280000 | 0 | 0 | 0 | 0 | 0
D662 | Completion of Dress Rehearsal (Mock Conversion IV) | Implementation | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0
D663 | Completion of Interface Testing Segment I | Implementation | 2081700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081700 | 0 | 0 | 0 | 0 | 2081700 | 2081700 | 0 | 0 | 0 | 0 | 0
D664 | Development of the Hypercare Support Plan | Implementation | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 455000 | 455000 | 0 | 0 | 0 | 0 | 0
D665 | Updated Post-Implementation Support Plan | Implementation | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 455000 | 455000 | 0 | 0 | 0 | 0 | 0
D666 | Support of UAT Segment I | Implementation | 2236500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2236500 | 0 | 0 | 0 | 0 | 2236500 | 2236500 | 0 | 0 | 0 | 0 | 0
D668 | Completion of Build Segment III DW/BI | Implementation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0
D696 | Completion of System Test Segment III | Implementation | 1378840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1378840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1378840 | 1378840 | 0 | 0 | 0 | 0 | 0
D698 | Completion of Inter/IntraUnit and Receipt Accrual Cost Collection Build | Implementation | 54867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 54867 | 0 | 0 | 0 | 0 | 54867 | 54867 | 0 | 0 | 0 | 0 | 0
D699 | Completion of AM Physical Inventory File Path Build | Implementation | 36167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 36167 | 0 | 0 | 0 | 0 | 36167 | 36167 | 0 | 0 | 0 | 0 | 0
D700 | Completion of Cash Reporting Solution Enhancement Build | Implementation | 39953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39953 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39953 | 39953 | 0 | 0 | 0 | 0 | 0
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 415692 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692 | 173205 | 242487 | 242487 | 0 | 242487 | 0
Prod Supp | AM Services | Prod Supp | 6849800 | 554500 | 554500 | 554500 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 0 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 0 | 572300 | 572300 | 572300 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 0 | 0 | 6849800 | 2861500 | 3988300 | 3988300 | 0 | 3988300 | 0
Prod Supp | IM Services (includes month credit -$4,130 from A10) | Prod Supp | 1406700 | 109900 | 109900 | 109900 | 113800 | 113800 | 113800 | 113800 | 113800 | 113800 | 0 | 113800 | 113800 | 113800 | 113800 | 113800 | 113800 | 109670 | 113800 | 113800 | 4130 | 109670 | 109670 | 109670 | 118670 | 0 | 0 | 118670 | 0 | 0 | 118670 | 0 | 0 | 118670 | 0 | 0 | 118670 | 0 | 0 | 0 | 0 | 1381920 | 593350 | 788570 | 788570 | 0 | 788570 | 0
Prod Supp | Oracle OCI Costs | Prod Supp | 749650 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 187414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749650 | 187414 | 562236 | 562236 | 0 | 562236 | 0
Prod Supp | Support Tools Maintenance | Prod Supp | 46381 | 46381 | 46381 | 46381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46381 | 0 | 46381 | 46381 | 0 | 46381 | 0
Prod Supp | Support Tools Purchase | Prod Supp | 311780 | 203556 | 311780 | 311780 | 0 | 0 | 0 | 0 | 0 | 0 | 108224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311780 | 0 | 311780 | 311780 | 0 | 311780 | 0
Prod Supp | Solution Software Support | Prod Supp | 32790 | 32790 | 15371 | 15371 | 0 | 0 | 0 | 0 | 0 | 0 | -17419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15371 | 0 | 15371 | 15371 | 0 | 15371 | 0
| Implementation Total: |  |  | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450000 | 0 | 0 | 1200000 | 1200000 | 1200000 | 2000000 | 2000000 | 0 |  | 8450000 | 1350000 | 3350000 | 3500000 | 0 | 0 | 2039953 | 0 | 0 | 1630000 | 0 | 0 | 2378840 | 0 | 0 | 6669234 | 0 | 0 | 0 | 0 | 30118027 | 23318027 | 0 | 6800000 | -6800000 | 6800000 | 0
| Production Support Facilities Total: |  |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692 | 173205 | 0 | 242487 | -242487 | 242487 | 0
| Production Support (No Facilities) Total: |  |  | 1134539 | 1225344 | 1225344 | 686100 | 686100 | 686100 | 686100 | 686100 | 686100 |  | 873512 | 873512 | 873512 | 686100 | 686100 | 686100 | 681970 | 686100 | 686100 |  | 869382 | 869382 | 869382 | 690970 | 0 | 0 | 690970 | 0 | 0 | 878384 | 0 | 0 | 690970 | 0 | 0 | 690970 | 0 | 0 | 0 | 0 | 9354902 | 3642264 | 0 | 5712638 | -5712638 | 5712638 | 0
Monthly Totals |  |  | 38580820 | 3419180 | 3509985 | 3509985 | 720741 | 720741 | 720741 | 720741 | 720741 | 720741 | 90805 | 4358153 | 908153 | 908153 | 1920741 | 1920741 | 1920741 | 2716611 | 2720741 | 720741 | -3445870 | 9354023 | 2254023 | 4254023 | 4225611 | 0 | 0 | 2765564 | 0 | 0 | 2543025 | 0 | 0 | 3104451 | 0 | 0 | 7394845 | 0 | 0 | 0 | 0 | 39888621 | 27133496 | 19855125 | 12755125 | 7100000 | 12755125 | 0
| Projected YTD |  |  | 3419180 |  |  | 4139921 |  |  | 4860662 |  |  | 4951467 | 9309620 |  |  | 11230361 |  |  | 13946972 |  |  | 10501102 | 23300995 |  |  | 27526606 |  |  | 30292170 |  |  | 32835195 |  |  | 35939646 |  |  | 43334491
| Incurred YTD |  |  |  | 3509985 |  |  | 4230726 |  |  | 4951467 |  |  |  | 5859620 |  |  | 7780361 |  |  | 10501102 |  |  |  | 12755125 |  |  | 12755125 |  |  | 12755125 |  |  | 12755125 |  |  | 12755125 |  |  | 12755125 |  | 12755125
| Paid YTD |  |  |  |  | 3509985 |  |  | 4230726 |  |  | 4951467 |  |  |  | 5859620 |  |  | 7780361 |  |  | 8501102 |  |  |  | 12755125 |  |  | 12755125 |  |  | 12755125 |  |  | 12755125 |  |  | 12755125 |  |  | 12755125 |  | 12755125

## Oracle Summary
Department of Financial Services
Florida PALM FY 2024 - 2025 Oracle Summary FYTD
| Quantity/Months | Quote |  |  | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  |  | Q2 Baseline Adjustment | October 2024 |  |  |  | November 2024 |  |  |  | December 2024 |  |  |  | Q3 Baseline Adjustment | January 2025 |  |  |  | February 2025 |  |  |  | March 2025 |  |  |  | April 2025 |  |  |  | May 2025 |  |  |  | June 2025 |  |  |  | FY 2024-25 CF |  | Total
Program |  | Tech Support | Total Purchase/ Subscription | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | CF Incurred | CF Paid | Total Projected | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support |  | 1518401.278 |  | 1518401.278 | 0 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 |  | 368152.757 | 0 | #REF! | 0 | 11447.5625 | 18005.03 | #REF! | 1170.4 | 0 | 0 | #REF! | 16834.63 | -361595.2895 | 697386.3233 | 0 | #REF! | 0 | 59750.0254 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 356190.0217 | 0 | #REF! | 0 | 59750.0254 | 0 | #REF! | 0 | 382376.3342 | 0 | #REF! | 0 | 0 | 0 | 1638623.0017 | 752716.6633 | 55330.34 | 55330.34
Assignment |  | 1518401.278 | 0 | 1518401.278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 368152.757 | 0 | 0 | 0 | 11447.5625 | 18005.03 | 0 | 1170.4 | 0 | 0 | 0 | 16834.63 |  | 669546.3917 | 0 | 0 | 0 | 18341.7437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328350.09 | 0 | 0 | 0 | 18341.7437 | 0 | 0 | 0 | 340968.0525 | 0 | 0 | 0 | 0 | 0 | 1393553.0517 | 687551.4217 | 18005.03 | 18005.03
Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 2 | 8525.418 | 0 | 8525.418 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 2131.3545 | 0 |  | 0 | 0 | 1170.4 |  | 1170.4 | 0 | 0 |  | 0 | -960.9545 | 1734.645 | 0 |  | 0 | 1170.4 | 0 |  | 0 | 0 | 0 |  | 0 | 867.3225 | 0 |  | 0 | 1170.4 | 0 |  | 0 | 2037.7225 | 0 |  | 0 | 0 | 0 | 8150.89 | 2905.045 | 1170.4 | 1170.4
Oracle Business Intelligence (Analytics) Server Administrator | 4 | 1479.59 | 0 | 1479.59 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -369.8975 | 739.795 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 | 1479.59 | 739.795 | 0 | 0
Oracle Business Intelligence Management Pack | 4 | 2933.77 | 0 | 2933.77 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -733.4425 | 1466.885 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 | 2933.77 | 1466.885 | 0 | 0
Oracle Business Intelligence Suite Foundation Edition | 4 | 76549.07 | 0 | 76549.07 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -19137.2675 | 38274.535 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 | 76549.07 | 38274.535 | 0 | 0
Oracle Data Integrator Enterprise Edition | 20 | 38274.54 | 0 | 38274.54 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -9568.635 | 19137.27 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 | 38274.54 | 19137.27 | 0 | 0
Oracle Data Visualization | 4 | 25517.06 | 0 | 25517.06 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -6379.265 | 12758.53 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 | 25517.06 | 12758.53 | 0 | 0
Oracle Financial Analytics Fusion Edition (DW/BI) | 100 | 14800.11 | 0 | 14800.11 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -3700.0275 | 7400.055 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 | 14800.11 | 7400.055 | 0 | 0
Oracle Managed File Transfer | 12 | 21373.31 | 0 | 21373.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5343.3275 | 10686.655 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 | 21373.31 | 10686.655 | 0 | 0
Oracle Management Pack for Oracle Data Integrator | 16 | 7042.33 | 0 | 7042.33 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -1760.5825 | 3521.165 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 | 7042.33 | 3521.165 | 0 | 0
Oracle SOA Management Pack Enterprise Edition | 14 | 20670.71 | 0 | 20670.71 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5167.6775 | 10335.355 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 | 20670.71 | 10335.355 | 0 | 0
Oracle SOA Suite for Oracle Middleware | 14 | 47542.18 | 0 | 47542.18 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -11885.545 | 23771.09 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 | 47542.18 | 23771.09 | 0 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 26 | 18471 | 0 | 18471 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -4617.75 | 9235.5 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 | 18471 | 9235.5 | 0 | 0
Oracle WebLogic Suite | 26 | 69266.8 | 0 | 69266.8 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -17316.7 | 34633.4 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 | 69266.8 | 34633.4 | 0 | 0
PeopleSoft Enterprise Contracts | 92083 | 55673.81 | 0 | 55673.81 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13214.6675 | 0 |  | 0 | 703.785 | 1034.99 |  | 0 | 0 | 0 |  | 1034.99 | -12883.4625 | 26429.335 | 0 |  | 0 | 1055.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 13214.6675 | 0 |  | 0 | 1055.6775 | 0 |  | 0 | 13918.4525 | 0 |  | 0 | 0 | 0 | 56708.8 | 27464.325 | 1034.99 | 1034.99
PeopleSoft Enterprise eSettlements | 92083 | 36536.19 | 0 | 36536.19 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 8672.185 | 0 |  | 0 | 461.8625 | 679.2 |  | 0 | 0 | 0 |  | 679.2 | -8454.8475 | 17344.37 | 0 |  | 0 | 692.7938 | 0 |  | 0 | 0 | 0 |  | 0 | 8672.185 | 0 |  | 0 | 692.7938 | 0 |  | 0 | 9134.0475 | 0 |  | 0 | 0 | 0 | 37215.39 | 18023.57 | 679.2 | 679.2
PeopleSoft Enterprise Expenses | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 1374.58 |  | 0 | 0 | 0 |  | 1374.58 | -17110.6375 | 35100.995 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 75315.45 | 36475.575 | 1374.58 | 1374.58
PeopleSoft Enterprise Financials | 92083 | 398410.84 | 0 | 398410.84 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 94566.2225 | 0 |  | 0 | 5036.4875 | 7406.6 |  | 0 | 0 | 0 |  | 7406.6 | -92196.11 | 189132.445 | 0 |  | 0 | 7554.7312 | 0 |  | 0 | 0 | 0 |  | 0 | 94566.2225 | 0 |  | 0 | 7554.7312 | 0 |  | 0 | 99602.71 | 0 |  | 0 | 0 | 0 | 405817.44 | 196539.045 | 7406.6 | 7406.6
PeopleSoft Enterprise Grants | 92083 | 52193.31 | 0 | 52193.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12388.525 | 0 |  | 0 | 659.8025 | 970.29 |  | 0 | 0 | 0 |  | 970.29 | -12078.0375 | 24777.05 | 0 |  | 0 | 989.7038 | 0 |  | 0 | 0 | 0 |  | 0 | 12388.525 | 0 |  | 0 | 989.7038 | 0 |  | 0 | 13048.3275 | 0 |  | 0 | 0 | 0 | 53163.6 | 25747.34 | 970.29 | 970.29
PeopleSoft Enterprise Human Resources | 114800 | 47938.36 | 0 | 47938.36 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -11984.59 | 23969.18 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 | 47938.36 | 23969.18 | 0 | 0
PeopleSoft Enterprise Payroll | 114800 | 58302.96 | 0 | 58302.96 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -14575.74 | 29151.48 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 | 58302.96 | 29151.48 | 0 | 0
PeopleSoft Enterprise Project Costing | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 1374.58 |  | 0 | 0 | 0 |  | 1374.58 | -17110.6375 | 35100.995 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 75315.45 | 36475.575 | 1374.58 | 1374.58
PeopleSoft Enterprise Purchasing | 92083 | 81770.5 | 0 | 81770.5 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19408.935 | 0 |  | 0 | 1033.69 | 1520.14 |  | 0 | 0 | 0 |  | 1520.14 | -18922.485 | 38817.87 | 0 |  | 0 | 1550.535 | 0 |  | 0 | 0 | 0 |  | 0 | 19408.935 | 0 |  | 0 | 1550.535 | 0 |  | 0 | 20442.625 | 0 |  | 0 | 0 | 0 | 83290.64 | 40338.01 | 1520.14 | 1520.14
PeopleSoft Enterprise Supplier Contract Management | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 1374.58 |  | 0 | 0 | 0 |  | 1374.58 | -17110.6375 | 35100.995 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 75315.45 | 36475.575 | 1374.58 | 1374.58
PeopleSoft Enterprise Treasury | 92083 | 59152.27 | 0 | 59152.27 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14040.2925 | 0 |  | 0 | 747.775 | 1099.67 |  | 0 | 0 | 0 |  | 1099.67 | -13688.3975 | 28080.585 | 0 |  | 0 | 1121.6625 | 0 |  | 0 | 0 | 0 |  | 0 | 14040.2925 | 0 |  | 0 | 1121.6625 | 0 |  | 0 | 14788.0675 | 0 |  | 0 | 0 | 0 | 60251.94 | 29180.255 | 1099.67 | 1099.67
PeopleSoft Enterprise Time and Labor | 114800 | 154154.54 | 0 | 154154.54 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 38538.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -38538.635 | 12846.2117 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 12846.2117 | 12846.2117 | 0 | 0
Analytics |  | 54273.384 |  | 54273.384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 0 | 13302.3 | 0 | 0 | -266.046 | 0 | 0 | 0 | 13302.3 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.35 | 0 | 0 | 0 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 54007.35 | 13302.3 | 13302.3 | 13302.3
HR Analytics (DW/BI) | 100 | 45227.82 | 0 | 45227.82 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 0 | 11085.25 |  | 0 | -221.705 | 0 | 0 |  | 11085.25 | 11307 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11307 | 0 |  | 0 | 11307 | 0 |  | 0 | 0 | 0 | 45006.25 | 11085.25 | 11085.25 | 11085.25
Project Analytics (DW/BI) | 20 | 9045.564 | 0 | 9045.564 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 0 | 2217.05 |  | 0 | -44.341 | 0 | 0 |  | 2217.05 | 2261.35 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2261.35 | 0 |  | 0 | 2261.35 | 0 |  | 0 | 0 | 0 | 9001.1 | 2217.05 | 2217.05 | 2217.05
OCI |  | 0 |  | 334079.18 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 11802.05 | 0 | 0 | -71717.745 | 27839.9317 | 0 | 0 | 11802.05 | 27839.9317 | 5920.44 | 0 | 5920.44 | 27839.9317 | 6300.52 | 0 | 0 | -71298.835 | 27839.9317 | 0 | 0 | 6300.52 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 0 | 0 | 191062.6 | 51862.9417 | 24023.01 | 24023.01
OAC (DW/BI) - DEV: $53,218.69 - Test : $63,779.29 - DR : $93,780.73 - Production : $123,300.47 | 4 | 0 | 334079.18 | 334079.18 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 11802.05 |  | 0 | -71717.745 | 27839.9317 | 0 |  | 11802.05 | 27839.9317 | 5920.44 |  | 5920.44 | 27839.9317 | 6300.52 |  | 0 | -71298.835 | 27839.9317 | 0 |  | 6300.52 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 0 | 0 | 191062.6 | 51862.9417 | 24023.01 | 24023.01
New License Purchase and Tech Support |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 1572674.662 |  | 1906753.842 | 27839.9317 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 27839.9317 | 11802.05 | #REF! | 0 | -71717.745 | 395992.6887 | 0 | #REF! | 11802.05 | 52855.8402 | 23925.47 | #REF! | 7090.84 | 27839.9317 | 19602.82 | #REF! | 16834.63 | -433160.1705 | 725226.255 | 0 | #REF! | 19602.82 | 101158.3071 | 0 | #REF! | 0 | 55679.8633 | 0 | #REF! | 0 | 384029.9533 | 0 | #REF! | 0 | 101158.3071 | 0 | #REF! | 0 | 423784.6158 | 0 | #REF! | 0 | 0 | 0 | 1638623.0017 | 752716.6633 | 55330.34 | 79353.35
Projected FYTD |  |  |  |  | 27839.9317 |  |  |  | 55679.8633 |  |  |  | 83519.795 |  |  |  |  | 407794.7387 |  |  |  | 460650.5788 |  |  |  | 488490.5105 |  |  |  |  | 780556.595 |  |  |  | 881714.9021 |  |  |  | 937394.7654 |  |  |  | 1321424.7188 |  |  |  | 1422583.0258 |  |  |  | 1846367.6417
Incurred FYTD | [5 empty] | 0 |  |  |  | 0 |  |  |  | 11802.05 |  |  | 11802.05 |  | 11802.05 |  |  |  | 35727.52 |  |  |  | 55330.34 |  |  | 102859.91 |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34
Paid FYTD | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 11802.05 |  |  |  | 18892.89 |  |  |  | 35727.52 | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34