## Monthly Summary
Department of Financial Services
Florida PALM FY 2024 - 2025 Spend Plan Summary FYTD
As of February 28, 2025
Annual
| TRUE | TRUE | TRUE |  | TRUE | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  |  | Q2 Basline Adjustment | October 2024 |  |  |  | November 2024 |  |  |  | December 2024 |  |  |  | Q3 Baseline Adjustment | January 2025 |  |  |  | February 2025 |  |  |  | Q4 Baseline Adjustment | March 2025 |  |  | April 2025 |  |  | May 2025 |  |  | June 2025 |  |  | CF 2024-25 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 46381361 | 30916123 | 15465238 | 38225141.2074 | 13359130.237 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| Appropriated | Released | Unreleased | Projected | Release Remaining | [12 empty] | Q1 Baseline Adjustment | [12 empty] | Q1 Baseline Adjustment | [8 empty] | Q1 Baseline Adjustment
FLAIR System Replacement (100781) | 46381361 | 30916123 | 15465238 | 38225141.2074 | 13359130.237 | 3724003.7017 | 3754458.96 |  | 3526393.96 | 1038867.7017 | 980185.15 |  | 912032.65 | 1104165.7017 | 956326.57 |  | 931197.19 | -176066.425 | 5078311.7037 | 1166508.099 |  | 1146445.87 | 2289008.2902 | 2151345.867 |  | 2196318.16 | 3073416.3817 | 2957055.409 |  | 973289.149 | -4165827.0005 | 10468319.2833 | 2516217.068 |  | 4492107.49 | 1179562.9854 | 3074895.64 |  | 1644450.55 | -6046327.0607 | 3636210.9959 | 0 | 0 | 4935069.1962 | 0 | 0 | 2986102.1999 | 0 | 0 | 9100323.5524 | 0 | 0 | 0 | 0 | 23613762.3238 | 17556992.763 | 15822235.019 | 20616800.2847 | 54.01%
SSI Implementation Services (FP004) |  |  |  | 22940987 |  | 2250000 | 2250000 |  | 2250000 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3450000 | 0 | 2 | 0 | 1200000 | 1200000 |  | 1200000 | 2000000 | 2000000 |  | 0 | -3450000 | 8450000 | 1350000 | 2 | 3350000 | 0 | 1350000 | 3 | 1350000 | -5750000 | 2289953 | 0 | 0 | 3200000 | 0 | 0 | 1750000 | 0 | 0 | 7551034 | 0 | 0 | 0 | 0 | 13900000 | 8150000 | 8150000 | 14790987 | 64.47%
Facilities and Maintenance (FP004) |  |  |  | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 277128 | 277128 | 277128 | 138564 | 33.33%
Production Support (FP004) |  |  |  | 9354902 |  | 1134539 | 1225344 | 3 | 1225344 | 686100 | 686100 |  | 686100 | 686100 | 686100 |  | 686100 | 90805 | 873512 | 873512 |  | 873512 | 686100 | 686100 |  | 686100 | 681970 | 686100 |  | 686100 | 4130 | 869382 | 869382 |  | 869382 | 690970 | 690970 |  | 0 | 0 | 690970 | 0 | 0 | 878384 | 0 | 0 | 690970 | 0 | 0 | 690970 | 0 | 0 | 0 | 0 | 6403608 | 6403608 | 5712638 | 2951294 | 31.55%
Additional Facilities |  |  |  | 174669.05 |  | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 10756.18 | 0 | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 0 | 10756.18 | 10756.18 |  | 21512.36 | 0 | 10756.18 | 10756.18 |  | 10756.18 | 19745.18 | 10756.18 | 2 | 10756.18 | -8989 | 28734.18 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 0 | 0 | 95038.44 | 86049.44 | 86049.44 | 88619.61 | 50.74%
Production Support Administration |  |  |  | 49558.17 |  | 2403.26 | 2383.44 |  | 2383.44 | 2403.26 | 2383.26 |  | 2383.26 | 2403.26 | 2383.26 |  | 0 | -59.82 | 2383.26 | 2383.26 |  | 2383.26 | 2383.26 | 2383.26 |  | 0 | 2383.26 | 2383.26 |  | 7149.78 | 0 | 27383.26 | 23342.13 |  | 6991.47 | 2383.26 | 2383.26 | 2 | 16350.66 | -4041.13 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 0 | 0 | 44066.26 | 40025.13 | 37641.87 | 9533.04 | 19.24%
Oracle Software and Maintenance (FP005) |  |  |  | 1620407.0167 |  | 27839.9317 | 0 | 2 | 0 | 27839.9317 | 0 | 2 | 0 | 27839.9317 | 11802.05 | 2 | 0 | -71717.745 | 395992.6887 | 0 | 2 | 11802.05 | 52855.8402 | 23925.47 | 2 | 7090.84 | 27839.9317 | 19602.82 | 2 | 16834.63 | -433160.1705 | 697386.3233 | 0 | 2 | 19602.82 | 59750.0254 | 718471.32 | 3 | 1170.4 | -38665.0287 | 42839.9317 | 0 | 0 | 356190.0217 | 0 | 0 | 59750.0254 | 0 | 0 | 387825.3779 | 0 | 0 | 0 | 0 | 812466.6887 | 773801.66 | 56500.74 | 846605.3567 | 52.25%
Project Administration |  |  |  | 235507.4708 |  | 22096.33 | 3269.34 | 2 | 3269.34 | 14735.33 | 15871.21 | 3 | 15871.21 | 87505.33 | 8724.08 | 2 | 202.51 | -96472.36 | 44898.575 | 15975.159 | 2 | 27771.38 | 12488.01 | 12253.957 |  | 11917.82 | 7778.01 | 783.149 | 2 | -2556.621 | -36152.33 | 89210.52 | 1043.758 | 2 | 1445.02 | 11313.52 | 1675.88 | 2 | 892.81 | -97804.402 | 132641.6242 | 0 | 0 | 14573.1045 | 0 | 0 | 14348.1045 | 0 | 0 | 14348.1045 | 0 | 0 | 0 | 0 | 157400.935 | 59596.533 | 58813.469 | 124562.778 | 67.64%
Support Services |  |  |  | 2181702 |  | 159536 | 149537 | 1 | 0 | 180200 | 150249.5 | 1 | 100297 | 180200 | 136177.5 | 1 | 149049.5 | -83972 | 180200 | 144268.5 | 1 | 90197.5 | 222536 | 123830 | 1 | 195448.5 | 229592 | 132285 | 1 | 128300 | -231944.5 | 196160 | 146090 | 1 | 128785 | 208000 | 155542 | 1 | 149677.5 | -92085.5 | 258320 | 0 | 0 | 270240 | 0 | 0 | 258320 | 0 | 0 | 246400 | 0 | 0 | 0 | 0 | 1240507.5 | 1137979.5 | 941755 | 1043722.5 | 47.84%
QA Support Services |  |  |  | 1251716.5 |  | 82192 | 78528 |  | 0 | 82192 | 80184 |  | 61984 | 74720 | 65742.5 |  | 50448 | -14649.5 | 85928 | 84972 |  | 95382.5 | 67248 | 57456 |  | 61120 | 78456 | 70504 |  | 81308 | -18700 | 93400 | 80962 | 1 | 70504 | 152760 | 110456 | 1 | 80962 | -54742 | 155728 | 0 | 0 | 158696 | 0 | 0 | 155728 | 0 | 0 | 152760 | 0 | 0 | 0 | 0 | 683546.5 | 628804.5 | 501708.5 | 622912 | 49.76%
IT Service Management Implementation and Software (100777) | 1304572 | 1304572 | 0 | 1176120.85 | 418647.39 | 38576.48 | 0 |  | 0 | 963.52 | 37612.96 |  | 37612.96 | 20124.28 | 0 |  | 0 | -22051.32 | 149298.91 | 149085.39 |  | 750 | 3333.09 | 750 |  | 19910.76 | 16139.54 | 17920.59 |  | 0 | -1015.56 | 963.52 | 1815 |  | 4776.95 | 668820.28 | 678740.67 |  | 141699.24 | 10771.87 | 1338.52 | 0 | 0 | 963.52 | 0 | 0 | 20391.58 | 0 | 0 | 267502.62 | 0 | 0 | 0 | 0 | 875152.74 | 885924.61 | 204749.91 | 290196.24 | 24.67%
ITSM Implementation and Administrative Support |  |  |  | 497726.51 |  | 37612.96 | 0 | 2 | 0 | 0 | 37612.96 | 3 | 37612.96 | 19160.76 | 0 | 2 | 0 | -19160.76 | 148335.39 | 148335.39 |  | 0 | 2369.57 | 0 | 2 | 19160.76 | 15176.02 | 17545.59 | 3 | 0 | 0 | 0 | 0 |  | 2961.95 | 0 | 8265.41 | 3 | 140739.24 | 8265.41 | 0 | 0 | 0 | 0 | 0 | 0 | 19428.06 | 0 | 0 | 266539.1 | 0 | 0 | 0 | 0 | 203493.94 | 211759.35 | 200474.91 | 285967.16 | 57.45%
ITSM Software |  |  |  | 678394.34 |  | 963.52 | 0 | 2 | 0 | 963.52 | 0 | 2 | 0 | 963.52 | 0 | 2 | 0 | -2890.56 | 963.52 | 750 | 2 | 750 | 963.52 | 750 | 2 | 750 | 963.52 | 375 | 2 | 0 | -1015.56 | 963.52 | 1815 | 3 | 1815 | 668820.28 | 670475.26 |  | 960 | 2506.46 | 1338.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 0 | 0 | 671658.8 | 674165.26 | 4275 | 4229.08 | 0.6234%
Contingency (100819) | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Salaries & Benefits (010000) | 10220897 | 10220897 | 0 | 9474293.59 | 4042090.74 | 823871.84 | 697273.25 |  | 697273.25 | 823871.83 | 777393.67 |  | 777393.67 | 823871.83 | 768441.69 |  | 768441.69 | -228506.89 | 823871.84 | 791115 |  | 791115 | 823871.83 | 764424.06 |  | 764424.06 | 823871.83 | 814406.38 |  | 814406.38 | -101670.06 | 823871.84 | 786352.09 |  | 786352.09 | 823871.83 | 779400.12 |  | 779400.12 | -81991.46 | 823871.83 | 0 | 0 | 823871.84 | 0 | 0 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 0 | 0 | 6260797.72 | 6178806.26 | 6178806.26 | 3295487.33 | 34.78%
Risk Management Insurance (103241) | 13957 | 13957 | 0 | 13957 | 0 | 7978 | 0 |  | 0 | 0 | 13957 | 5 | 13957 | 0 | 0 |  | 0 | 5979 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13957 | 13957 | 13957 | 0 | 0%
DMS HR Transfer (107040) | 24000 | 24000 | 0 | 24000 | 18000 | 6152.25 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -6152.25 | 12000 | 0 |  | 0 | 0 | 6000 |  | 6000 | 0 | 0 |  | 0 | -6000 | 12000 | 0 |  | 0 | 0 | 0 |  | 0 | -12000 | 12000 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 6000 | 6000 | 18000 | 75%
Totals | 60944787 | 42479549 | 18465238 | 48913512.6474 | 17837868.367 | 4600582.2717 | 4451732.21 |  | 4223667.21 | 1863703.0517 | 1809148.78 |  | 1740996.28 | 1948161.8117 | 1724768.26 |  | 1699638.88 | -426797.885 | 6063482.4537 | 2106708.489 |  | 1938310.87 | 3116213.2102 | 2922519.927 |  | 2986652.98 | 3913427.7517 | 3789382.379 |  | 1787695.529 | -4274512.6205 | 11305154.6433 | 3304384.158 |  | 5283236.53 | 2672255.0954 | 4533036.43 |  | 2565549.91 | -6129546.6507 | 4422073.1862 | 0 | 0 | 5765904.5562 | 0 | 0 | 3830365.6099 | 0 | 0 | 10191698.0024 | 0 | 0 | 0 | 0 | 30781669.7837 | 24641680.633 | 22225748.189 | 24220483.8547 | 49.57%
Running Totals | [5 empty] | 4600582.2717 | 4451732.21 |  | 4223667.21 | 6464285.3233 | 6260880.99 |  | 5964663.49 | 8412447.135 | 7985649.25 |  | 7664302.37 | 7985649.25 | 14049131.7037 | 10092357.739 |  | 9602613.24 | 17165344.9138 | 13014877.666 |  | 12589266.22 | 21078772.6655 | 16804260.045 |  | 14376961.749 | 16804260.045 | 28109414.6883 | 20108644.203 |  | 19660198.279 | 30781669.7837 | 24641680.633 |  | 22225748.189 | 24652123.133 | 29074196.3192 | 24641680.633 | 22225748.189 | 34840100.8753 | 24641680.633 | 22225748.189 | 38670466.4852 | 24641680.633 | 22225748.189 | 48862164.4877 | 24641680.633 | 22225748.189 |  | 22225748.189
Monthly Total Incurred/Total Projected | [5 empty] | 96.76% |  |  |  | 97.07% |  |  |  | 88.53% |  |  |  |  | 34.74% |  |  |  | 93.78% |  |  |  | 96.83% |  |  |  |  | 29.23% |  |  |  | 169.6% |  |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Monthly Total Incurred/Total Projected (Variance) | [5 empty] | -3.235% |  |  |  | -2.927% |  |  |  | -11.47% |  |  |  |  | -65.26% |  |  |  | -6.216% |  |  |  | -3.17% |  |  |  |  | -70.77% |  |  |  | 69.63% |  |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [5 empty] | 96.76% |  |  |  | 96.85% |  |  |  | 94.93% |  |  |  |  | 71.84% |  |  |  | 75.82% |  |  |  | 79.72% |  |  |  |  | 71.54% |  |  |  | 80.05% |  |  |  |  | 84.75% |  |  | 70.73% |  |  | 63.72% |  |  | 50.43%
FYTD Total Incurred/Total Projected (Variance) | [5 empty] | -3.235% |  |  |  | -3.147% |  |  |  | -5.073% |  |  |  |  | -28.16% |  |  |  | -24.18% |  |  |  | -20.28% |  |  |  |  | -28.46% |  |  |  | -19.95% |  |  |  |  | -15.25% |  |  | -29.27% |  |  | -36.28% |  |  | -49.57%

## Footnotes
Department of Financial Services
FY 2024 - 2025 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Incurred amounts were greater than anticipated due to an additional appropriation to the category.
6

## SSI Detail
|  |  |  | July 2024 |  |  | August 2024 |  |  | September 2024 |  |  | Q2 Baseline Adjustment | October 2024 |  |  | November 2024 |  |  | December 2024 |  |  | Q3 Baseline Adjustment | January 2025 |  |  | February 2025 |  |  | Q4 Baseline Adjustment | March 2025 |  |  | April 2025 |  |  | May 2025 |  |  | June 2025 |  |  | CF 2024-25
|  | Description | Total Deliverable Cost FY 24-25 | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid |  | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid |  | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid |  | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Projection | Projection Remaining | Projected FYTD | Total Accepted / Approved | Projected FYTD Pending | Total Paid | Payment Pending
Department of Financial Services
Florida PALM FY 2024 - 2025 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
D648 | Completion of Build Segment II | Implementation | 2250000 | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 2250000 | 2250000 | 0 | 2250000 | 0
D649 | Completion of Build Segment III | Implementation | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | -2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2250000 | 2250000 | 0 | 2250000 | 0 | 0
D650 | Completion of Solution Design (Requirements) DW/BI | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000 | 1200000 | 0 | 1200000 | 0
D651 | Completion of Mock Conversion I | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | -1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | -1200000 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 1200000 | 0 | 1200000 | 0 | 0
D652 | Completion of System Test Segment I | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000 | 2000000 | 0 | 2000000 | 0
D653 | Completion of Build Segment I DW/BI | Implementation | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 1350000 | 1350000 | 0 | 1350000 | 0
D654 | Completion of Build Segment IV | Implementation | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650000 | 0 | 0 | 0 | 0 | 0 | -2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650000 | 0 | 0 | 0 | 0 | 2650000 | 2650000 | 2650000 | 0 | 2650000 | 0 | 0
D655 | Completion of Mock Conversion II (System Test Environment) | Implementation | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | -1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 1000000 | 1000000 | 0 | 1000000 | 0 | 0
D656 | Completion of System Test Segment II | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0
D657 | Completion of Mock Conversion III (UAT) | Implementation | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0
D658 | Develop the Deployment and Contingency Plan | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0
D659 | Completion of Build Segment II DW/BI | Implementation | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0
D660 | Payroll Parallel Testing Plan | Implementation | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 550000 | 280000 | 0 | 0 | 0 | 0 | 0
D662 | Completion of Dress Rehearsal (Mock Conversion IV) | Implementation | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0
D663 | Completion of Interface Testing Segment I | Implementation | 2081700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081700 | 0 | 0 | 0 | 0 | 0
D664 | Development of the Hypercare Support Plan | Implementation | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 455000 | 455000 | 0 | 0 | 0 | 0 | 0
D665 | Updated Post-Implementation Support Plan | Implementation | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 455000 | 455000 | 0 | 0 | 0 | 0 | 0
D666 | Support of UAT Segment I | Implementation | 2236500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2236500 | 0 | 0 | 0 | 0 | 0
D668 | Completion of Build Segment III DW/BI | Implementation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0
D696 | Completion of System Test Segment III | Implementation | 1378840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1378840 | 0 | 0 | 0 | 0 | 0
D698 | Completion of Inter/IntraUnit and Receipt Accrual Cost Collection Build | Implementation | 54867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54867 | 0 | 0 | 0 | 0 | 54867 | 54867 | 0 | 0 | 0 | 0 | 0
D699 | Completion of AM Physical Inventory File Path Build | Implementation | 36167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36167 | 0 | 0 | 0 | 0 | 36167 | 36167 | 0 | 0 | 0 | 0 | 0
D700 | Completion of Cash Reporting Solution Enhancement Build | Implementation | 39953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39953 | 39953 | 0 | 0 | 0 | 0 | 0
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 415692 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692 | 173205 | 242487 | 242487 | 0 | 242487 | 0
Prod Supp | AM Services | Prod Supp | 6849800 | 554500 | 554500 | 554500 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 0 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 0 | 572300 | 572300 | 572300 | 572300 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 0 | 0 | 6849800 | 2861500 | 3988300 | 3988300 | 0 | 3988300 | 0
Prod Supp | IM Services (includes month credit -$4,130 from A10) | Prod Supp | 1406700 | 109900 | 109900 | 109900 | 113800 | 113800 | 113800 | 113800 | 113800 | 113800 | 0 | 113800 | 113800 | 113800 | 113800 | 113800 | 113800 | 109670 | 113800 | 113800 | 4130 | 109670 | 109670 | 109670 | 118670 | 118670 | 0 | 0 | 118670 | 0 | 0 | 118670 | 0 | 0 | 118670 | 0 | 0 | 118670 | 0 | 0 | 0 | 0 | 1381920 | 593350 | 788570 | 788570 | 0 | 788570 | 0
Prod Supp | Oracle OCI Costs | Prod Supp | 749650 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749650 | 187414 | 562236 | 562236 | 0 | 562236 | 0
Prod Supp | Support Tools Maintenance | Prod Supp | 46381 | 46381 | 46381 | 46381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46381 | 0 | 46381 | 46381 | 0 | 46381 | 0
Prod Supp | Support Tools Purchase | Prod Supp | 311780 | 203556 | 311780 | 311780 | 0 | 0 | 0 | 0 | 0 | 0 | 108224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311780 | 0 | 311780 | 311780 | 0 | 311780 | 0
Prod Supp | Solution Software Support | Prod Supp | 32790 | 32790 | 15371 | 15371 | 0 | 0 | 0 | 0 | 0 | 0 | -17419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15371 | 0 | 15371 | 15371 | 0 | 15371 | 0
| Implementation Total: |  |  | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450000 | 0 | 0 | 1200000 | 1200000 | 1200000 | 2000000 | 2000000 | 0 |  | 8450000 | 1350000 | 3350000 | 0 | 1350000 | 1350000 |  | 2289953 | 0 | 0 | 3200000 | 0 | 0 | 1750000 | 0 | 0 | 7551034 | 0 | 0 | 0 | 0 | 22940987 | 14790987 | 0 | 8150000 | -8150000 | 8150000 | 0
| Production Support Facilities Total: |  |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 |  | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692 | 138564 | 0 | 277128 | -277128 | 277128 | 0
| Production Support (No Facilities) Total: |  |  | 1134539 | 1225344 | 1225344 | 686100 | 686100 | 686100 | 686100 | 686100 | 686100 |  | 873512 | 873512 | 873512 | 686100 | 686100 | 686100 | 681970 | 686100 | 686100 |  | 869382 | 869382 | 869382 | 690970 | 690970 | 0 |  | 690970 | 0 | 0 | 878384 | 0 | 0 | 690970 | 0 | 0 | 690970 | 0 | 0 | 0 | 0 | 9354902 | 2951294 | 0 | 6403608 | -6403608 | 5712638 | 690970
Monthly Totals |  |  | 38580820 | 3419180 | 3509985 | 3509985 | 720741 | 720741 | 720741 | 720741 | 720741 | 720741 | 90805 | 4358153 | 908153 | 908153 | 1920741 | 1920741 | 1920741 | 2716611 | 2720741 | 720741 | -3445870 | 9354023 | 2254023 | 4254023 | 725611 | 2075611 | 1384641 | -5750000 | 3015564 | 0 | 0 | 4113025 | 0 | 0 | 2475611 | 0 | 0 | 8276645 | 0 | 0 | 0 | 0 | 32711581 | 27133496 | 19855125 | 12755125 | 7100000 | 12755125 | 0
| Projected YTD |  |  | 3419180 |  |  | 4139921 |  |  | 4860662 |  |  | 4951467 | 9309620 |  |  | 11230361 |  |  | 13946972 |  |  | 10501102 | 19855125 |  |  | 20580736 |  |  | 14830736 | 17846300 |  |  | 21959325 |  |  | 24434936 |  |  | 32711581
| Incurred YTD |  |  |  | 3509985 |  |  | 4230726 |  |  | 4951467 |  |  |  | 5859620 |  |  | 7780361 |  |  | 10501102 |  |  |  | 12755125 |  |  | 14830736 |  |  |  | 14830736 |  |  | 14830736 |  |  | 14830736 |  |  | 14830736 |  | 14830736
| Paid YTD |  |  |  |  | 3509985 |  |  | 4230726 |  |  | 4951467 |  |  |  | 5859620 |  |  | 7780361 |  |  | 8501102 |  |  |  | 12755125 |  |  | 14139766 |  |  |  | 14139766 |  |  | 14139766 |  |  | 14139766 |  |  | 14139766 |  | 14139766

## Oracle Summary
Department of Financial Services
Florida PALM FY 2024 - 2025 Oracle Summary FYTD
| Quantity/Months | Quote |  |  | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  |  | Q2 Baseline Adjustment | October 2024 |  |  |  | November 2024 |  |  |  | December 2024 |  |  |  | Q3 Baseline Adjustment | January 2025 |  |  |  | February 2025 |  |  |  | Q4 Baseline Adjustment | March 2025 |  |  |  | April 2025 |  |  |  | May 2025 |  |  |  | June 2025 |  |  |  | FY 2024-25 CF |  | Total
Program |  | Tech Support | Total Purchase/ Subscription | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | CF Incurred | CF Paid | Total Projected | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support |  | 1518401.278 |  | 1518401.278 | 0 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 |  | 368152.757 | 0 | #REF! | 0 | 11447.5625 | 18005.03 | #REF! | 1170.4 | 0 | 0 | #REF! | 16834.63 | -361595.2895 | 697386.3233 | 0 | #REF! | 0 | 59750.0254 | 682368.79 | #REF! | 1170.4 | -5519.3454 | 42839.9317 | 0 | #REF! | 0 | 356190.0217 | 0 | #REF! | 0 | 59750.0254 | 0 | #REF! | 0 | 382376.3342 | 0 | #REF! | 0 | 0 | 0 | 1659072.0454 | 812466.6888 | 773801.66 | 56500.74
Assignment |  | 1518401.278 | 0 | 1518401.278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 368152.757 | 0 | 0 | 0 | 11447.5625 | 18005.03 | 0 | 1170.4 | 0 | 0 | 0 | 16834.63 |  | 669546.3917 | 0 | 0 | 0 | 18341.7437 | 682368.79 | 0 | 1170.4 |  | 0 | 0 | 0 | 0 | 328350.09 | 0 | 0 | 0 | 18341.7437 | 0 | 0 | 0 | 340968.0525 | 0 | 0 | 0 | 0 | 0 | 1399002.0954 | 705893.1654 | 700373.82 | 19175.43
Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 2 | 8525.418 | 0 | 8525.418 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 2131.3545 | 0 |  | 0 | 0 | 1170.4 |  | 1170.4 | 0 | 0 |  | 0 | -960.9545 | 1734.645 | 0 |  | 0 | 1170.4 | 2905.04 |  | 1170.4 | -0.005 | 0 | 0 |  | 0 | 867.3225 | 0 |  | 0 | 1170.4 | 0 |  | 0 | 2037.7225 | 0 |  | 0 | 0 | 0 | 8150.89 | 4075.445 | 4075.44 | 2340.8
Oracle Business Intelligence (Analytics) Server Administrator | 4 | 1479.59 | 0 | 1479.59 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -369.8975 | 739.795 | 0 |  | 0 | 0 | 739.8 |  | 0 | 0.005 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 | 1479.59 | 739.795 | 739.8 | 0
Oracle Business Intelligence Management Pack | 4 | 2933.77 | 0 | 2933.77 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -733.4425 | 1466.885 | 0 |  | 0 | 0 | 1466.88 |  | 0 | -0.005 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 | 2933.77 | 1466.885 | 1466.88 | 0
Oracle Business Intelligence Suite Foundation Edition | 4 | 76549.07 | 0 | 76549.07 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -19137.2675 | 38274.535 | 0 |  | 0 | 0 | 38274.54 |  | 0 | 0.005 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 | 76549.07 | 38274.535 | 38274.54 | 0
Oracle Data Integrator Enterprise Edition | 20 | 38274.54 | 0 | 38274.54 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -9568.635 | 19137.27 | 0 |  | 0 | 0 | 19137.28 |  | 0 | 0.01 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 | 38274.54 | 19137.27 | 19137.28 | 0
Oracle Data Visualization | 4 | 25517.06 | 0 | 25517.06 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -6379.265 | 12758.53 | 0 |  | 0 | 0 | 12758.54 |  | 0 | 0.01 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 | 25517.06 | 12758.53 | 12758.54 | 0
Oracle Financial Analytics Fusion Edition (DW/BI) | 100 | 14800.11 | 0 | 14800.11 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -3700.0275 | 7400.055 | 0 |  | 0 | 0 | 7400.06 |  | 0 | 0.005 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 | 14800.11 | 7400.055 | 7400.06 | 0
Oracle Managed File Transfer | 12 | 21373.31 | 0 | 21373.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5343.3275 | 10686.655 | 0 |  | 0 | 0 | 10686.66 |  | 0 | 0.005 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 | 21373.31 | 10686.655 | 10686.66 | 0
Oracle Management Pack for Oracle Data Integrator | 16 | 7042.33 | 0 | 7042.33 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -1760.5825 | 3521.165 | 0 |  | 0 | 0 | 3521.16 |  | 0 | -0.005 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 | 7042.33 | 3521.165 | 3521.16 | 0
Oracle SOA Management Pack Enterprise Edition | 14 | 20670.71 | 0 | 20670.71 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5167.6775 | 10335.355 | 0 |  | 0 | 0 | 10335.36 |  | 0 | 0.005 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 | 20670.71 | 10335.355 | 10335.36 | 0
Oracle SOA Suite for Oracle Middleware | 14 | 47542.18 | 0 | 47542.18 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -11885.545 | 23771.09 | 0 |  | 0 | 0 | 23771.1 |  | 0 | 0.01 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 | 47542.18 | 23771.09 | 23771.1 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 26 | 18471 | 0 | 18471 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -4617.75 | 9235.5 | 0 |  | 0 | 0 | 9235.52 |  | 0 | 0.02 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 | 18471 | 9235.5 | 9235.52 | 0
Oracle WebLogic Suite | 26 | 69266.8 | 0 | 69266.8 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -17316.7 | 34633.4 | 0 |  | 0 | 0 | 34633.4 |  | 0 | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 | 69266.8 | 34633.4 | 34633.4 | 0
PeopleSoft Enterprise Contracts | 92083 | 55673.81 | 0 | 55673.81 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13214.6675 | 0 |  | 0 | 703.785 | 1034.99 |  | 0 | 0 | 0 |  | 1034.99 | -12883.4625 | 26429.335 | 0 |  | 0 | 1055.6775 | 27150.02 |  | 0 | -334.9925 | 0 | 0 |  | 0 | 13214.6675 | 0 |  | 0 | 1055.6775 | 0 |  | 0 | 13918.4525 | 0 |  | 0 | 0 | 0 | 57043.7975 | 28520.0025 | 28185.01 | 1034.99
PeopleSoft Enterprise eSettlements | 92083 | 36536.19 | 0 | 36536.19 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 8672.185 | 0 |  | 0 | 461.8625 | 679.2 |  | 0 | 0 | 0 |  | 679.2 | -8454.8475 | 17344.37 | 0 |  | 0 | 692.7938 | 17817.33 |  | 0 | -219.8337 | 0 | 0 |  | 0 | 8672.185 | 0 |  | 0 | 692.7938 | 0 |  | 0 | 9134.0475 | 0 |  | 0 | 0 | 0 | 37435.2337 | 18716.3638 | 18496.53 | 679.2
PeopleSoft Enterprise Expenses | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 1374.58 |  | 0 | 0 | 0 |  | 1374.58 | -17110.6375 | 35100.995 | 0 |  | 0 | 1402.08 | 36058.13 |  | 0 | -444.945 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 75760.38 | 37877.655 | 37432.71 | 1374.58
PeopleSoft Enterprise Financials | 92083 | 398410.84 | 0 | 398410.84 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 94566.2225 | 0 |  | 0 | 5036.4875 | 7406.6 |  | 0 | 0 | 0 |  | 7406.6 | -92196.11 | 189132.445 | 0 |  | 0 | 7554.7312 | 194289.82 |  | 0 | -2397.3563 | 0 | 0 |  | 0 | 94566.2225 | 0 |  | 0 | 7554.7312 | 0 |  | 0 | 99602.71 | 0 |  | 0 | 0 | 0 | 408214.8113 | 204093.7762 | 201696.42 | 7406.6
PeopleSoft Enterprise Grants | 92083 | 52193.31 | 0 | 52193.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12388.525 | 0 |  | 0 | 659.8025 | 970.29 |  | 0 | 0 | 0 |  | 970.29 | -12078.0375 | 24777.05 | 0 |  | 0 | 989.7038 | 25452.7 |  | 0 | -314.0538 | 0 | 0 |  | 0 | 12388.525 | 0 |  | 0 | 989.7038 | 0 |  | 0 | 13048.3275 | 0 |  | 0 | 0 | 0 | 53477.6638 | 26737.0437 | 26422.99 | 970.29
PeopleSoft Enterprise Human Resources | 114800 | 47938.36 | 0 | 47938.36 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -11984.59 | 23969.18 | 0 |  | 0 | 0 | 23969.18 |  | 0 | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 | 47938.36 | 23969.18 | 23969.18 | 0
PeopleSoft Enterprise Payroll | 114800 | 58302.96 | 0 | 58302.96 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -14575.74 | 29151.48 | 0 |  | 0 | 0 | 29151.48 |  | 0 | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 | 58302.96 | 29151.48 | 29151.48 | 0
PeopleSoft Enterprise Project Costing | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 1374.58 |  | 0 | 0 | 0 |  | 1374.58 | -17110.6375 | 35100.995 | 0 |  | 0 | 1402.08 | 36058.13 |  | 0 | -444.945 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 75760.38 | 37877.655 | 37432.71 | 1374.58
PeopleSoft Enterprise Purchasing | 92083 | 81770.5 | 0 | 81770.5 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19408.935 | 0 |  | 0 | 1033.69 | 1520.14 |  | 0 | 0 | 0 |  | 1520.14 | -18922.485 | 38817.87 | 0 |  | 0 | 1550.535 | 39876.38 |  | 0 | -492.025 | 0 | 0 |  | 0 | 19408.935 | 0 |  | 0 | 1550.535 | 0 |  | 0 | 20442.625 | 0 |  | 0 | 0 | 0 | 83782.675 | 41888.545 | 41396.52 | 1520.14
PeopleSoft Enterprise Supplier Contract Management | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 1374.58 |  | 0 | 0 | 0 |  | 1374.58 | -17110.6375 | 35100.995 | 0 |  | 0 | 1402.08 | 36058.13 |  | 0 | -444.945 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 75760.38 | 37877.655 | 37432.71 | 1374.58
PeopleSoft Enterprise Treasury | 92083 | 59152.27 | 0 | 59152.27 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14040.2925 | 0 |  | 0 | 747.775 | 1099.67 |  | 0 | 0 | 0 |  | 1099.67 | -13688.3975 | 28080.585 | 0 |  | 0 | 1121.6625 | 28846.32 |  | 0 | -355.9275 | 0 | 0 |  | 0 | 14040.2925 | 0 |  | 0 | 1121.6625 | 0 |  | 0 | 14788.0675 | 0 |  | 0 | 0 | 0 | 60607.8825 | 30301.9175 | 29945.99 | 1099.67
PeopleSoft Enterprise Time and Labor | 114800 | 154154.54 | 0 | 154154.54 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 38538.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -38538.635 | 12846.2117 | 0 |  | 0 | 0 | 12775.83 |  | 0 | -70.3817 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 12846.2117 | 12846.2117 | 12775.83 | 0
Analytics |  | 54273.384 |  | 54273.384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 0 | 13302.3 | 0 | 0 | -266.046 | 0 | 0 | 0 | 13302.3 | 13568.35 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.35 | 0 | 0 | 0 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 54007.35 | 26870.65 | 26870.65 | 13302.3
HR Analytics (DW/BI) | 100 | 45227.82 | 0 | 45227.82 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 0 | 11085.25 |  | 0 | -221.705 | 0 | 0 |  | 11085.25 | 11307 | 11307 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11307 | 0 |  | 0 | 11307 | 0 |  | 0 | 0 | 0 | 45006.25 | 22392.25 | 22392.25 | 11085.25
Project Analytics (DW/BI) | 20 | 9045.564 | 0 | 9045.564 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 0 | 2217.05 |  | 0 | -44.341 | 0 | 0 |  | 2217.05 | 2261.35 | 2261.35 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2261.35 | 0 |  | 0 | 2261.35 | 0 |  | 0 | 0 | 0 | 9001.1 | 4478.4 | 4478.4 | 2217.05
OCI |  | 0 |  | 334079.18 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 11802.05 | 0 | 0 | -71717.745 | 27839.9317 | 0 | 0 | 11802.05 | 27839.9317 | 5920.44 | 0 | 5920.44 | 27839.9317 | 6300.52 | 0 | 0 | -71298.835 | 27839.9317 | 0 | 0 | 6300.52 | 27839.9317 | 22534.18 | 0 | 0 | -33145.6833 | 42839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 0 | 0 | 206062.6 | 79702.8733 | 46557.19 | 24023.01
OAC (DW/BI) - DEV: $53,218.69 - Test : $63,779.29 - DR : $93,780.73 - Production : $123,300.47 | 4 | 0 | 334079.18 | 334079.18 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 11802.05 |  | 0 | -71717.745 | 27839.9317 | 0 |  | 11802.05 | 27839.9317 | 5920.44 |  | 5920.44 | 27839.9317 | 6300.52 |  | 0 | -71298.835 | 27839.9317 | 0 |  | 6300.52 | 27839.9317 | 22534.18 |  | 0 | -33145.6833 | 42839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 0 | 0 | 206062.6 | 79702.8733 | 46557.19 | 24023.01
New License Purchase and Tech Support |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 1572674.662 |  | 1906753.842 | 27839.9317 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 27839.9317 | 11802.05 | #REF! | 0 | -71717.745 | 395992.6887 | 0 | #REF! | 11802.05 | 52855.8402 | 23925.47 | #REF! | 7090.84 | 27839.9317 | 19602.82 | #REF! | 16834.63 | -433160.1705 | 725226.255 | 0 | #REF! | 19602.82 | 59750.0254 | 718471.32 | #REF! | 1170.4 | -38665.0288 | 42839.9317 | 0 | #REF! | 0 | 356190.0217 | 0 | #REF! | 0 | 59750.0254 | 0 | #REF! | 0 | 382376.3342 | 0 | #REF! | 0 | 0 | 0 | 1659072.0454 | 812466.6888 | 773801.66 | 56500.74
Projected FYTD |  |  |  |  | 27839.9317 |  |  |  | 55679.8633 |  |  |  | 83519.795 |  |  |  |  | 407794.7387 |  |  |  | 460650.5788 |  |  |  | 488490.5105 |  |  |  | 55330.34 | 752716.6633 |  |  |  | 812466.6887 |  |  |  | 773801.66 | 816641.5917 |  |  |  | 1172831.6133 |  |  |  | 1232581.6387 |  |  |  | 1620407.0167
Incurred FYTD | [5 empty] | 0 |  |  |  | 0 |  |  |  | 11802.05 |  |  | 11802.05 |  | 11802.05 |  |  |  | 35727.52 |  |  |  | 55330.34 |  |  |  |  | 55330.34 |  |  |  | 773801.66 |  |  |  |  | 773801.66 |  |  |  | 773801.66 |  |  |  | 773801.66 |  |  |  | 773801.66
Paid FYTD | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 11802.05 |  |  |  | 11802.05 |  |  |  | 18892.89 |  |  |  | 35727.52 |  |  |  |  | 55330.34 |  |  |  | 56500.74 |  |  |  |  | 56500.74 |  |  |  | 56500.74 |  |  |  | 56500.74 |  |  |  | 56500.74