## Monthly Summary
Department of Financial Services
Florida PALM FY 2024 - 2025 Spend Plan Summary FYTD
As of December 31, 2024
Annual
| TRUE | TRUE | TRUE |  | TRUE | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  |  | Q2 Basline Adjustment | October 2024 |  |  |  | November 2024 |  |  |  | December 2024 |  |  |  | Q3 Baseline Adjustment | January 2025 |  |  | February 2025 |  |  | March 2025 |  |  | April 2025 |  |  | May 2025 |  |  | June 2025 |  |  | CF 2024-25 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 46381361 | 17337427 | 29043934 | 45658206.3472 | 5371546.945 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| Appropriated | Released | Unreleased | Projected | Release Remaining | [12 empty] | Q1 Baseline Adjustment | [12 empty] | Q1 Baseline Adjustment
FLAIR System Replacement (100781) | 46381361 | 17337427 | 29043934 | 45658206.3472 | 5371546.945 | 3724003.7017 | 3754458.96 |  | 3526393.96 | 1038867.7017 | 980185.15 |  | 912032.65 | 1104165.7017 | 956326.57 |  | 931197.19 | -176066.425 | 5078311.7014 | 1166508.099 |  | 1146445.87 | 2289008.2879 | 2151345.867 |  | 2196318.16 | 3073416.3817 | 2957055.409 |  | 973289.149 | -4165827.0005 | 10468735.9475 | 0 | 0 | 4732119.6496 | 0 | 0 | 3265042.5558 | 0 | 0 | 3376895.2758 | 0 | 0 | 3626056.2796 | 0 | 0 | 8223476.5883 | 0 | 0 | 0 | 0 | 16131707.0555 | 11965880.055 | 9685676.979 | 33692326.2967 | 73.79%
SSI Implementation Services (FP004) |  |  |  | 30118027 |  | 2250000 | 2250000 |  | 2250000 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3450000 | 0 | 2 | 0 | 1200000 | 1200000 |  | 1200000 | 2000000 | 2000000 |  | 0 | -3450000 | 8450000 | 0 | 0 | 3500000 | 0 | 0 | 2039953 | 0 | 0 | 1630000 | 0 | 0 | 2378840 | 0 | 0 | 6669234 | 0 | 0 | 0 | 0 | 8900000 | 5450000 | 3450000 | 24668027 | 81.9%
Facilities and Maintenance (FP004) |  |  |  | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 207846 | 207846 | 207846 | 207846 | 50%
Production Support (FP004) |  |  |  | 9354902 |  | 1134539 | 1225344 | 3 | 1225344 | 686100 | 686100 |  | 686100 | 686100 | 686100 |  | 686100 | 90805 | 873512 | 873512 |  | 873512 | 686100 | 686100 |  | 686100 | 681970 | 686100 |  | 686100 | 4130 | 869382 | 0 | 0 | 690970 | 0 | 0 | 690970 | 0 | 0 | 878384 | 0 | 0 | 690970 | 0 | 0 | 690970 | 0 | 0 | 0 | 0 | 4839126 | 4843256 | 4843256 | 4511646 | 48.23%
Additional Facilities |  |  |  | 174669.05 |  | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 10756.18 | 0 | 10756.18 | 10756.18 |  | 10756.18 | 10756.18 | 10756.18 |  | 0 | 10756.18 | 10756.18 |  | 21512.36 | 0 | 10756.18 | 0 | 0 | 19745.18 | 0 | 0 | 19745.18 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 0 | 0 | 64537.08 | 64537.08 | 64537.08 | 110131.97 | 63.05%
Production Support Administration |  |  |  | 53599.3 |  | 2403.26 | 2383.44 |  | 2383.44 | 2403.26 | 2383.26 |  | 2383.26 | 2403.26 | 2383.26 |  | 0 | -59.82 | 2383.26 | 2383.26 |  | 2383.26 | 2383.26 | 2383.26 |  | 0 | 2383.26 | 2383.26 |  | 7149.78 | 0 | 27383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 2383.26 | 0 | 0 | 0 | 0 | 14299.74 | 14299.74 | 14299.74 | 39299.56 | 73.32%
Oracle Software and Maintenance (FP005) |  |  |  | 1638623.0017 |  | 27839.9317 | 0 | 2 | 0 | 27839.9317 | 0 | 2 | 0 | 27839.9317 | 11802.05 | 2 | 0 | -71717.745 | 395992.6887 | 0 | 2 | 11802.05 | 52855.8402 | 23925.47 | 2 | 7090.84 | 27839.9317 | 19602.82 | 2 | 16834.63 | -433160.1705 | 697386.3233 | 0 | 0 | 59750.0254 | 0 | 0 | 27839.9317 | 0 | 0 | 356190.0217 | 0 | 0 | 59750.0254 | 0 | 0 | 382376.3342 | 0 | 0 | 0 | 0 | 488490.5105 | 55330.34 | 35727.52 | 1583292.6617 | 96.62%
Project Administration |  |  |  | 209999.9956 |  | 22096.33 | 3269.34 | 2 | 3269.34 | 14735.33 | 15871.21 | 3 | 15871.21 | 87505.33 | 8724.08 | 2 | 202.51 | -96472.36 | 44898.5728 | 15975.159 | 2 | 27771.38 | 12488.0078 | 12253.957 |  | 11917.82 | 7778.01 | 783.149 | 2 | -2556.621 | -36152.33 | 89627.1842 | 0 | 0 | 11230.1842 | 0 | 0 | 20510.1842 | 0 | 0 | 10735.1842 | 0 | 0 | 10510.1842 | 0 | 0 | 10510.1842 | 0 | 0 | 0 | 0 | 93029.225 | 56876.895 | 56475.639 | 153123.105 | 72.92%
Support Services |  |  |  | 2694907.5 |  | 159536 | 149537 | 1 | 0 | 180200 | 150249.5 | 1 | 100297 | 180200 | 136177.5 | 1 | 149049.5 | -83972 | 180200 | 144268.5 | 1 | 90197.5 | 222536 | 123830 | 1 | 195448.5 | 229592 | 132285 | 1 | 128300 | -231944.5 | 196160 | 0 | 0 | 320000 | 0 | 0 | 335600 | 0 | 0 | 351200 | 0 | 0 | 335600 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 1068292 | 836347.5 | 663292.5 | 1858560 | 68.97%
QA Support Services |  |  |  | 997786.5 |  | 82192 | 78528 |  | 0 | 82192 | 80184 |  | 61984 | 74720 | 65742.5 | 1 | 50448 | -14649.5 | 85928 | 84972 |  | 95382.5 | 67248 | 57456 |  | 61120 | 78456 | 70504 |  | 81308 | -18700 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 93400 | 0 | 0 | 0 | 0 | 456086.5 | 437386.5 | 350242.5 | 560400 | 56.16%
IT Service Management Implementation and Software (100777) | 1304572 | 1304572 | 0 | 879006.82 | 1099203.06 | 38576.48 | 0 |  | 0 | 963.52 | 37612.96 |  | 37612.96 | 20124.28 | 0 |  | 0 | -22051.32 | 149298.91 | 149085.39 |  | 750 | 3333.09 | 750 |  | 19910.76 | 16139.54 | 17920.59 |  | 0 | -1015.56 | 963.52 | 0 | 0 | 668820.28 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 0 | 0 | 206384.5 | 205368.94 | 58273.72 | 673637.88 | 76.64%
ITSM Implementation and Administrative Support |  |  |  | 203493.94 |  | 37612.96 | 0 | 2 | 0 | 0 | 37612.96 | 3 | 37612.96 | 19160.76 | 0 | 2 | 0 | -19160.76 | 148335.39 | 148335.39 |  | 0 | 2369.57 | 0 | 2 | 19160.76 | 15176.02 | 17545.59 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203493.94 | 203493.94 | 56773.72 | 0 | 0%
ITSM Software |  |  |  | 675512.88 |  | 963.52 | 0 | 2 | 0 | 963.52 | 0 | 2 | 0 | 963.52 | 0 | 2 | 0 | -2890.56 | 963.52 | 750 | 2 | 750 | 963.52 | 750 | 2 | 750 | 963.52 | 375 | 2 | 0 | -1015.56 | 963.52 | 0 | 0 | 668820.28 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 963.52 | 0 | 0 | 0 | 0 | 2890.56 | 1875 | 1500 | 673637.88 | 99.72%
Contingency (100819) | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Salaries & Benefits (010000) | 10146991 | 10146991 | 0 | 9556285.05 | 5533936.95 | 823871.84 | 697273.25 |  | 697273.25 | 823871.83 | 777393.67 |  | 777393.67 | 823871.83 | 768441.69 |  | 768441.69 | -228506.89 | 823871.84 | 791115 |  | 791115 | 823871.83 | 764424.06 |  | 764424.06 | 823871.83 | 814406.38 |  | 814406.38 | -101670.06 | 823871.84 | 0 | 0 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 823871.84 | 0 | 0 | 823871.83 | 0 | 0 | 823871.83 | 0 | 0 | 0 | 0 | 4714724.11 | 4613054.05 | 4613054.05 | 4943231 | 51.73%
Risk Management Insurance (103241) | 13957 | 13957 | 0 | 13957 | 0 | 7978 | 0 |  | 0 | 0 | 13957 | 5 | 13957 | 0 | 0 |  | 0 | 5979 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13957 | 13957 | 13957 | 0 | 0%
DMS HR Transfer (107040) | 24000 | 24000 | 0 | 24000 | 18000 | 6152.25 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -6152.25 | 12000 | 0 |  | 0 | 0 | 6000 |  | 6000 | 0 | 0 |  | 0 | -6000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 6000 | 6000 | 18000 | 75%
Totals | 60870881 | 28826947 | 32043934 | 56131455.2172 | 12022686.955 | 4600582.2717 | 4451732.21 |  | 4223667.21 | 1863703.0517 | 1809148.78 |  | 1740996.28 | 1948161.8117 | 1724768.26 |  | 1699638.88 | -426797.885 | 6063482.4514 | 2106708.489 |  | 1938310.87 | 3116213.2079 | 2922519.927 |  | 2986652.98 | 3913427.7517 | 3789382.379 |  | 1787695.529 | -4274512.6205 | 11305571.3075 | 0 | 0 | 6224811.7596 | 0 | 0 | 4089877.9058 | 0 | 0 | 4207730.6358 | 0 | 0 | 4450891.6296 | 0 | 0 | 9048311.9383 | 0 | 0 | 0 | 0 | 21078772.6655 | 16804260.045 | 14376961.749 | 39327195.1767 | 70.06%
Running Totals | [5 empty] | 4600582.2717 | 4451732.21 |  | 4223667.21 | 6464285.3233 | 6260880.99 |  | 5964663.49 | 8412447.135 | 7985649.25 |  | 7664302.37 | 7985649.25 | 14049131.7014 | 10092357.739 |  | 9602613.24 | 17165344.9094 | 13014877.666 |  | 12589266.22 | 21078772.6611 | 16804260.045 |  | 14376961.749 | 16804260.0406 | 32384343.9686 | 16804260.045 | 14376961.749 | 38609155.7281 | 16804260.045 | 14376961.749 | 42699033.634 | 16804260.045 | 14376961.749 | 46906764.2698 | 16804260.045 | 14376961.749 | 51357655.8994 | 16804260.045 | 14376961.749 | 60405967.8377 | 16804260.045 | 14376961.749 |  | 14376961.749
Monthly Total Incurred/Total Projected | [5 empty] | 96.76% |  |  |  | 97.07% |  |  |  | 88.53% |  |  |  |  | 34.74% |  |  |  | 93.78% |  |  |  | 96.83% |  |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Monthly Total Incurred/Total Projected (Variance) | [5 empty] | -3.235% |  |  |  | -2.927% |  |  |  | -11.47% |  |  |  |  | -65.26% |  |  |  | -6.216% |  |  |  | -3.17% |  |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [5 empty] | 96.76% |  |  |  | 96.85% |  |  |  | 94.93% |  |  |  |  | 71.84% |  |  |  | 75.82% |  |  |  | 79.72% |  |  |  |  | 51.89% |  |  | 43.52% |  |  | 39.36% |  |  | 35.82% |  |  | 32.72% |  |  | 27.82%
FYTD Total Incurred/Total Projected (Variance) | [5 empty] | -3.235% |  |  |  | -3.147% |  |  |  | -5.073% |  |  |  |  | -28.16% |  |  |  | -24.18% |  |  |  | -20.28% |  |  |  |  | -48.11% |  |  | -56.48% |  |  | -60.64% |  |  | -64.18% |  |  | -67.28% |  |  | -72.18%

## Footnotes
Department of Financial Services
FY 2024 - 2025 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Incurred amounts were greater than anticipated due to an additional appropriation to the category.
6

## SSI Detail
|  |  |  | July 2024 |  |  | August 2024 |  |  | September 2024 |  |  | Q2 Baseline Adjustment | October 2024 |  |  | November 2024 |  |  | December 2024 |  |  | Q3 Baseline Adjustment | January 2025 |  |  | February 2025 |  |  | March 2025 |  |  | April 2025 |  |  | May 2025 |  |  | June 2025 |  |  | CF 2024-25
|  | Description | Total Deliverable Cost FY 24-25 | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid |  | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid |  | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Projection | Projection Remaining | Projected FYTD | Total Accepted / Approved | Projected FYTD Pending | Total Paid | Payment Pending
Department of Financial Services
Florida PALM FY 2024 - 2025 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
D648 | Completion of Build Segment II | Implementation | 2250000 | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 2250000 | 2250000 | 0 | 2250000 | 0
D649 | Completion of Build Segment III | Implementation | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2250000 | 2250000 | 0 | 2250000 | 0 | 0
D650 | Completion of Solution Design (Requirements) DW/BI | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1200000 | 1200000 | 0 | 1200000 | 0
D651 | Completion of Mock Conversion I | Implementation | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | -1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 1200000 | 0 | 1200000 | 0 | 0
D652 | Completion of System Test Segment I | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 2000000 | 2000000 | 0 | 0 | 2000000
D653 | Completion of Build Segment I DW/BI | Implementation | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0
D654 | Completion of Build Segment IV | Implementation | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650000 | 2650000 | 0 | 0 | 0 | 0 | 0
D655 | Completion of Mock Conversion II (System Test Environment) | Implementation | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0
D656 | Completion of System Test Segment II | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0
D657 | Completion of Mock Conversion III (UAT) | Implementation | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0
D658 | Develop the Deployment and Contingency Plan | Implementation | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0
D659 | Completion of Build Segment II DW/BI | Implementation | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0
D660 | Payroll Parallel Testing Plan | Implementation | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 | 280000 | 0 | 0 | 0 | 0 | 0
D662 | Completion of Dress Rehearsal (Mock Conversion IV) | Implementation | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0
D663 | Completion of Interface Testing Segment I | Implementation | 2081700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081700 | 0 | 0 | 0 | 0 | 2081700 | 2081700 | 0 | 0 | 0 | 0 | 0
D664 | Development of the Hypercare Support Plan | Implementation | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 455000 | 455000 | 0 | 0 | 0 | 0 | 0
D665 | Updated Post-Implementation Support Plan | Implementation | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 455000 | 455000 | 0 | 0 | 0 | 0 | 0
D666 | Support of UAT Segment I | Implementation | 2236500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2236500 | 0 | 0 | 0 | 0 | 2236500 | 2236500 | 0 | 0 | 0 | 0 | 0
D668 | Completion of Build Segment III DW/BI | Implementation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 1350000 | 1350000 | 0 | 0 | 0 | 0 | 0
D696 | Completion of System Test Segment III | Implementation | 1378840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1378840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1378840 | 1378840 | 0 | 0 | 0 | 0 | 0
D698 | Completion of Inter/IntraUnit and Receipt Accrual Cost Collection Build | Implementation | 54867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 54867 | 0 | 0 | 0 | 0 | 54867 | 54867 | 0 | 0 | 0 | 0 | 0
D699 | Completion of AM Physical Inventory File Path Build | Implementation | 36167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 36167 | 0 | 0 | 0 | 0 | 36167 | 36167 | 0 | 0 | 0 | 0 | 0
D700 | Completion of Cash Reporting Solution Enhancement Build | Implementation | 39953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39953 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39953 | 39953 | 0 | 0 | 0 | 0 | 0
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 415692 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692 | 207846 | 207846 | 207846 | 0 | 207846 | 0
Prod Supp | AM Services | Prod Supp | 6849800 | 554500 | 554500 | 554500 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 0 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 572300 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 572300 | 0 | 0 | 0 | 0 | 6849800 | 3433800 | 3416000 | 3416000 | 0 | 3416000 | 0
Prod Supp | IM Services (includes month credit -$4,130 from A10) | Prod Supp | 1406700 | 109900 | 109900 | 109900 | 113800 | 113800 | 113800 | 113800 | 113800 | 113800 | 0 | 113800 | 113800 | 113800 | 113800 | 113800 | 113800 | 109670 | 113800 | 113800 | 4130 | 109670 | 0 | 0 | 118670 | 0 | 0 | 118670 | 0 | 0 | 118670 | 0 | 0 | 118670 | 0 | 0 | 118670 | 0 | 0 | 0 | 0 | 1381920 | 703020 | 674770 | 678900 | -4130 | 678900 | 0
Prod Supp | Oracle OCI Costs | Prod Supp | 749650 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187412 | 187412 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749650 | 374826 | 374824 | 374824 | 0 | 374824 | 0
Prod Supp | Support Tools Maintenance | Prod Supp | 46381 | 46381 | 46381 | 46381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46381 | 0 | 46381 | 46381 | 0 | 46381 | 0
Prod Supp | Support Tools Purchase | Prod Supp | 311780 | 203556 | 311780 | 311780 | 0 | 0 | 0 | 0 | 0 | 0 | 108224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311780 | 0 | 311780 | 311780 | 0 | 311780 | 0
Prod Supp | Solution Software Support | Prod Supp | 32790 | 32790 | 15371 | 15371 | 0 | 0 | 0 | 0 | 0 | 0 | -17419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15371 | 0 | 15371 | 15371 | 0 | 15371 | 0
| Implementation Total: |  |  | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450000 | 0 | 0 | 1200000 | 1200000 | 1200000 | 2000000 | 2000000 | 0 |  | 8450000 | 0 | 0 | 3500000 | 0 | 0 | 2039953 | 0 | 0 | 1630000 | 0 | 0 | 2378840 | 0 | 0 | 6669234 | 0 | 0 | 0 | 0 | 30118027 | 24668027 | 0 | 5450000 | -5450000 | 3450000 | 2000000
| Production Support Facilities Total: |  |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 |  | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692 | 207846 | 0 | 207846 | -207846 | 207846 | 0
| Production Support (No Facilities) Total: |  |  | 1134539 | 1225344 | 1225344 | 686100 | 686100 | 686100 | 686100 | 686100 | 686100 |  | 873512 | 873512 | 873512 | 686100 | 686100 | 686100 | 681970 | 686100 | 686100 |  | 869382 | 0 | 0 | 690970 | 0 | 0 | 690970 | 0 | 0 | 878384 | 0 | 0 | 690970 | 0 | 0 | 690970 | 0 | 0 | 0 | 0 | 9354902 | 4511646 | 0 | 4843256 | -4843256 | 4843256 | 0
Monthly Totals |  |  | 38580820 | 3419180 | 3509985 | 3509985 | 720741 | 720741 | 720741 | 720741 | 720741 | 720741 | 90805 | 4358153 | 908153 | 908153 | 1920741 | 1920741 | 1920741 | 2716611 | 2720741 | 720741 | -3445870 | 9354023 | 0 | 0 | 4225611 | 0 | 0 | 2765564 | 0 | 0 | 2543025 | 0 | 0 | 3104451 | 0 | 0 | 7394845 | 0 | 0 | 0 | 0 | 39888621 | 29387519 | 13946972 | 10501102 | 3445870 | 8501102 | 2000000
| Projected YTD |  |  | 3419180 |  |  | 4139921 |  |  | 4860662 |  |  | 4951467 | 9309620 |  |  | 11230361 |  |  | 13946972 |  |  | 10501102 | 23300995 |  |  | 27526606 |  |  | 30292170 |  |  | 32835195 |  |  | 35939646 |  |  | 43334491
| Incurred YTD |  |  |  | 3509985 |  |  | 4230726 |  |  | 4951467 |  |  |  | 5859620 |  |  | 7780361 |  |  | 10501102 |  |  |  | 10501102 |  |  | 10501102 |  |  | 10501102 |  |  | 10501102 |  |  | 10501102 |  |  | 10501102 |  | 10501102
| Paid YTD |  |  |  |  | 3509985 |  |  | 4230726 |  |  | 4951467 |  |  |  | 5859620 |  |  | 7780361 |  |  | 8501102 |  |  |  | 8501102 |  |  | 8501102 |  |  | 8501102 |  |  | 8501102 |  |  | 8501102 |  |  | 8501102 |  | 8501102

## Oracle Summary
Department of Financial Services
Florida PALM FY 2024 - 2025 Oracle Summary FYTD
| Quantity/Months | Quote |  |  | July 2024 |  |  |  | August 2024 |  |  |  | September 2024 |  |  |  | Q2 Baseline Adjustment | October 2024 |  |  |  | November 2024 |  |  |  | December 2024 |  |  |  | Q3 Baseline Adjustment | January 2025 |  |  |  | February 2025 |  |  |  | March 2025 |  |  |  | April 2025 |  |  |  | May 2025 |  |  |  | June 2025 |  |  |  | FY 2024-25 CF |  | Total
Program |  | Tech Support | Total Purchase/ Subscription | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | CF Incurred | CF Paid | Total Projected | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support |  | 1518401.278 |  | 1518401.278 | 0 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 |  | 368152.757 | 0 | #REF! | 0 | 11447.5625 | 18005.03 | #REF! | 1170.4 | 0 | 0 | #REF! | 16834.63 | -361595.2895 | 669546.3917 | 0 | #REF! | 0 | 18341.7437 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 328350.09 | 0 | #REF! | 0 | 18341.7437 | 0 | #REF! | 0 | 340968.0525 | 0 | #REF! | 0 | 0 | 0 | 1393553.0517 | 488490.5105 | 55330.34 | 35727.52
Assignment |  | 1518401.278 | 0 | 1518401.278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 368152.757 | 0 | 0 | 0 | 11447.5625 | 18005.03 | 0 | 1170.4 | 0 | 0 | 0 | 16834.63 |  | 669546.3917 | 0 | 0 | 0 | 18341.7437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328350.09 | 0 | 0 | 0 | 18341.7437 | 0 | 0 | 0 | 340968.0525 | 0 | 0 | 0 | 0 | 0 | 1393553.0517 | 379600.3195 | 18005.03 | 18005.03
Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 2 | 8525.418 | 0 | 8525.418 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 2131.3545 | 0 |  | 0 | 0 | 1170.4 |  | 1170.4 | 0 | 0 |  | 0 | -960.9545 | 1734.645 | 0 |  | 0 | 1170.4 | 0 |  | 0 | 0 | 0 |  | 0 | 867.3225 | 0 |  | 0 | 1170.4 | 0 |  | 0 | 2037.7225 | 0 |  | 0 | 0 | 0 | 8150.89 | 2131.3545 | 1170.4 | 1170.4
Oracle Business Intelligence (Analytics) Server Administrator | 4 | 1479.59 | 0 | 1479.59 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -369.8975 | 739.795 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 | 1479.59 | 369.8975 | 0 | 0
Oracle Business Intelligence Management Pack | 4 | 2933.77 | 0 | 2933.77 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -733.4425 | 1466.885 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 | 2933.77 | 733.4425 | 0 | 0
Oracle Business Intelligence Suite Foundation Edition | 4 | 76549.07 | 0 | 76549.07 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -19137.2675 | 38274.535 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 | 76549.07 | 19137.2675 | 0 | 0
Oracle Data Integrator Enterprise Edition | 20 | 38274.54 | 0 | 38274.54 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -9568.635 | 19137.27 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 | 38274.54 | 9568.635 | 0 | 0
Oracle Data Visualization | 4 | 25517.06 | 0 | 25517.06 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -6379.265 | 12758.53 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 | 25517.06 | 6379.265 | 0 | 0
Oracle Financial Analytics Fusion Edition (DW/BI) | 100 | 14800.11 | 0 | 14800.11 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -3700.0275 | 7400.055 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 | 14800.11 | 3700.0275 | 0 | 0
Oracle Managed File Transfer | 12 | 21373.31 | 0 | 21373.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5343.3275 | 10686.655 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 | 21373.31 | 5343.3275 | 0 | 0
Oracle Management Pack for Oracle Data Integrator | 16 | 7042.33 | 0 | 7042.33 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -1760.5825 | 3521.165 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 | 7042.33 | 1760.5825 | 0 | 0
Oracle SOA Management Pack Enterprise Edition | 14 | 20670.71 | 0 | 20670.71 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -5167.6775 | 10335.355 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 | 20670.71 | 5167.6775 | 0 | 0
Oracle SOA Suite for Oracle Middleware | 14 | 47542.18 | 0 | 47542.18 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -11885.545 | 23771.09 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 | 47542.18 | 11885.545 | 0 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 26 | 18471 | 0 | 18471 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -4617.75 | 9235.5 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 | 18471 | 4617.75 | 0 | 0
Oracle WebLogic Suite | 26 | 69266.8 | 0 | 69266.8 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -17316.7 | 34633.4 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 | 69266.8 | 17316.7 | 0 | 0
PeopleSoft Enterprise Contracts | 92083 | 55673.81 | 0 | 55673.81 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13214.6675 | 0 |  | 0 | 703.785 | 1034.99 |  | 0 | 0 | 0 |  | 1034.99 | -12883.4625 | 26429.335 | 0 |  | 0 | 1055.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 13214.6675 | 0 |  | 0 | 1055.6775 | 0 |  | 0 | 13918.4525 | 0 |  | 0 | 0 | 0 | 56708.8 | 13918.4525 | 1034.99 | 1034.99
PeopleSoft Enterprise eSettlements | 92083 | 36536.19 | 0 | 36536.19 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 8672.185 | 0 |  | 0 | 461.8625 | 679.2 |  | 0 | 0 | 0 |  | 679.2 | -8454.8475 | 17344.37 | 0 |  | 0 | 692.7938 | 0 |  | 0 | 0 | 0 |  | 0 | 8672.185 | 0 |  | 0 | 692.7938 | 0 |  | 0 | 9134.0475 | 0 |  | 0 | 0 | 0 | 37215.39 | 9134.0475 | 679.2 | 679.2
PeopleSoft Enterprise Expenses | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 1374.58 |  | 0 | 0 | 0 |  | 1374.58 | -17110.6375 | 35100.995 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 75315.45 | 18485.2175 | 1374.58 | 1374.58
PeopleSoft Enterprise Financials | 92083 | 398410.84 | 0 | 398410.84 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 94566.2225 | 0 |  | 0 | 5036.4875 | 7406.6 |  | 0 | 0 | 0 |  | 7406.6 | -92196.11 | 189132.445 | 0 |  | 0 | 7554.7312 | 0 |  | 0 | 0 | 0 |  | 0 | 94566.2225 | 0 |  | 0 | 7554.7312 | 0 |  | 0 | 99602.71 | 0 |  | 0 | 0 | 0 | 405817.44 | 99602.71 | 7406.6 | 7406.6
PeopleSoft Enterprise Grants | 92083 | 52193.31 | 0 | 52193.31 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 12388.525 | 0 |  | 0 | 659.8025 | 970.29 |  | 0 | 0 | 0 |  | 970.29 | -12078.0375 | 24777.05 | 0 |  | 0 | 989.7038 | 0 |  | 0 | 0 | 0 |  | 0 | 12388.525 | 0 |  | 0 | 989.7038 | 0 |  | 0 | 13048.3275 | 0 |  | 0 | 0 | 0 | 53163.6 | 13048.3275 | 970.29 | 970.29
PeopleSoft Enterprise Human Resources | 114800 | 47938.36 | 0 | 47938.36 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -11984.59 | 23969.18 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 | 47938.36 | 11984.59 | 0 | 0
PeopleSoft Enterprise Payroll | 114800 | 58302.96 | 0 | 58302.96 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -14575.74 | 29151.48 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 | 58302.96 | 14575.74 | 0 | 0
PeopleSoft Enterprise Project Costing | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 1374.58 |  | 0 | 0 | 0 |  | 1374.58 | -17110.6375 | 35100.995 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 75315.45 | 18485.2175 | 1374.58 | 1374.58
PeopleSoft Enterprise Purchasing | 92083 | 81770.5 | 0 | 81770.5 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 19408.935 | 0 |  | 0 | 1033.69 | 1520.14 |  | 0 | 0 | 0 |  | 1520.14 | -18922.485 | 38817.87 | 0 |  | 0 | 1550.535 | 0 |  | 0 | 0 | 0 |  | 0 | 19408.935 | 0 |  | 0 | 1550.535 | 0 |  | 0 | 20442.625 | 0 |  | 0 | 0 | 0 | 83290.64 | 20442.625 | 1520.14 | 1520.14
PeopleSoft Enterprise Supplier Contract Management | 92083 | 73940.87 | 0 | 73940.87 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 17550.4975 | 0 |  | 0 | 934.72 | 1374.58 |  | 0 | 0 | 0 |  | 1374.58 | -17110.6375 | 35100.995 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 0 | 0 |  | 0 | 17550.4975 | 0 |  | 0 | 1402.08 | 0 |  | 0 | 18485.2175 | 0 |  | 0 | 0 | 0 | 75315.45 | 18485.2175 | 1374.58 | 1374.58
PeopleSoft Enterprise Treasury | 92083 | 59152.27 | 0 | 59152.27 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14040.2925 | 0 |  | 0 | 747.775 | 1099.67 |  | 0 | 0 | 0 |  | 1099.67 | -13688.3975 | 28080.585 | 0 |  | 0 | 1121.6625 | 0 |  | 0 | 0 | 0 |  | 0 | 14040.2925 | 0 |  | 0 | 1121.6625 | 0 |  | 0 | 14788.0675 | 0 |  | 0 | 0 | 0 | 60251.94 | 14788.0675 | 1099.67 | 1099.67
PeopleSoft Enterprise Time and Labor | 114800 | 154154.54 | 0 | 154154.54 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 38538.635 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -38538.635 | 12846.2117 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 12846.2117 | 38538.635 | 0 | 0
Analytics |  | 54273.384 |  | 54273.384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.346 | 0 | 0 | 0 | 0 | 13302.3 | 0 | 0 | -266.046 | 0 | 0 | 0 | 0 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13568.35 | 0 | 0 | 0 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 54273.396 | 13568.346 | 13302.3 | 0
HR Analytics (DW/BI) | 100 | 45227.82 | 0 | 45227.82 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 11306.955 | 0 |  | 0 | 0 | 11085.25 |  | 0 | -221.705 | 0 | 0 |  | 0 | 11307 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11307 | 0 |  | 0 | 11307 | 0 |  | 0 | 0 | 0 | 45006.25 | 11306.955 | 11085.25 | 0
Project Analytics (DW/BI) | 20 | 9045.564 | 0 | 9045.564 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 2261.391 | 0 |  | 0 | 0 | 2217.05 |  | 0 | -44.341 | 0 | 0 |  | 0 | 2261.35 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2261.35 | 0 |  | 0 | 2261.35 | 0 |  | 0 | 0 | 0 | 9001.1 | 2261.391 | 2217.05 | 0
OCI |  | 0 |  | 334079.18 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 11802.05 | 0 | 0 | -71717.745 | 27839.9317 | 0 | 0 | 11802.05 | 27839.9317 | 5920.44 | 0 | 5920.44 | 27839.9317 | 6300.52 | 0 | 0 | -71298.835 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 27839.9317 | 0 | 0 | 0 | 0 | 0 | 334079.18 | 95321.845 | 24023.01 | 17722.49
OAC (DW/BI) - DEV: $53,218.69 - Test : $63,779.29 - DR : $93,780.73 - Production : $123,300.47 | 4 | 0 | 334079.18 | 334079.18 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 11802.05 |  | 0 | -71717.745 | 27839.9317 | 0 |  | 11802.05 | 27839.9317 | 5920.44 |  | 5920.44 | 27839.9317 | 6300.52 |  | 0 | -71298.835 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 27839.9317 | 0 |  | 0 | 0 | 0 | 191062.6 | 95321.845 | 24023.01 | 17722.49
New License Purchase and Tech Support |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 1572674.662 |  | 1906753.842 | 27839.9317 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 27839.9317 | 11802.05 | #REF! | 0 | -71717.745 | 395992.6887 | 0 | #REF! | 11802.05 | 52855.8402 | 23925.47 | #REF! | 7090.84 | 27839.9317 | 19602.82 | #REF! | 16834.63 | -433160.1705 | 697386.3233 | 0 | #REF! | 0 | 59750.0254 | 0 | #REF! | 0 | 27839.9317 | 0 | #REF! | 0 | 356190.0217 | 0 | #REF! | 0 | 59750.0254 | 0 | #REF! | 0 | 382376.3342 | 0 | #REF! | 0 | 0 | 0 | 1781905.6277 | 488490.5105 | 55330.34 | 53450.01
Projected FYTD |  |  |  |  | 27839.9317 |  |  |  | 55679.8633 |  |  |  | 83519.795 |  |  |  |  | 407794.7387 |  |  |  | 460650.5788 |  |  |  | 488490.5105 |  |  |  |  | 1185876.8338 |  |  |  | 1245626.8592 |  |  |  | 1273466.7909 |  |  |  | 1629656.8126 |  |  |  | 1689406.838 |  |  |  | 2071783.1722
Incurred FYTD | [5 empty] | 0 |  |  |  | 0 |  |  |  | 11802.05 |  |  | 11802.05 |  | 11802.05 |  |  |  | 35727.52 |  |  |  | 55330.34 |  |  | 102859.91 |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34 |  |  |  | 55330.34
Paid FYTD | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 11802.05 |  |  |  | 18892.89 |  |  |  | 35727.52 | 55330.34 |  |  |  | 35727.52 |  |  |  | 35727.52 |  |  |  | 35727.52 |  |  |  | 35727.52 |  |  |  | 35727.52 |  |  |  | 35727.52