## Monthly Summary
Department of Financial Services
Florida PALM FY 2025 - 2026 Spend Plan Summary FYTD
As of August 31, 2025
Annual
| TRUE | TRUE | TRUE | TRUE | TRUE |  | ERROR | July 2025 |  |  |  | August 2025 |  |  |  | September 2025 |  |  | October 2025 |  |  | November 2025 |  |  | December 2025 |  |  | January 2026 |  |  | February 2026 |  |  | March 2026 |  |  | April 2026 |  |  | May 2026 |  |  | June 2026 |  |  | CF 2025-26 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 10130387 | 45930662 | 56061049 | 14015262 | 42045787 | 50967055.7945 | 11552033.4 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| FY 24-25 Revert & Appropriated | FY 25-26 GAA Appropriated | FY 25-26 Total Appropriation | Released | Unreleased | Projected | Release Remaining
FLAIR System Replacement (100781) | 10130387 | 45930662 | 56061049 | 14015262 | 42045787 | 50967055.7945 | 11552033.4 | 4631851.0633 | 2445591.29 |  | 1335444.96 | 6967995.1821 | 3224806.19 |  | 1127783.64 | 2639834.5033 | 0 | 0 | 2969906.106 | 0 | 0 | 7158944.1833 | 0 | 0 | 2170347.6233 | 0 | 0 | 3410392.716 | 0 | 0 | 3972664.3933 | 0 | 0 | 1906029.4233 | 0 | 0 | 4562292.136 | 0 | 0 | 7376081.9533 | 0 | 0 | 3200716.511 | 0 | 0 | #REF! | #REF! | 11599846.2454 | 5670397.48 | 2463228.6 | 45296658.3145 | 88.87%
SSI Implementation Services (FP004) | [5 empty] | 27831023 |  | 2000000 | 0 |  | 0 | 5338840 | 2000000 | 2 | 0 | 994983 | 0 | 0 | 0 | 0 | 0 | 5818200 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 1976500 | 0 | 0 | 0 | 0 | 0 | 2681700 | 0 | 0 | 6020800 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 7338840 | 2000000 | 0 | 25831023 | 92.81%
Facilities and Maintenance (FP004) | [5 empty] | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 69282 | 69282 | 69282 | 346410 | 83.33%
Production Support (FP004) | [5 empty] | 9948750 |  | 1534630 | 1521776 |  | 830806 | 713885 | 713885 |  | 690970 | 713885 | 0 | 0 | 907013 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 907013 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 907014 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 0 | 0 | 2248515 | 2235661 | 1521776 | 7713089 | 77.53%
Additional Facilities | [5 empty] | 241100.58 |  | 19961.81 | 19961.81 |  | 0 | 19961.81 | 19961.81 |  | 39923.62 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 20143.61 | 0 | 0 | 20143.61 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 0 | 0 | 39923.62 | 39923.62 | 39923.62 | 201176.96 | 83.44%
Production Support Administration | [5 empty] | 824518.12 |  | 41971.78 | 1177 | 2 | 1177 | 7971.78 | 5355.02 |  | 5355.02 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 34971.78 | 0 | 0 | 675828.54 | 0 | 0 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 0 | 0 | 49943.56 | 6532.02 | 6532.02 | 817986.1 | 99.21%
Oracle Software and Maintenance (FP005) | [5 empty] | 2227299.5945 |  | 44165.81 | 17097.05 | 2 | 17097.05 | 394048.7587 | 24821.06 | 2 | 1217.22 | 33788.58 | 0 | 0 | 368705.6727 | 0 | 0 | 72151.86 | 0 | 0 | 33788.58 | 0 | 0 | 368705.6727 | 0 | 0 | 58583.51 | 0 | 0 | 33788.58 | 0 | 0 | 368705.6727 | 0 | 0 | 64807.85 | 0 | 0 | 386059.0477 | 0 | 0 | 0 | 0 | 438214.5687 | 41918.11 | 18314.27 | 2185381.4845 | 98.12%
Project Administration | [5 empty] | 293888.04 |  | 30988.5233 | 19025.51 | 2 | 19025.51 | 30724.2733 | 18534.26 | 2 | 18534.26 | 80067.4133 | 0 | 0 | 37297.5633 | 0 | 0 | 11907.5333 | 0 | 0 | 11907.5333 | 0 | 0 | 16207.5333 | 0 | 0 | 12857.5333 | 0 | 0 | 22407.5333 | 0 | 0 | 15707.5333 | 0 | 0 | 11907.5333 | 0 | 0 | 11907.5333 | 0 | 0 | 0 | 0 | 61712.7967 | 37559.77 | 37559.77 | 256328.27 | 87.22%
Florida PALM-UAT | [5 empty] | 2750000 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 275000 | 0 | 0 | 1100000 | 0 | 0 | 0 | 0 | 0 | 825000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | 0 | 0 | 0 | 2750000 | 100%
Support Services | [5 empty] | 4411977.46 |  | 585621.14 | 503522.92 | 5,1 | 252332.4 | 288650.56 | 272608.04 |  | 223318.52 | 333631.92 | 0 | 0 | 375635.28 | 0 | 0 | 333625.2 | 0 | 0 | 361631.92 | 0 | 0 | 364331.92 | 0 | 0 | 333625.2 | 0 | 0 | 361631.92 | 0 | 0 | 361631.92 | 0 | 0 | 347628.56 | 0 | 0 | 364331.92 | 0 | 0 | 0 | 0 | 874271.7 | 776130.96 | 475650.92 | 3635846.5 | 82.41%
QA Support Services | [5 empty] | 2022807 |  | 339871 | 328390 |  | 180366 | 139272 | 135000 |  | 113824 | 145904 | 0 | 0 | 118680 | 0 | 0 | 149600 | 0 | 0 | 164560 | 0 | 0 | 164560 | 0 | 0 | 149600 | 0 | 0 | 164560 | 0 | 0 | 164560 | 0 | 0 | 157080 | 0 | 0 | 164560 | 0 | 0 | #REF! | #REF! | 479143 | 463390 | 294190 | 1559417 | 77.09%
Florida PALM Unprojected Project Reserves | [5 empty] | 0
Contingency (100819) | 3000000 |  | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Salaries & Benefits (010000) IRTF |  | 10995719 | 10995719 | 10995719 | 0 | 10995719 | 9335768.79 | 916309.9167 | 849765.77 |  | 849765.77 | 916309.9167 | 810184.44 |  | 810184.44 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 0 | 0 | 1832619.8333 | 1659950.21 | 1659950.21 | 9335768.79 | 84.9%
Salaries & Benefits (010000) GRF |  | 1889784 | 1889784 | 472446 | 1417338 | 1889784 | 406419.99 | 157482 | 33013 |  | 33013 | 157482 | 33013.01 |  | 33013.01 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 |  |  | 314964 | 66026.01 | 66026.01 | 1823757.99 | 96.51%
Data Processing Services (210000) |  | 0 | 0 | 0 | 0 | 112138 | 0 | 112138 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112138 | 0 | 0 | 112138 | 100%
Risk Management Insurance (103241) |  | 14572 | 14572 | 14572 | 0 | 14572 | 14572 | 13957 | 0 |  | 0 | 0 | 0 |  | 0 | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13957 | 0 | 0 | 14572 | 100%
DMS HR Transfer (107040) IRTF |  | 24000 | 24000 | 24000 | 0 | 24000 | 24000 | 6000 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 24000 | 100%
DMS HR Transfer (107040) GRF |  | 3520 | 3520 | 3520 |  | 3520 | 3520 | 880 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 880 | 0 | 0 | 3520 | 100%
Totals | 13130387 | 58858257 | 71988644 | 25525519 | 46463125 | 64006788.7945 | 21336314.18 | 5838617.98 | 3328370.06 |  | 2218223.73 | 8041787.0987 | 4068003.64 |  | 1970981.09 | 3714241.42 | 0 | 0 | 4050578.0227 | 0 | 0 | 8232736.1 | 0 | 0 | 3244139.54 | 0 | 0 | 4491064.6327 | 0 | 0 | 5046456.31 | 0 | 0 | 2979821.34 | 0 | 0 | 5642964.0527 | 0 | 0 | 8449873.87 | 0 | 0 | 4274508.4277 | 0 | 0 | #REF! | #REF! | 13880405.0787 | 7396373.7 | 4189204.82 | 56610415.0945 | 100%
Running Totals | [7 empty] | 5838617.98 | 3328370.06 |  | 2218223.73 | 13880405.0787 | 7396373.7 |  | 4189204.82 | 17594646.4988 | 7396373.7 | 4189204.82 | 21645224.5214 | 7396373.7 | 4189204.82 | 29877960.6214 | 7396373.7 | 4189204.82 | 33122100.1614 | 7396373.7 | 4189204.82 | 37613164.7941 | 7396373.7 | 4189204.82 | 42659621.1041 | 7396373.7 | 4189204.82 | 45639442.4441 | 7396373.7 | 4189204.82 | 51282406.4968 | 7396373.7 | 4189204.82 | 59732280.3668 | 7396373.7 | 4189204.82 | 64006788.7945 | 7396373.7 | 4189204.82 |  | #REF! |  |  | Total Incurred/Total Projected FYTD |  | 53.29%
Monthly Total Incurred/Total Projected | [7 empty] | 57.01% |  |  |  | 50.59% |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% | [6 empty] | Total Paid/Total Projected FYTD |  | 30.18%
Monthly Total Incurred/Total Projected (Variance) | [7 empty] | -42.99% |  |  |  | -49.41% |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [7 empty] | 57.01% |  |  |  | 53.29% |  |  |  | 42.04% |  |  | 34.17% |  |  | 24.76% |  |  | 22.33% |  |  | 19.66% |  |  | 17.34% |  |  | 16.21% |  |  | 14.42% |  |  | 12.38% |  |  | 11.56% | [6 empty] | Total Release/Total Appropriation |  | 194.4%
FYTD Total Incurred/Total Projected (Variance) | [7 empty] | -42.99% |  |  |  | -46.71% |  |  |  | -57.96% |  |  | -65.83% |  |  | -75.24% |  |  | -77.67% |  |  | -80.34% |  |  | -82.66% |  |  | -83.79% |  |  | -85.58% |  |  | -87.62% |  |  | -88.44%
[50 empty] | Total Paid/Total Release |  | 16.41%
Reconciles to ALRR | No |  | Yes | No | No | [5 empty] | No |  |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | #REF! |  |  | No

## Footnotes
Department of Financial Services
FY 2025 - 2026 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Contractor hours projected and incurred amounts were greater than anticipated due to June 2025 hours not being projected to be incurred in July 2025.
6

## SSI Detail
|  |  |  | July 2025 |  |  | August 2025 |  |  | September 2025 |  |  | October 2025 |  |  | November 2025 |  |  | December 2025 |  |  | January 2026 |  |  | February 2026 |  |  | March 2026 |  |  | April 2026 |  |  | May 2026 |  |  | June 2026 |  |  | CF 2025-26
|  | Description | Total Deliverable Cost FY 25-26 | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Projection
Department of Financial Services
Florida PALM FY 2025 - 2026 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
657 | Completion of Mock Conversion III (UAT) | Implementation | 2000000 |  |  |  | 2000000 | 2000000 | [31 empty] | 0 | 0 | 2000000
658 | Develop the Deployment and Contingency Plan | Implementation | 2000000 |  |  |  | 2000000 | [32 empty] | 0 | 0 | 2000000
661 | Completion of System Test DW/BI | Implementation | 1338840 |  |  |  | 1338840 | [32 empty] | 0 | 0 | 1338840
662 | Completion of Mock Conversion IV | Implementation | 1500000 | [12 empty] | 1500000 | [23 empty] | 0 | 0 | 1500000
663 | Completion of Interface Testing Segment I | Implementation | 2081700 | [12 empty] | 2081700 | [23 empty] | 0 | 0 | 2081700
666 | Support of UAT Segment I | Implementation | 2236500 | [12 empty] | 2236500 | [23 empty] | 0 | 0 | 2236500
667 | Completion of Mock Go-Lives (Dry Run #1) | Implementation | 1500000 | [18 empty] | 1500000 | [17 empty] | 0 | 0 | 1500000
669 | Support of UAT Segment II | Implementation | 1976500 | [21 empty] | 1976500 | [14 empty] | 0 | 0 | 1976500
670 | Completion of Payroll Parallel Testing | Implementation | 600000 | [27 empty] | 600000 | [8 empty] | 0 | 0 | 600000
671 | Completion of Interface Testing Segment II | Implementation | 2081700 | [27 empty] | 2081700 | [8 empty] | 0 | 0 | 2081700
672 | Support of UAT Segment III | Implementation | 1976500 | [30 empty] | 1976500 | [5 empty] | 0 | 0 | 1976500
673 | Completion of Mock Go-Lives (Dry Run #2) | Implementation | 1500000 | [30 empty] | 1500000 | [5 empty] | 0 | 0 | 1500000
674 | Completion of Penetration Testing | Implementation | 513400 | [30 empty] | 513400 | [5 empty] | 0 | 0 | 513400
675 | Completion of Performance Testing | Implementation | 1480900 | [30 empty] | 1480900 | [5 empty] | 0 | 0 | 1480900
676 | Completion of Disaster Recovery Testing | Implementation | 550000 | [30 empty] | 550000 | [5 empty] | 0 | 0 | 550000
677 | Completion of Mock Go-Lives (Dry Run #3) | Implementation | 1500000 | [15 empty] | 0 | [17 empty] | 1500000 |  |  | 0 | 0 | 1500000
696 | Completion of System Test Segment III | Implementation | 2000000 | 2000000 | [35 empty] | 0 | 0 | 2000000
697 | Completion of Employee Self-Service Build | Implementation | 994983 | [6 empty] | 994983 | [29 empty] | 0 | 0 | 994983
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 415692 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 0 | 0 | 415692
Prod Supp | AM Services | Prod Supp | 7071100 | 572300 | 572300 |  | 590800 | 590800 | 572300 | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 0 | 0 | 7071100
Prod Supp | IM Services (Reduced Monthly by $3,715 SNow Credit) | Prod Supp | 1446020 | 119085 | 118670 |  | 123085 | 123085 | 118670 | 123085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 0 | 0 | 1446020
Prod Supp | Oracle OCI Costs | Prod Supp | 784513 | 196128 | 196128 | 196128 | 0 |  |  | 0 |  |  | 196128 |  |  | 0 |  |  | 0 |  |  | 196128 |  |  | 0 |  |  | 0 |  |  | 196129 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 784513
Prod Supp | Support Tools Maintenance | Prod Supp | 47772 | 47772 | 47772 | 47772 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 47772
Prod Supp | Support Tools Purchase | Prod Supp | 571800 | 571800 | 571800 | 571800 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 571800
Prod Supp | Solution Software Support (Reduced by $4,980 for A7 credit) | Prod Supp | 27545 | 27545 | 15106 | 15106 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 27545
| Implementation Total: |  |  | 2000000 | 0 | 0 | 5338840 | 2000000 | 0 | 994983 | 0 | 0 | 0 | 0 | 0 | 5818200 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 1976500 | 0 | 0 | 0 | 0 | 0 | 2681700 | 0 | 0 | 6020800 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 27831023
| Production Support Facilities Total: |  |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692
| Production Support (No Facilities) Total: |  |  | 1534630 | 1521776 | 830806 | 713885 | 713885 | 690970 | 713885 | 0 | 0 | 907013 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 907013 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 907014 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 0 | 0 | 9948750
Monthly Totals |  |  | 38195465 | 3569271 | 1556417 | 865447 | 6087366 | 2748526 | 725611 | 1743509 | 0 | 0 | 941654 | 0 | 0 | 6563726 | 0 | 0 | 745526 | 0 | 0 | 2441654 | 0 | 0 | 2722026 | 0 | 0 | 745526 | 0 | 0 | 3623355 | 0 | 0 | 6766326 | 0 | 0 | 2245526 | 0 | 0 | 0 | 0 | 38195465
| Projected YTD |  |  | 3569271 |  |  | 9656637 |  |  | 11400146 |  |  | 12341800 |  |  | 18905526 |  |  | 19651052 |  |  | 22092706 |  |  | 24814732 |  |  | 25560258 |  |  | 29183613 |  |  | 35949939 |  |  | 38195465
| Incurred YTD |  |  |  | 1556417 |  |  | 4304943 |  |  | 4304943 |  |  | 4304943 |  |  | 4304943 |  |  | 4304943 |  |  | 4304943 |  |  | 4304943 |  |  | 4304943 |  |  | 4304943 |  |  | 4304943 |  |  | 4304943 |  | 4304943
| Paid YTD |  |  |  |  | 865447 |  |  | 1591058 |  |  | 1591058 |  |  | 1591058 |  |  | 1591058 |  |  | 1591058 |  |  | 1591058 |  |  | 1591058 |  |  | 1591058 |  |  | 1591058 |  |  | 1591058 |  |  | 1591058 |  | 1591058

## Oracle Summary
Department of Financial Services
Florida PALM FY 2025 - 2026 Oracle Summary FYTD
| Quantity/Months | Quote |  |  | July 2025 |  |  |  | August 2025 |  |  |  | September 2025 |  |  |  | October 2025 |  |  |  | November 2025 |  |  |  | December 2025 |  |  |  | January 2026 |  |  |  | February 2026 |  |  |  | March 2026 |  |  |  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026 |  |  |  | FY 2025-26 CF |  | Total
Program |  | Tech Support | Total Purchase/ Subscription | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | CF Incurred | CF Paid | Total Projected | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support |  | 1413950.7308 | 0 | 1413950.7308 | 0 | 0 | #REF! | 0 | 346738.6487 | 1217.22 | #REF! | 1217.22 | 0 | 0 | #REF! | 0 | 334917.0927 | 0 | #REF! | 0 | 18570.59 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 334917.0927 | 0 | #REF! | 0 | 18570.59 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 334917.0927 | 0 | #REF! | 0 | 18570.59 | 0 | #REF! | 0 | 352270.4677 | 0 | #REF! | 0 | 0 | 0 | 2227299.5945 | 438214.5687 | 41918.11 | 18314.27
Assignment |  | 1413950.7308 | 0 | 1413950.7308 | 0 | 0 | 0 | 0 | 346738.6487 | 1217.22 | 0 | 1217.22 | 0 | 0 | 0 | 0 | 334917.0927 | 0 | 0 | 0 | 18570.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334917.0927 | 0 | 0 | 0 | 18570.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334917.0927 | 0 | 0 | 0 | 18570.59 | 0 | 0 | 0 | 352270.4677 | 0 | 0 | 0 | 0 | 0 | 1759472.1645 | 346738.6487 | 1217.22 | 1217.22
Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 2 | 8407.53 | 0 | 8407.53 | 0 | 0 |  | 0 | 2084.5375 | 1217.22 |  | 1217.22 | 0 | 0 |  | 0 | 884.6675 | 0 |  | 0 | 1217.215 | 0 |  | 0 | 0 | 0 |  | 0 | 884.6675 | 0 |  | 0 | 1217.215 | 0 |  | 0 | 0 | 0 |  | 0 | 884.6675 | 0 |  | 0 | 1217.215 | 0 |  | 0 | 884.6675 | 0 |  | 0 |  |  | 9274.8525 | 2084.5375 | 1217.22 | 1217.22
Oracle Business Intelligence (Analytics) Server Administrator | 4 | 1509.1834 | 0 | 1509.1834 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | 377.2959 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 377.2959 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 377.2959 | 0 |  | 0 | 0 | 0 |  | 0 | 377.2959 | 0 |  | 0 |  |  | 1879.0809 | 369.8975 | 0 | 0
Oracle Business Intelligence Management Pack | 4 | 2992.44 | 0 | 2992.44 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | 748.11 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 748.11 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 748.11 | 0 |  | 0 | 0 | 0 |  | 0 | 748.11 | 0 |  | 0 |  |  | 3725.8825 | 733.4425 | 0 | 0
Oracle Business Intelligence Suite Foundation Edition | 4 | 78080.06 | 0 | 78080.06 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | 19520.015 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19520.015 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19520.015 | 0 |  | 0 | 0 | 0 |  | 0 | 19520.015 | 0 |  | 0 |  |  | 97217.3275 | 19137.2675 | 0 | 0
Oracle Data Integrator Enterprise Edition | 20 | 39040.032 | 0 | 39040.032 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | 9760.008 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9760.008 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9760.008 | 0 |  | 0 | 0 | 0 |  | 0 | 9760.008 | 0 |  | 0 |  |  | 48608.667 | 9568.635 | 0 | 0
Oracle Data Visualization | 4 | 26027.3955 | 0 | 26027.3955 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | 6506.8489 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6506.8489 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6506.8489 | 0 |  | 0 | 0 | 0 |  | 0 | 6506.8489 | 0 |  | 0 |  |  | 32406.6605 | 6379.265 | 0 | 0
Oracle Financial Analytics Fusion Edition (DW/BI) | 100 | 15096.1104 | 0 | 15096.1104 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | 3774.0276 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3774.0276 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3774.0276 | 0 |  | 0 | 0 | 0 |  | 0 | 3774.0276 | 0 |  | 0 |  |  | 18796.1379 | 3700.0275 | 0 | 0
Oracle Managed File Transfer | 12 | 21800.7813 | 0 | 21800.7813 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | 5450.1953 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5450.1953 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5450.1953 | 0 |  | 0 | 0 | 0 |  | 0 | 5450.1953 | 0 |  | 0 |  |  | 27144.1088 | 5343.3275 | 0 | 0
Oracle Management Pack for Oracle Data Integrator | 16 | 7183.1817 | 0 | 7183.1817 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | 1795.7954 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1795.7954 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1795.7954 | 0 |  | 0 | 0 | 0 |  | 0 | 1795.7954 | 0 |  | 0 |  |  | 8943.7642 | 1760.5825 | 0 | 0
Oracle SOA Management Pack Enterprise Edition | 14 | 21084.1199 | 0 | 21084.1199 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | 5271.03 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5271.03 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5271.03 | 0 |  | 0 | 0 | 0 |  | 0 | 5271.03 | 0 |  | 0 |  |  | 26251.7974 | 5167.6775 | 0 | 0
Oracle SOA Suite for Oracle Middleware | 14 | 48493.0302 | 0 | 48493.0302 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | 12123.2575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12123.2575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12123.2575 | 0 |  | 0 | 0 | 0 |  | 0 | 12123.2575 | 0 |  | 0 |  |  | 60378.5752 | 11885.545 | 0 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 26 | 18840.42 | 0 | 18840.42 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | 4710.105 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4710.105 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4710.105 | 0 |  | 0 | 0 | 0 |  | 0 | 4710.105 | 0 |  | 0 |  |  | 23458.17 | 4617.75 | 0 | 0
Oracle WebLogic Suite | 26 | 70652.1264 | 0 | 70652.1264 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | 17663.0316 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17663.0316 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17663.0316 | 0 |  | 0 | 0 | 0 |  | 0 | 17663.0316 | 0 |  | 0 |  |  | 87968.8264 | 17316.7 | 0 | 0
PeopleSoft Enterprise Contracts | 102084 | 58183.35 | 0 | 58183.35 | 0 | 0 |  | 0 | 14270.345 | 0 |  | 0 | 0 | 0 |  | 0 | 13478.9675 | 0 |  | 0 | 1066.87 | 0 |  | 0 | 0 | 0 |  | 0 | 13478.9675 | 0 |  | 0 | 1066.87 | 0 |  | 0 | 0 | 0 |  | 0 | 13478.9675 | 0 |  | 0 | 1066.87 | 0 |  | 0 | 14545.8375 | 0 |  | 0 |  |  | 72453.695 | 14270.345 | 0 | 0
PeopleSoft Enterprise eSettlements | 102084 | 38183.04 | 0 | 38183.04 | 0 | 0 |  | 0 | 9364.9788 | 0 |  | 0 | 0 | 0 |  | 0 | 8845.6225 | 0 |  | 0 | 700.1375 | 0 |  | 0 | 0 | 0 |  | 0 | 8845.6225 | 0 |  | 0 | 700.1375 | 0 |  | 0 | 0 | 0 |  | 0 | 8845.6225 | 0 |  | 0 | 700.1375 | 0 |  | 0 | 9545.76 | 0 |  | 0 |  |  | 47548.0188 | 9364.9788 | 0 | 0
PeopleSoft Enterprise Expenses | 102084 | 77273.8 | 0 | 77273.8 | 0 | 0 |  | 0 | 18952.5775 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 19318.45 | 0 |  | 0 |  |  | 96226.3775 | 18952.5775 | 0 | 0
PeopleSoft Enterprise Financials | 102084 | 416369.45 | 0 | 416369.45 | 0 | 0 |  | 0 | 102120.9538 | 0 |  | 0 | 0 | 0 |  | 0 | 96457.545 | 0 |  | 0 | 7634.8175 | 0 |  | 0 | 0 | 0 |  | 0 | 96457.545 | 0 |  | 0 | 7634.8175 | 0 |  | 0 | 0 | 0 |  | 0 | 96457.545 | 0 |  | 0 | 7634.8175 | 0 |  | 0 | 104092.3625 | 0 |  | 0 |  |  | 518490.4038 | 102120.9538 | 0 | 0
PeopleSoft Enterprise Grants | 102084 | 54545.96 | 0 | 54545.96 | 0 | 0 |  | 0 | 13378.2288 | 0 |  | 0 | 0 | 0 |  | 0 | 12636.2925 | 0 |  | 0 | 1000.1975 | 0 |  | 0 | 0 | 0 |  | 0 | 12636.2925 | 0 |  | 0 | 1000.1975 | 0 |  | 0 | 0 | 0 |  | 0 | 12636.2925 | 0 |  | 0 | 1000.1975 | 0 |  | 0 | 13636.49 | 0 |  | 0 |  |  | 67924.1888 | 13378.2288 | 0 | 0
PeopleSoft Enterprise Human Resources | 120400 | 48897.13 | 0 | 48897.13 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | 12224.2825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12224.2825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12224.2825 | 0 |  | 0 | 0 | 0 |  | 0 | 12224.2825 | 0 |  | 0 |  |  | 60881.72 | 11984.59 | 0 | 0
PeopleSoft Enterprise Payroll | 120400 | 59469.02 | 0 | 59469.02 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | 14867.255 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14867.255 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14867.255 | 0 |  | 0 | 0 | 0 |  | 0 | 14867.255 | 0 |  | 0 |  |  | 74044.76 | 14575.74 | 0 | 0
PeopleSoft Enterprise Project Costing | 102084 | 77273.8 | 0 | 77273.8 | 0 | 0 |  | 0 | 18952.5775 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 19318.45 | 0 |  | 0 |  |  | 96226.3775 | 18952.5775 | 0 | 0
PeopleSoft Enterprise Purchasing | 102084 | 85456.36 | 0 | 85456.36 | 0 | 0 |  | 0 | 20959.47 | 0 |  | 0 | 0 | 0 |  | 0 | 19797.1175 | 0 |  | 0 | 1566.9725 | 0 |  | 0 | 0 | 0 |  | 0 | 19797.1175 | 0 |  | 0 | 1566.9725 | 0 |  | 0 | 0 | 0 |  | 0 | 19797.1175 | 0 |  | 0 | 1566.9725 | 0 |  | 0 | 21364.09 | 0 |  | 0 |  |  | 106415.83 | 20959.47 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 102084 | 77273.8 | 0 | 77273.8 | 0 | 0 |  | 0 | 18952.5775 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 19318.45 | 0 |  | 0 |  |  | 96226.3775 | 18952.5775 | 0 | 0
PeopleSoft Enterprise Treasury | 102084 | 61818.61 | 0 | 61818.61 | 0 | 0 |  | 0 | 15161.955 | 0 |  | 0 | 0 | 0 |  | 0 | 14321.1 | 0 |  | 0 | 1133.5525 | 0 |  | 0 | 0 | 0 |  | 0 | 14321.1 | 0 |  | 0 | 1133.5525 | 0 |  | 0 | 0 | 0 |  | 0 | 14321.1 | 0 |  | 0 | 1133.5525 | 0 |  | 0 | 15454.6525 | 0 |  | 0 |  |  | 76980.565 | 15161.955 | 0 | 0
PeopleSoft Enterprise Time and Labor | 120400 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Analytics |  | 55358.8517 | 0 | 55358.8517 | 0 | 0 | 0 | 0 | 13568.35 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19792.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6224.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12448.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52034.06 | 13568.35 | 13568.35 | 0
HR Analytics (DW/BI) | 100 | 46132.3764 | 0 | 46132.3764 | 0 | 0 |  | 0 | 11307 | 11307 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 16493.97 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5186.97 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 10373.94 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 43361.88 | 11307 | 11307 | 0
Project Analytics (DW/BI) | 20 | 9226.4753 | 0 | 9226.4753 | 0 | 0 |  | 0 | 2261.35 | 2261.35 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3298.72 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1037.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2074.74 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 8672.18 | 2261.35 | 2261.35 | 0
Financials Analytics (DW/BI) | 3000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
OAC |  | 0 | 405463 | 405463 | 44165.81 | 17097.05 |  | 17097.05 | 33741.76 | 10035.49 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 |  |  | 415793.37 | 77907.57 | 27132.54 | 17097.05
OAC (DW/BI) - DEV: $53,219.00 - Test: $63,779.00 - DR: $94,238.00 - Production: $194,227.00 | 4 | 0 | 405463 | 405463 | 44165.81 | 17097.05 |  | 17097.05 | 33741.76 | 10035.49 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 0 | 0 | 415793.37 | 77907.57 | 27132.54 | 17097.05
New License Purchase and Tech Support |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 1469309.5824 | 405463 | 1874772.5824 | 44165.81 | 17097.05 | #REF! | 17097.05 | 394048.7587 | 24821.06 | #REF! | 1217.22 | 33788.58 | 0 | #REF! | 0 | 368705.6727 | 0 | #REF! | 0 | 72151.86 | 0 | #REF! | 0 | 33788.58 | 0 | #REF! | 0 | 368705.6727 | 0 | #REF! | 0 | 58583.51 | 0 | #REF! | 0 | 33788.58 | 0 | #REF! | 0 | 368705.6727 | 0 | #REF! | 0 | 64807.85 | 0 | #REF! | 0 | 386059.0477 | 0 | #REF! | 0 | 0 | 0 | 2227299.5945 | 438214.5687 | 41918.11 | 18314.27
Projected FYTD |  |  |  |  | 44165.81 |  |  |  | 438214.5687 |  |  |  | 472003.1487 |  |  |  | 840708.8214 |  |  |  | 912860.6814 |  |  |  | 946649.2614 |  |  |  | 1315354.9341 |  |  |  | 1373938.4441 |  |  |  | 1407727.0241 |  |  |  | 1776432.6968 |  |  |  | 1841240.5468 |  |  |  | 2227299.5945
Incurred FYTD | [5 empty] | 17097.05 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11
Paid FYTD | [7 empty] | 17097.05 |  |  |  | 18314.27 |  |  |  | 18314.27 |  |  |  | 18314.27 |  |  |  | 18314.27 |  |  |  | 18314.27 |  |  |  | 18314.27 |  |  |  | 18314.27 |  |  |  | 18314.27 |  |  |  | 18314.27 |  |  |  | 18314.27 |  |  |  | 18314.27

## Florida PALM-UAT
Department of Financial Services
Florida PALM FY 2025 - 2026 PALM Readiness Detail FYTD
|  |  |  | July 2025 |  |  | August 2025 |  |  | September 2025 |  |  | October 2025 |  |  | November 2025 |  |  | December 2025 |  |  | January 2026 |  |  | February 2026 |  |  | March 2026 |  |  | April 2026 |  |  | May 2026 |  |  | June 2026 |  |  | CF 2025-26 |  | Total
Item Description | Rate | Quantity | Total Projected | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Incurred | Paid | Projected FYTD | Incurred FYTD | Paid FYTD
PALM Readiness Deliverables | 0 |  | 2750000 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | 1100000 | 0 | 0 | 0 | 0 | 0 | 825000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UAT-QA D1 Project Schedule |  |  | 275000 | [6 empty] | 275000 | [31 empty] | 0
UAT-QA D2 Standardized UAT and Automation Testing Plan |  |  | 550000 | [9 empty] | 550000 | [28 empty] | 0
UAT-QA D3 Report Providing Confirmation of Functional / Non-Functional Requirements and Agencies Ability to Comply with Financial Regulations |  |  | 550000 | [9 empty] | 550000 | [28 empty] | 0
UAT-QA D4 Deployment of Streamline Testing Efforts and Regression Testing Automation |  |  | 825000 | [15 empty] | 825000 | [22 empty] | 0
UAT-QA D5 Final Assessment Report |  |  | 550000 | [24 empty] | 550000 | [13 empty] | 0
Total |  |  | 2750000 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | 1100000 | 0 | 0 | 0 | 0 | 0 | 825000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  | 0 |  |  | 275000 |  |  | 1375000 |  |  | 1375000 |  |  | 2200000 |  |  | 2200000 |  |  | 2200000 |  |  | 2750000 |  |  | 2750000 |  |  | 2750000 |  |  | 2750000
Incurred FYTD |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
Paid FYTD | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0