## Monthly Summary
Department of Financial Services
Florida PALM FY 2025 - 2026 Spend Plan Summary FYTD
As of September 30, 2025
Annual
| TRUE | TRUE | TRUE | TRUE | TRUE |  | ERROR | July 2025 |  |  |  | August 2025 |  |  |  | September 2025 |  |  |  | Q2 Baseline Adjustment | October 2025 |  |  | November 2025 |  |  | December 2025 |  |  | January 2026 |  |  | February 2026 |  |  | March 2026 |  |  | April 2026 |  |  | May 2026 |  |  | June 2026 |  |  | CF 2025-26 |  | Fiscal Year to Date
Category (Cost Area / Contract) | 10130387 | 45930662 | 56061049 | 26439659 | 29621390 | 49950225.6095 | 19737272.92 | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
| FY 24-25 Revert & Appropriated | FY 25-26 GAA Appropriated | FY 25-26 Total Appropriation | Released | Unreleased | Projected | Release Remaining | [12 empty] | Q1 Baseline Adjustment
FLAIR System Replacement (100781) | 10130387 | 45930662 | 56061049 | 26439659 | 29621390 | 49950225.6095 | 19737272.92 | 4631851.0633 | 2445591.29 |  | 1335444.96 | 6967995.1871 | 3224806.19 |  | 1127783.64 | 2639834.5033 | 2227550.22 |  | 4239157.48 | -6341733.0537 | 6305759.5453 | 0 | 0 | 5042152.3589 | 0 | 0 | 1874375.7989 | 0 | 0 | 5568268.2282 | 0 | 0 | 6326079.9056 | 0 | 0 | 1329104.9356 | 0 | 0 | 4810367.6482 | 0 | 0 | 7625077.4656 | 0 | 0 | 3171092.0232 | 0 | 0 | #REF! | #REF! | 7897947.7 | 7897947.7 | 6702386.08 | 42052277.9095 | 84.19%
SSI Implementation Services (FP004) | [5 empty] | 27285523 |  | 2000000 | 0 |  | 0 | 5338840 | 2000000 | 2 | 0 | 994983 | 994983 |  | 2994983 | -5338840 | 4000000 | 0 | 0 | 3420540 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3667500 | 0 | 0 | 0 | 0 | 0 | 2681700 | 0 | 0 | 6020800 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 2994983 | 2994983 | 2994983 | 24290540 | 89.02%
Facilities and Maintenance (FP004) | [5 empty] | 415692 |  | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 34641 | 34641 |  | 34641 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 103923 | 103923 | 103923 | 311769 | 75%
Production Support (FP004) | [5 empty] | 9935896 |  | 1534630 | 1521776 |  | 830806 | 713885 | 713885 |  | 690970 | 713885 | 713885 |  | 713885 | -12854 | 907013 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 907013 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 907014 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 0 | 0 | 2949546 | 2949546 | 2235661 | 6986350 | 70.31%
Additional Facilities | [5 empty] | 241100.58 |  | 19961.81 | 19961.81 |  | 0 | 19961.81 | 19961.81 |  | 39923.62 | 19961.81 | 19961.81 |  | 19961.81 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 19961.81 | 0 | 0 | 20143.61 | 0 | 0 | 20143.61 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 0 | 0 | 59885.43 | 59885.43 | 59885.43 | 181215.15 | 75.16%
Production Support Administration | [5 empty] | 810106.56 |  | 41971.78 | 1177 | 2 | 1177 | 7971.78 | 5355.02 |  | 5355.02 | 7971.78 | 2971.76 | 2 | 2971.76 | -48411.56 | 41971.78 | 0 | 0 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 34971.78 | 0 | 0 | 675828.54 | 0 | 0 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 7971.78 | 0 | 0 | 0 | 0 | 9503.78 | 9503.78 | 9503.78 | 800602.78 | 98.83%
Oracle Software and Maintenance (FP005) | [5 empty] | 2127622.2495 |  | 44165.81 | 17097.05 | 2 | 17097.05 | 394048.7637 | 24821.06 | 2 | 1217.22 | 33788.58 | 20602.24 | 2 | 23603.84 | -409482.8037 | 714227.1064 | 0 | 0 | 72151.86 | 0 | 0 | 33788.58 | 0 | 0 | 362753.0094 | 0 | 0 | 52630.8467 | 0 | 0 | 27835.9167 | 0 | 0 | 362753.0094 | 0 | 0 | 58855.1867 | 0 | 0 | 380106.3844 | 0 | 0 | 0 | 0 | 62520.35 | 62520.35 | 41918.11 | 2065101.8995 | 97.06%
Project Administration | [5 empty] | 293888.04 |  | 30988.5233 | 19025.51 | 2 | 19025.51 | 30724.2733 | 18534.26 | 2 | 18534.26 | 80067.4133 | 8503.03 | 2 | 8503.03 | -95717.41 | 113869.5689 | 0 | 0 | 36175.7089 | 0 | 0 | 11175.7089 | 0 | 0 | 15475.7089 | 0 | 0 | 12125.7089 | 0 | 0 | 21675.7089 | 0 | 0 | 14975.7089 | 0 | 0 | 11175.7089 | 0 | 0 | 11175.7089 | 0 | 0 | 0 | 0 | 46062.8 | 46062.8 | 46062.8 | 247825.24 | 84.33%
Florida PALM-UAT | [5 empty] | 2750000 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 275000 | 0 | 2 | 0 | -275000 | 0 | 0 | 0 | 275000 | 0 | 0 | 550000 | 0 | 0 | 687500 | 0 | 0 | 687500 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | 0 | 0 | 0 | 2750000 | 100%
Support Services | [5 empty] | 4102079.18 |  | 585621.14 | 503522.92 | 5,1 | 252332.4 | 288650.56 | 272608.04 |  | 223318.52 | 333631.92 | 304834.38 |  | 300480.04 | -126938.28 | 355395.28 | 0 | 0 | 315225.2 | 0 | 0 | 341391.92 | 0 | 0 | 341391.92 | 0 | 0 | 315225.2 | 0 | 0 | 341391.92 | 0 | 0 | 341391.92 | 0 | 0 | 328308.56 | 0 | 0 | 341391.92 | 0 | 0 | 0 | 0 | 1080965.34 | 1080965.34 | 776130.96 | 3021113.84 | 73.65%
QA Support Services | [5 empty] | 1988318 |  | 339871 | 328390 |  | 180366 | 139272 | 135000 |  | 113824 | 145904 | 127168 | 1 | 140128 | -34489 | 118680 | 0 | 0 | 149600 | 0 | 0 | 164560 | 0 | 0 | 164560 | 0 | 0 | 149600 | 0 | 0 | 164560 | 0 | 0 | 164560 | 0 | 0 | 157080 | 0 | 0 | 164560 | 0 | 0 | #REF! | #REF! | 590558 | 590558 | 434318 | 1397760 | 70.3%
Florida PALM Unprojected Project Reserves | [5 empty] | 0
Contingency (100819) | 3000000 |  | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Salaries & Benefits (010000) IRTF |  | 11201828 | 11201828 | 11201828 | 0 | 10733685.48 | 8714931.77 | 916309.9167 | 849765.77 |  | 849765.77 | 916309.9167 | 810184.44 |  | 810184.44 | 916309.9167 | 826946.02 |  | 826946.02 | -262033.52 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 916309.9167 | 0 | 0 | 0 | 0 | 2486896.23 | 2486896.23 | 2486896.23 | 8246789.25 | 76.83%
Salaries & Benefits (010000) GRF |  | 1924578 | 1924578 | 962285 | 962293 | 1516377.02 | 863245.98 | 157482 | 33013 |  | 33013 | 157482 | 33013.01 |  | 33013.01 | 157482 | 33013.01 |  | 33013.01 | -373406.98 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 | 157482 | 0 | 0 |  |  | 99039.02 | 99039.02 | 99039.02 | 1417338 | 93.47%
Data Processing Services (210000) |  | 0 | 0 | 0 | 0 | 0 | 0 | 112138 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -112138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Risk Management Insurance (103241) |  | 14572 | 14572 | 14572 | 0 | 14572 | 0 | 13957 | 0 |  | 0 | 0 | 0 |  | 0 | 615 | 14572 | 3 | 14572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14572 | 14572 | 14572 | 0 | 0%
DMS HR Transfer (107040) IRTF |  | 24081 | 24081 | 24081 | 0 | 24081 | 24081 | 6000 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -6000 | 12040.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6020.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6020.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24081 | 100%
DMS HR Transfer (107040) GRF |  | 3528 | 3528 | 3528 | 0 | 3528 | 3528 | 880 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -880 | 1764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3528 | 100%
Totals | 13130387 | 59099249 | 72229636 | 38645953 | 33583683 | 62242469.1095 | 29343059.67 | 5838617.98 | 3328370.06 |  | 2218223.73 | 8041787.1037 | 4068003.64 |  | 1970981.09 | 3714241.42 | 3102081.25 |  | 5113688.51 | -7096191.5538 | 7393355.962 | 0 | 0 | 6115944.2756 | 0 | 0 | 2948167.7156 | 0 | 0 | 6648962.3949 | 0 | 0 | 7399871.8222 | 0 | 0 | 2402896.8522 | 0 | 0 | 5891061.8149 | 0 | 0 | 8698869.3822 | 0 | 0 | 4244883.9399 | 0 | 0 | #REF! | #REF! | 10498454.95 | 10498454.95 | 9302893.33 | 51744014.1595 | 100%
Running Totals | [7 empty] | 5838617.98 | 3328370.06 |  | 2218223.73 | 13880405.0838 | 7396373.7 |  | 4189204.82 | 17594646.5038 | 10498454.95 |  | 9302893.33 | 10498454.95 | 17891810.912 | 10498454.95 | 9302893.33 | 24007755.1876 | 10498454.95 | 9302893.33 | 26955922.9031 | 10498454.95 | 9302893.33 | 33604885.298 | 10498454.95 | 9302893.33 | 41004757.1202 | 10498454.95 | 9302893.33 | 43407653.9725 | 10498454.95 | 9302893.33 | 49298715.7874 | 10498454.95 | 9302893.33 | 57997585.1696 | 10498454.95 | 9302893.33 | 62242469.1095 | 10498454.95 | 9302893.33 |  | #REF! |  |  | Total Incurred/Total Projected FYTD |  | 100%
Monthly Total Incurred/Total Projected | [7 empty] | 57.01% |  |  |  | 50.59% |  |  |  | 83.52% |  |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% | [6 empty] | Total Paid/Total Projected FYTD |  | 88.61%
Monthly Total Incurred/Total Projected (Variance) | [7 empty] | -42.99% |  |  |  | -49.41% |  |  |  | -16.48% |  |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [7 empty] | 57.01% |  |  |  | 53.29% |  |  |  | 59.67% |  |  |  |  | 58.68% |  |  | 43.73% |  |  | 38.95% |  |  | 31.24% |  |  | 25.6% |  |  | 24.19% |  |  | 21.3% |  |  | 18.1% |  |  | 16.87% | [6 empty] | Total Release/Total Appropriation |  | 53.5%
FYTD Total Incurred/Total Projected (Variance) | [7 empty] | -42.99% |  |  |  | -46.71% |  |  |  | -40.33% |  |  |  |  | -41.32% |  |  | -56.27% |  |  | -61.05% |  |  | -68.76% |  |  | -74.4% |  |  | -75.81% |  |  | -78.7% |  |  | -81.9% |  |  | -83.13%
[52 empty] | Total Paid/Total Release |  | 24.07%
Reconciles to ALRR | No |  | Yes | Yes | Yes | [5 empty] | No |  |  |  | No |  |  |  | No |  |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  | #REF! |  |  | No

## Footnotes
Department of Financial Services
FY 2025 - 2026 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Contractor hours projected and incurred amounts were greater than anticipated due to June 2025 hours not being projected to be incurred in July 2025.
6

## SSI Detail
|  |  |  | July 2025 |  |  | August 2025 |  |  | September 2025 |  |  | Q2 Baseline Adjustment | October 2025 |  |  | November 2025 |  |  | December 2025 |  |  | January 2026 |  |  | February 2026 |  |  | March 2026 |  |  | April 2026 |  |  | May 2026 |  |  | June 2026 |  |  | CF 2025-26
|  | Description | Total Deliverable Cost FY 25-26 | July Projection | July Accepted / Approved | July Paid | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid |  | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Projection
Department of Financial Services
Florida PALM FY 2025 - 2026 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
657 | Completion of Mock Conversion III (UAT) | Implementation | 2000000 |  |  |  | 2000000 | 2000000 |  |  |  | 2000000 | 0 | [27 empty] | 0 | 0 | 2000000
658 | Develop the Deployment and Contingency Plan | Implementation | 2000000 |  |  |  | 2000000 | [5 empty] | -2000000 | 2000000 | [26 empty] | 0 | 0 | 2000000
661 | Completion of System Test DW/BI | Implementation | 1338840 |  |  |  | 1338840 | [5 empty] | -1338840 |  |  |  | 1338840 | [23 empty] | 0 | 0 | 1338840
662 | Completion of Mock Conversion IV | Implementation | 1500000 | [9 empty] | 0 | [9 empty] | 1500000 | [17 empty] | 0 | 0 | 1500000
663 | Completion of Interface Testing Segment I | Implementation | 2081700 | [9 empty] | 0 |  |  |  | 2081700 | [23 empty] | 0 | 0 | 2081700
666 | Support of UAT Segment I | Implementation | 2236500 | [9 empty] | 0 | [12 empty] | 1691000 | [14 empty] | 0 | 0 | 1691000
667 | Completion of Mock Go-Lives (Dry Run #1) | Implementation | 1500000 | [9 empty] | 0 | [9 empty] | 1500000 | [17 empty] | 0 | 0 | 1500000
669 | Support of UAT Segment II | Implementation | 1976500 | [9 empty] | 0 | [12 empty] | 1976500 | [14 empty] | 0 | 0 | 1976500
670 | Completion of Payroll Parallel Testing | Implementation | 600000 | [9 empty] | 0 | [18 empty] | 600000 | [8 empty] | 0 | 0 | 600000
671 | Completion of Interface Testing Segment II | Implementation | 2081700 | [9 empty] | 0 | [18 empty] | 2081700 | [8 empty] | 0 | 0 | 2081700
672 | Support of UAT Segment III | Implementation | 1976500 | [9 empty] | 0 | [21 empty] | 1976500 | [5 empty] | 0 | 0 | 1976500
673 | Completion of Mock Go-Lives (Dry Run #2) | Implementation | 1500000 | [9 empty] | 0 | [21 empty] | 1500000 | [5 empty] | 0 | 0 | 1500000
674 | Completion of Penetration Testing | Implementation | 513400 | [9 empty] | 0 | [21 empty] | 513400 | [5 empty] | 0 | 0 | 513400
675 | Completion of Performance Testing | Implementation | 1480900 | [9 empty] | 0 | [21 empty] | 1480900 | [5 empty] | 0 | 0 | 1480900
676 | Completion of Disaster Recovery Testing | Implementation | 550000 | [9 empty] | 0 | [21 empty] | 550000 | [5 empty] | 0 | 0 | 550000
677 | Completion of Mock Go-Lives (Dry Run #3) | Implementation | 1500000 | [9 empty] | 0 | [6 empty] | 0 | [17 empty] | 1500000 |  |  | 0 | 0 | 1500000
696 | Completion of System Test Segment III | Implementation | 2000000 | 2000000 | [8 empty] | -2000000 | 2000000 | [26 empty] | 0 | 0 | 2000000
697 | Completion of Employee Self-Service Build | Implementation | 994983 | [6 empty] | 994983 | 994983 | 994983 | 0 | [27 empty] | 0 | 0 | 994983
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 415692 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 0 | 0 | 415692
Prod Supp | AM Services | Prod Supp | 7071100 | 572300 | 572300 |  | 590800 | 590800 | 572300 | 590800 | 590800 | 590800 | 0 | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 590800 |  |  | 0 | 0 | 7071100
Prod Supp | IM Services (Reduced Monthly by $3,715 SNow Credit) | Prod Supp | 1446020 | 119085 | 118670 |  | 123085 | 123085 | 118670 | 123085 | 123085 | 123085 | -415 | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 120085 |  |  | 0 | 0 | 1445605
Prod Supp | Oracle OCI Costs | Prod Supp | 784513 | 196128 | 196128 | 196128 | 0 |  |  | 0 |  |  | 0 | 196128 |  |  | 0 |  |  | 0 |  |  | 196128 |  |  | 0 |  |  | 0 |  |  | 196129 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 784513
Prod Supp | Support Tools Maintenance | Prod Supp | 47772 | 47772 | 47772 | 47772 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 47772
Prod Supp | Support Tools Purchase | Prod Supp | 571800 | 571800 | 571800 | 571800 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 571800
Prod Supp | Solution Software Support (Reduced by $4,980 for A7 credit) | Prod Supp | 27545 | 27545 | 15106 | 15106 | 0 |  |  | 0 |  |  | -12439 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 15106
| Implementation Total: |  |  | 2000000 | 0 | 0 | 5338840 | 2000000 | 0 | 994983 | 994983 | 2994983 | -5338840 | 4000000 | 0 | 0 | 3420540 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3667500 | 0 | 0 | 0 | 0 | 0 | 2681700 | 0 | 0 | 6020800 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 27285523
| Production Support Facilities Total: |  |  | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 34641 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692
| Production Support (No Facilities) Total: |  |  | 1534630 | 1521776 | 830806 | 713885 | 713885 | 690970 | 713885 | 713885 | 713885 | -12854 | 907013 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 907013 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 907014 | 0 | 0 | 710885 | 0 | 0 | 710885 | 0 | 0 | 0 | 0 | 9935896
Monthly Totals |  |  | 38195465 | 3569271 | 1556417 | 865447 | 6087366 | 2748526 | 725611 | 1743509 | 1743509 | 3743509 | -5351694 | 4941654 | 0 | 0 | 4166066 | 0 | 0 | 745526 | 0 | 0 | 3941654 | 0 | 0 | 4413026 | 0 | 0 | 745526 | 0 | 0 | 3623355 | 0 | 0 | 6766326 | 0 | 0 | 2245526 | 0 | 0 | 0 | 0 | 37637111
| Projected YTD |  |  | 3569271 |  |  | 9656637 |  |  | 11400146 |  |  | 6048452 | 10990106 |  |  | 15156172 |  |  | 15901698 |  |  | 19843352 |  |  | 24256378 |  |  | 25001904 |  |  | 28625259 |  |  | 35391585 |  |  | 37637111
| Incurred YTD |  |  |  | 1556417 |  |  | 4304943 |  |  | 6048452 |  |  |  | 6048452 |  |  | 6048452 |  |  | 6048452 |  |  | 6048452 |  |  | 6048452 |  |  | 6048452 |  |  | 6048452 |  |  | 6048452 |  |  | 6048452 |  | 6048452
| Paid YTD |  |  |  |  | 865447 |  |  | 1591058 |  |  | 5334567 |  |  |  | 5334567 |  |  | 5334567 |  |  | 5334567 |  |  | 5334567 |  |  | 5334567 |  |  | 5334567 |  |  | 5334567 |  |  | 5334567 |  |  | 5334567 |  | 5334567

## Oracle Summary
Department of Financial Services
Florida PALM FY 2025 - 2026 Oracle Summary FYTD
| Quantity/Months | Quote |  |  | July 2025 |  |  |  | August 2025 |  |  |  | September 2025 |  |  |  | Q2 Baseline Adjustment | October 2025 |  |  |  | November 2025 |  |  |  | December 2025 |  |  |  | January 2026 |  |  |  | February 2026 |  |  |  | March 2026 |  |  |  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026 |  |  |  | FY 2025-26 CF |  | Total
Program |  | Tech Support | Total Purchase/ Subscription | Total Projection | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | CF Incurred | CF Paid | Total Projected | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support |  | 1413950.7308 | 0 | 1413950.7308 | 0 | 0 | #REF! | 0 | 346738.6537 | 1217.22 | #REF! | 1217.22 | 0 | 0 | #REF! | 0 | -345521.4338 | 680438.5264 | 0 | #REF! | 0 | 18570.59 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 334917.0927 | 0 | #REF! | 0 | 18570.59 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 334917.0927 | 0 | #REF! | 0 | 18570.59 | 0 | #REF! | 0 | 352270.4677 | 0 | #REF! | 0 | 0 | 0 | 2537105.0533 | 62520.35 | 62520.35 | 41918.11
Assignment |  | 1413950.7308 | 0 | 1413950.7308 | 0 | 0 | 0 | 0 | 346738.6537 | 1217.22 | 0 | 1217.22 | 0 | 0 | 0 | 0 | -345521.4338 | 680438.5264 | 0 | 0 | 0 | 18570.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334917.0927 | 0 | 0 | 0 | 18570.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334917.0927 | 0 | 0 | 0 | 18570.59 | 0 | 0 | 0 | 352270.4677 | 0 | 0 | 0 | 0 | 0 | 2104993.6033 | 1217.22 | 1217.22 | 1217.22
Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 2 | 8407.53 | 0 | 8407.53 | 0 | 0 |  | 0 | 2084.5425 | 1217.22 |  | 1217.22 | 0 | 0 |  | 0 | -867.3225 | 1751.99 | 0 |  | 0 | 1217.215 | 0 |  | 0 | 0 | 0 |  | 0 | 884.6675 | 0 |  | 0 | 1217.215 | 0 |  | 0 | 0 | 0 |  | 0 | 884.6675 | 0 |  | 0 | 1217.215 | 0 |  | 0 | 884.6675 | 0 |  | 0 |  |  | 10142.18 | 1217.22 | 1217.22 | 1217.22
Oracle Business Intelligence (Analytics) Server Administrator | 4 | 1509.1834 | 0 | 1509.1834 | 0 | 0 |  | 0 | 369.8975 | 0 |  | 0 | 0 | 0 |  | 0 | -369.8975 | 747.1934 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 377.2959 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 377.2959 | 0 |  | 0 | 0 | 0 |  | 0 | 377.2959 | 0 |  | 0 |  |  | 2248.9784 | 0 | 0 | 0
Oracle Business Intelligence Management Pack | 4 | 2992.44 | 0 | 2992.44 | 0 | 0 |  | 0 | 733.4425 | 0 |  | 0 | 0 | 0 |  | 0 | -733.4425 | 1481.5525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 748.11 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 748.11 | 0 |  | 0 | 0 | 0 |  | 0 | 748.11 | 0 |  | 0 |  |  | 4459.325 | 0 | 0 | 0
Oracle Business Intelligence Suite Foundation Edition | 4 | 78080.06 | 0 | 78080.06 | 0 | 0 |  | 0 | 19137.2675 | 0 |  | 0 | 0 | 0 |  | 0 | -19137.2675 | 38657.2825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19520.015 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19520.015 | 0 |  | 0 | 0 | 0 |  | 0 | 19520.015 | 0 |  | 0 |  |  | 116354.595 | 0 | 0 | 0
Oracle Data Integrator Enterprise Edition | 20 | 39040.032 | 0 | 39040.032 | 0 | 0 |  | 0 | 9568.635 | 0 |  | 0 | 0 | 0 |  | 0 | -9568.635 | 19328.643 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9760.008 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9760.008 | 0 |  | 0 | 0 | 0 |  | 0 | 9760.008 | 0 |  | 0 |  |  | 58177.302 | 0 | 0 | 0
Oracle Data Visualization | 4 | 26027.3955 | 0 | 26027.3955 | 0 | 0 |  | 0 | 6379.265 | 0 |  | 0 | 0 | 0 |  | 0 | -6379.265 | 12886.1139 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6506.8489 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6506.8489 | 0 |  | 0 | 0 | 0 |  | 0 | 6506.8489 | 0 |  | 0 |  |  | 38785.9255 | 0 | 0 | 0
Oracle Financial Analytics Fusion Edition (DW/BI) | 100 | 15096.1104 | 0 | 15096.1104 | 0 | 0 |  | 0 | 3700.0275 | 0 |  | 0 | 0 | 0 |  | 0 | -3700.0275 | 7474.0551 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3774.0276 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3774.0276 | 0 |  | 0 | 0 | 0 |  | 0 | 3774.0276 | 0 |  | 0 |  |  | 22496.1654 | 0 | 0 | 0
Oracle Managed File Transfer | 12 | 21800.7813 | 0 | 21800.7813 | 0 | 0 |  | 0 | 5343.3275 | 0 |  | 0 | 0 | 0 |  | 0 | -5343.3275 | 10793.5228 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5450.1953 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5450.1953 | 0 |  | 0 | 0 | 0 |  | 0 | 5450.1953 | 0 |  | 0 |  |  | 32487.4363 | 0 | 0 | 0
Oracle Management Pack for Oracle Data Integrator | 16 | 7183.1817 | 0 | 7183.1817 | 0 | 0 |  | 0 | 1760.5825 | 0 |  | 0 | 0 | 0 |  | 0 | -1760.5825 | 3556.3779 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1795.7954 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1795.7954 | 0 |  | 0 | 0 | 0 |  | 0 | 1795.7954 | 0 |  | 0 |  |  | 10704.3467 | 0 | 0 | 0
Oracle SOA Management Pack Enterprise Edition | 14 | 21084.1199 | 0 | 21084.1199 | 0 | 0 |  | 0 | 5167.6775 | 0 |  | 0 | 0 | 0 |  | 0 | -5167.6775 | 10438.7075 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5271.03 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5271.03 | 0 |  | 0 | 0 | 0 |  | 0 | 5271.03 | 0 |  | 0 |  |  | 31419.4749 | 0 | 0 | 0
Oracle SOA Suite for Oracle Middleware | 14 | 48493.0302 | 0 | 48493.0302 | 0 | 0 |  | 0 | 11885.545 | 0 |  | 0 | 0 | 0 |  | 0 | -11885.545 | 24008.8025 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12123.2575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12123.2575 | 0 |  | 0 | 0 | 0 |  | 0 | 12123.2575 | 0 |  | 0 |  |  | 72264.1202 | 0 | 0 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 26 | 18840.42 | 0 | 18840.42 | 0 | 0 |  | 0 | 4617.75 | 0 |  | 0 | 0 | 0 |  | 0 | -4617.75 | 9327.855 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4710.105 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4710.105 | 0 |  | 0 | 0 | 0 |  | 0 | 4710.105 | 0 |  | 0 |  |  | 28075.92 | 0 | 0 | 0
Oracle WebLogic Suite | 26 | 70652.1264 | 0 | 70652.1264 | 0 | 0 |  | 0 | 17316.7 | 0 |  | 0 | 0 | 0 |  | 0 | -17316.7 | 34979.7316 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17663.0316 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17663.0316 | 0 |  | 0 | 0 | 0 |  | 0 | 17663.0316 | 0 |  | 0 |  |  | 105285.5264 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 102084 | 58183.35 | 0 | 58183.35 | 0 | 0 |  | 0 | 14270.345 | 0 |  | 0 | 0 | 0 |  | 0 | -14270.345 | 27749.3125 | 0 |  | 0 | 1066.87 | 0 |  | 0 | 0 | 0 |  | 0 | 13478.9675 | 0 |  | 0 | 1066.87 | 0 |  | 0 | 0 | 0 |  | 0 | 13478.9675 | 0 |  | 0 | 1066.87 | 0 |  | 0 | 14545.8375 | 0 |  | 0 |  |  | 86724.04 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 102084 | 38183.04 | 0 | 38183.04 | 0 | 0 |  | 0 | 9364.9788 | 0 |  | 0 | 0 | 0 |  | 0 | -9364.9788 | 18210.6013 | 0 |  | 0 | 700.1375 | 0 |  | 0 | 0 | 0 |  | 0 | 8845.6225 | 0 |  | 0 | 700.1375 | 0 |  | 0 | 0 | 0 |  | 0 | 8845.6225 | 0 |  | 0 | 700.1375 | 0 |  | 0 | 9545.76 | 0 |  | 0 |  |  | 56912.9975 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 102084 | 77273.8 | 0 | 77273.8 | 0 | 0 |  | 0 | 18952.5775 | 0 |  | 0 | 0 | 0 |  | 0 | -18952.5775 | 36854.085 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 19318.45 | 0 |  | 0 |  |  | 115178.955 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 102084 | 416369.45 | 0 | 416369.45 | 0 | 0 |  | 0 | 102120.9538 | 0 |  | 0 | 0 | 0 |  | 0 | -102120.9538 | 198578.4987 | 0 |  | 0 | 7634.8175 | 0 |  | 0 | 0 | 0 |  | 0 | 96457.545 | 0 |  | 0 | 7634.8175 | 0 |  | 0 | 0 | 0 |  | 0 | 96457.545 | 0 |  | 0 | 7634.8175 | 0 |  | 0 | 104092.3625 | 0 |  | 0 |  |  | 620611.3575 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 102084 | 54545.96 | 0 | 54545.96 | 0 | 0 |  | 0 | 13378.2288 | 0 |  | 0 | 0 | 0 |  | 0 | -13378.2288 | 26014.5212 | 0 |  | 0 | 1000.1975 | 0 |  | 0 | 0 | 0 |  | 0 | 12636.2925 | 0 |  | 0 | 1000.1975 | 0 |  | 0 | 0 | 0 |  | 0 | 12636.2925 | 0 |  | 0 | 1000.1975 | 0 |  | 0 | 13636.49 | 0 |  | 0 |  |  | 81302.4175 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 120400 | 48897.13 | 0 | 48897.13 | 0 | 0 |  | 0 | 11984.59 | 0 |  | 0 | 0 | 0 |  | 0 | -11984.59 | 24208.8725 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12224.2825 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12224.2825 | 0 |  | 0 | 0 | 0 |  | 0 | 12224.2825 | 0 |  | 0 |  |  | 72866.31 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 120400 | 59469.02 | 0 | 59469.02 | 0 | 0 |  | 0 | 14575.74 | 0 |  | 0 | 0 | 0 |  | 0 | -14575.74 | 29442.995 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14867.255 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14867.255 | 0 |  | 0 | 0 | 0 |  | 0 | 14867.255 | 0 |  | 0 |  |  | 88620.5 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 102084 | 77273.8 | 0 | 77273.8 | 0 | 0 |  | 0 | 18952.5775 | 0 |  | 0 | 0 | 0 |  | 0 | -18952.5775 | 36854.085 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 19318.45 | 0 |  | 0 |  |  | 115178.955 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 102084 | 85456.36 | 0 | 85456.36 | 0 | 0 |  | 0 | 20959.47 | 0 |  | 0 | 0 | 0 |  | 0 | -20959.47 | 40756.5875 | 0 |  | 0 | 1566.9725 | 0 |  | 0 | 0 | 0 |  | 0 | 19797.1175 | 0 |  | 0 | 1566.9725 | 0 |  | 0 | 0 | 0 |  | 0 | 19797.1175 | 0 |  | 0 | 1566.9725 | 0 |  | 0 | 21364.09 | 0 |  | 0 |  |  | 127375.3 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 102084 | 77273.8 | 0 | 77273.8 | 0 | 0 |  | 0 | 18952.5775 | 0 |  | 0 | 0 | 0 |  | 0 | -18952.5775 | 36854.085 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 0 | 0 |  | 0 | 17901.5075 | 0 |  | 0 | 1416.9425 | 0 |  | 0 | 19318.45 | 0 |  | 0 |  |  | 115178.955 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 102084 | 61818.61 | 0 | 61818.61 | 0 | 0 |  | 0 | 15161.955 | 0 |  | 0 | 0 | 0 |  | 0 | -15161.955 | 29483.055 | 0 |  | 0 | 1133.5525 | 0 |  | 0 | 0 | 0 |  | 0 | 14321.1 | 0 |  | 0 | 1133.5525 | 0 |  | 0 | 0 | 0 |  | 0 | 14321.1 | 0 |  | 0 | 1133.5525 | 0 |  | 0 | 15454.6525 | 0 |  | 0 |  |  | 92142.52 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 120400 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Analytics |  | 55358.8517 | 0 | 55358.8517 | 0 | 0 | 0 | 0 | 13568.35 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 13568.35 | 0 | 0 | 0 | 0 | 0 | 19792.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6224.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12448.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52034.06 | 13568.35 | 13568.35 | 13568.35
HR Analytics (DW/BI) | 100 | 46132.3764 | 0 | 46132.3764 | 0 | 0 |  | 0 | 11307 | 11307 |  | 0 | 0 | 0 |  | 11307 | 0 | 0 | 0 |  | 0 | 16493.97 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5186.97 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 10373.94 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 43361.88 | 11307 | 11307 | 11307
Project Analytics (DW/BI) | 20 | 9226.4753 | 0 | 9226.4753 | 0 | 0 |  | 0 | 2261.35 | 2261.35 |  | 0 | 0 | 0 |  | 2261.35 | 0 | 0 | 0 |  | 0 | 3298.72 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1037.37 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2074.74 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 8672.18 | 2261.35 | 2261.35 | 2261.35
Financials Analytics (DW/BI) | 3000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
OAC |  | 0 | 405463 | 405463 | 44165.81 | 17097.05 |  | 17097.05 | 33741.76 | 10035.49 |  | 0 | 33788.58 | 20602.24 |  | 10035.49 | -63961.37 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 |  |  | 380077.39 | 47734.78 | 47734.78 | 27132.54
OAC (DW/BI) - DEV: $53,219.00 - Test: $63,779.00 - DR: $94,238.00 - Production: $194,227.00 | 4 | 0 | 405463 | 405463 | 44165.81 | 17097.05 |  | 17097.05 | 33741.76 | 10035.49 |  | 0 | 33788.58 | 20602.24 |  | 10035.49 | -63961.37 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 33788.58 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 0 | 0 | 380077.39 | 47734.78 | 47734.78 | 27132.54
New License Purchase and Tech Support |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 1469309.5824 | 405463 | 1874772.5824 | 44165.81 | 17097.05 | #REF! | 17097.05 | 394048.7637 | 24821.06 | #REF! | 1217.22 | 33788.58 | 20602.24 | #REF! | 23603.84 | -409482.8038 | 714227.1064 | 0 | #REF! | 0 | 72151.86 | 0 | #REF! | 0 | 33788.58 | 0 | #REF! | 0 | 362753.0094 | 0 | #REF! | 0 | 52630.8467 | 0 | #REF! | 0 | 27835.9167 | 0 | #REF! | 0 | 362753.0094 | 0 | #REF! | 0 | 58855.1867 | 0 | #REF! | 0 | 380106.3844 | 0 | #REF! | 0 | 0 | 0 | 2537105.0533 | 62520.35 | 62520.35 | 41918.11
Projected FYTD |  |  |  |  | 44165.81 |  |  |  | 438214.5737 |  |  |  | 472003.1537 |  |  |  | 62520.35 | 776747.4564 |  |  |  | 848899.3164 |  |  |  | 882687.8964 |  |  |  | 1245440.9058 |  |  |  | 1298071.7525 |  |  |  | 1325907.6691 |  |  |  | 1688660.6785 |  |  |  | 1747515.8652 |  |  |  | 2127622.2495
Incurred FYTD | [5 empty] | 17097.05 |  |  |  | 41918.11 |  |  |  | 62520.35 |  |  |  |  | 62520.35 |  |  |  | 62520.35 |  |  |  | 62520.35 |  |  |  | 62520.35 |  |  |  | 62520.35 |  |  |  | 62520.35 |  |  |  | 62520.35 |  |  |  | 62520.35 |  |  |  | 62520.35
Paid FYTD | [7 empty] | 17097.05 |  |  |  | 18314.27 |  |  |  | 41918.11 |  |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11 |  |  |  | 41918.11

## Florida PALM-UAT
Department of Financial Services
Florida PALM FY 2025 - 2026 PALM Readiness Detail FYTD
|  |  |  | July 2025 |  |  | August 2025 |  |  | September 2025 |  |  | Q2 Baseline Adjustment | October 2025 |  |  | November 2025 |  |  | December 2025 |  |  | January 2026 |  |  | February 2026 |  |  | March 2026 |  |  | April 2026 |  |  | May 2026 |  |  | June 2026 |  |  | CF 2025-26 |  | Total
Item Description | Rate | Quantity | Total Projected | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Incurred | Paid | Projected FYTD | Incurred FYTD | Paid FYTD
PALM Readiness Deliverables | #REF! |  | 2750000 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | -275000 | 0 | 0 | 0 | 275000 | 0 | 0 | 550000 | 0 | 0 | 687500 | 0 | 0 | 687500 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | 0 | #REF! | #REF!
UAT-QA D1 Project Schedule |  |  | 275000 | [6 empty] | 275000 |  |  | -275000 |  |  |  | 275000 | [25 empty] | 0 | 0 | 0
UAT-QA D2 Standardized UAT and Automation Testing Plan |  |  | 550000 | [9 empty] | 0 | [6 empty] | 550000 | [22 empty] | 0 | 0 | 0
UAT-QA D3 Report Identifying Common Agency Test Scripts |  |  | 687500 | [19 empty] | 687500 | [19 empty] | 0
UAT-QA D4 Report Providing Confirmation of Functional / Non-Functional Requirements and Agencies Ability to Comply with Financial Regulations |  |  | 687500 | [9 empty] | 0 | [12 empty] | 687500 | [16 empty] | 0 | 0 | 0
UAT-QA D5 Deployment of Streamline Testing Efforts and Regression Testing Automation |  |  | 275000 | [9 empty] | 0 | [18 empty] | 275000 | [10 empty] | 0 | 0 | 0
UAT-QA D6 Final Assessment Report |  |  | 275000 | [9 empty] | 0 | [21 empty] | 275000 | [7 empty] | 0 | 0 | 0
Total |  |  | 2750000 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | -275000 | 0 | 0 | 0 | 275000 | 0 | 0 | 550000 | 0 | 0 | 687500 | 0 | 0 | 687500 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projected FYTD |  |  |  | 0 |  |  | 0 |  |  | 275000 |  |  | 0 | 0 |  |  | 275000 |  |  | 825000 |  |  | 1512500 |  |  | 2200000 |  |  | 2200000 |  |  | 2475000 |  |  | 2750000 |  |  | 2750000
Incurred FYTD |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
Paid FYTD | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0