## Monthly Summary
Department of Financial Services
Florida PALM FY 2026 - 2027 Spend Plan Summary FYTD
As of July 31, 2026
Annual
[12 empty] | July 2026 |  |  |  | Release Request Baseline Adjustment | August 2026 |  |  | September 2026 |  |  | October 2026 |  |  | November 2026 |  |  | December 2026 |  |  | January 2027 |  |  | February 2027 |  |  | March 2027 |  |  | April 2027 |  |  | May 2027 |  |  | June 2027 |  |  | CF 2026-27 |  | Fiscal Year to Date
Category (Cost Area / Contract) |  |  |  | FY 25-26 Revert & Appropriated | FY 26-27 GAA Appropriated | FY 26-27 Total Appropriation | Released | Unreleased | Unobligated | 53811358.4764 | 8309789.21 | Projected | Incurred |  | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Total CF Incurred | Total CF Paid | Projected FYTD | Incurred FYTD | Paid FYTD | Balance (Projected - Incurred) | % Remaining
[10 empty] | Projected | Release Remaining
FLAIR System Replacement (100781) | Payment Terms | Contract Type | Disbursement Type | 15533430 | 39040586 | 54574016 | 11611760 | 42962256 | 762657.5236 | 53811358.4764 | 8309789.21 | 5084877.0525 | 3301970.79 |  | 2387390.14 | -1782906.2625 | 6870324.3616 | 0 | 0 | 1363219.4639 | 0 | 0 | 2468566.5396 | 0 | 0 | 9487628.1939 | 0 | 0 | 1355304.6639 | 0 | 0 | 5015843.3529 | 0 | 0 | 7638329.6301 | 0 | 0 | 4292767.2773 | 0 | 0 | 4838882.3029 | 0 | 0 | 4252157.2773 | 0 | 0 | 2926364.6229 | 0 | 0 | 0 | 0 | 3301970.79 | 3301970.79 | 2387390.14 | 50509387.6864 | 93.86%
SSI Implementation Services (FP004) | Paid in Arrears | Fixed Fee | Encumbered | [6 empty] | 29472433 |  | 1480900 | 0 | 2 | 0 | -1480900 | 4957400 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 8102500 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 4953733 | 0 | 0 | 2374000 | 0 | 0 | 2374000 | 0 | 0 | 2374000 | 0 | 0 | 736800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29472433 | 100%
Facilities and Maintenance (FP004) | Advance Pay | Fixed Fee | Encumbered | [6 empty] | 415692 |  | 34641 | 34641 |  | 34641 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 34641 | 34641 | 34641 | 381051 | 91.67%
Production Support (FP004) | Both | Fixed Fee | Encumbered | [6 empty] | 12427182.5 |  | 1398177 | 1316027.5 | 2 | 1119896.5 | -82149.5 | 735896 | 0 | 0 | 735896 | 0 | 0 | 932027 | 0 | 0 | 735896 | 0 | 0 | 735896 | 0 | 0 | 932027 | 0 | 0 | 1221085 | 0 | 0 | 1221085 | 0 | 0 | 1419177 | 0 | 0 | 1221085 | 0 | 0 | 1221085 | 0 | 0 | 0 | 0 | 1316027.5 | 1316027.5 | 1119896.5 | 11111155 | 89.41%
Additional Facilities | Advance Pay | Fixed Fee | Encumbered | [6 empty] | 245681.66 |  | 20360.23 | 20360.23 |  | 20360.23 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20360.23 | 0 | 0 | 20542.03 | 0 | 0 | 20542.03 | 0 | 0 | 20542.03 | 0 | 0 | 20766.98 | 0 | 0 | 20766.98 | 0 | 0 | 0 | 0 | 20360.23 | 20360.23 | 20360.23 | 225321.43 | 91.71%
Oracle Software and Maintenance (FP005) | Paid in Arrears | Fixed Fee | Encumbered | [6 empty] | 2433842.3836 |  | 27835.9167 | 28885.77 | 3 | 28885.77 | 1049.8533 | 457413.2744 | 0 | 0 | 27835.9167 | 0 | 0 | 387151.7923 | 0 | 0 | 105142.8067 | 0 | 0 | 27835.9167 | 0 | 0 | 387151.7923 | 0 | 0 | 105142.8067 | 0 | 0 | 27835.9167 | 0 | 0 | 387151.7923 | 0 | 0 | 105142.8067 | 0 | 0 | 387151.7923 | 0 | 0 | 0 | 0 | 28885.77 | 28885.77 | 28885.77 | 2404956.6136 | 98.81%
Project Administration | Paid in Arrears | Fixed Fee | Both | [6 empty] | 342391.35 |  | 17454.8458 | 28119.49 | 3 | 28119.49 | 10664.6442 | 53776.5373 | 0 | 0 | 66765.6373 | 0 | 0 | 16665.8373 | 0 | 0 | 17365.8373 | 0 | 0 | 49165.8373 | 0 | 0 | 16665.8373 | 0 | 0 | 17295.8373 | 0 | 0 | 16665.8373 | 0 | 0 | 21572.9873 | 0 | 0 | 16665.8373 | 0 | 0 | 21665.8373 | 0 | 0 | 0 | 0 | 28119.49 | 28119.49 | 28119.49 | 314271.86 | 91.79%
Support Services | Paid in Arrears | Time & Materials | Encumbered | [6 empty] | 5120644.12 |  | 676464.2 | 594227.16 | 5,1 | 310354.91 | -82237.04 | 356465.56 | 0 | 0 | 372148.92 | 0 | 0 | 372148.92 | 0 | 0 | 366150.56 | 0 | 0 | 381833.92 | 0 | 0 | 484292.4 | 0 | 0 | 484292.4 | 0 | 0 | 484292.4 | 0 | 0 | 468092.4 | 0 | 0 | 366150.56 | 0 | 0 | 390548.92 | 0 | 0 | 0 | 0 | 594227.16 | 594227.16 | 310354.91 | 4526416.96 | 88.4%
QA Support Services | Paid in Arrears | Time & Materials | Encumbered | [6 empty] | 1340728 |  | 215040 | 214328 |  | 111928 | -712 | 102400 | 0 | 0 | 102400 | 0 | 0 | 102400 | 0 | 0 | 102400 | 0 | 0 | 102400 | 0 | 0 | 102400 | 0 | 0 | 102400 | 0 | 0 | 102400 | 0 | 0 | 102400 | 0 | 0 | 102400 | 0 | 0 | 102400 | 0 | 0 | 0 | 0 | 214328 | 214328 | 111928 | 1126400 | 84.01%
Production Support Administration | Paid in Arrears | Fixed Fee | Both | [6 empty] | 801931.3628 |  | 3171.76 | 3349.54 | 3 | 3349.54 | 177.78 | 3171.76 | 0 | 0 | 3171.76 | 0 | 0 | 3171.76 | 0 | 0 | 3171.76 | 0 | 0 | 3171.76 | 0 | 0 | 38305.0933 | 0 | 0 | 699197.5561 | 0 | 0 | 11305.0933 | 0 | 0 | 11305.0933 | 0 | 0 | 11305.0933 | 0 | 0 | 11305.0933 | 0 | 0 | 0 | 0 | 3349.54 | 3349.54 | 3349.54 | 798581.8228 | 99.58%
Florida PALM-UAT | Paid in Arrears | Fixed Fee | Encumbered | [6 empty] | 1210832.1 |  | 1210832.1 | 1062032.1 | 2 | 729854.7 | -148800 | 148800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1062032.1 | 1062032.1 | 729854.7 | 148800 | 12.29%
Contingency (100819) |  |  |  | 3000000 | 0 | 3000000 | 0 | 3000000 | 3000000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Salaries & Benefits (010000) |  |  |  | 0 | 11338685 | 11338685 | 11338685 | 0 | 116718.8267 | 11221966.1733 | 10510513.41 | 944890.4167 | 828171.59 |  | 828171.59 | -116718.8267 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 944890.4167 | 0 | 0 | 0 | 0 | 828171.59 | 828171.59 | 828171.59 | 10393794.5833 | 92.62%
Salaries & Benefits (010000) |  |  |  | 0 | 1948107 | 1948107 | 487027 | 1461080 | 96900.08 | 1851206.92 | 421584.83 | 162342.25 | 65442.17 |  | 65442.17 | -96900.08 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 162342.25 | 0 | 0 | 0 | 0 | 65442.17 | 65442.17 | 65442.17 | 1785764.75 | 96.46%
Risk Management Insurance (103241) |  |  |  | 0 | 14572 | 14572 | 14572 | 0 | 0 | 14572 | 14572 | 14572 | 0 | 2 | 0 | -14572 | 14572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14572 | 100%
DMS HR Transfer (107040) |  |  |  | 0 | 24081 | 24081 | 24081 | 0 | 0 | 24081 | 24081 | 6020.25 | 0 | 2 | 0 | -6020.25 | 6020.25 | 0 | 0 | 0 | 0 | 0 | 6020.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6020.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6020.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24081 | 100%
DMS HR Transfer (107040) |  |  |  | 0 | 3528 | 3528 | 3528 | 0 | 0 | 3528 | 3528 | 882 | 0 |  | 0 | -882 | 882 | 0 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3528 | 100%
Totals |  |  |  | 18533430 | 52369559 | 70902989 | 23479653 | 47423336 | 3976276.4302 | 66926712.5698 | 19284068.45 | 6213583.9692 | 4195584.55 |  | 3281003.9 | -2017999.4192 | 7999031.2783 | 0 | 0 | 2470452.1306 | 0 | 0 | 3582701.4563 | 0 | 0 | 10594860.8606 | 0 | 0 | 2462537.3306 | 0 | 0 | 6129978.2696 | 0 | 0 | 8745562.2967 | 0 | 0 | 5399999.9439 | 0 | 0 | 5953017.2196 | 0 | 0 | 5359389.9439 | 0 | 0 | 4033597.2896 | 0 | 0 | 0 | 0 | 4195584.55 | 4195584.55 | 3281003.9 | 62731128.0198 | 100%
Running Totals | [11 empty] | 6213583.9692 | 4195584.55 |  | 3281003.9 | 4195584.55 | 12194615.8283 | 4195584.55 | 3281003.9 | 14665067.9589 | 4195584.55 | 3281003.9 | 18247769.4152 | 4195584.55 | 3281003.9 | 28842630.2758 | 4195584.55 | 3281003.9 | 31305167.6064 | 4195584.55 | 3281003.9 | 37435145.876 | 4195584.55 | 3281003.9 | 46180708.1727 | 4195584.55 | 3281003.9 | 51580708.1166 | 4195584.55 | 3281003.9 | 57533725.3362 | 4195584.55 | 3281003.9 | 62893115.2802 | 4195584.55 | 3281003.9 | 66926712.5698 | 4195584.55 | 3281003.9 |  | 3281003.9 |  |  | Total Incurred/Total Projected FYTD |  | 100%
Monthly Total Incurred/Total Projected | [11 empty] | 67.52% |  |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% | [6 empty] | Total Paid/Total Projected FYTD |  | 78.2%
Monthly Total Incurred/Total Projected (Variance) | [11 empty] | -32.48% |  |  |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100% |  |  | -100%
FYTD Total Incurred/Total Projected | [11 empty] | 67.52% |  |  |  |  | 34.41% |  |  | 28.61% |  |  | 22.99% |  |  | 14.55% |  |  | 13.4% |  |  | 11.21% |  |  | 9.085% |  |  | 8.134% |  |  | 7.292% |  |  | 6.671% |  |  | 6.269% | [6 empty] | Total Release/Total Appropriation |  | 126.7%
FYTD Total Incurred/Total Projected (Variance) | [11 empty] | -32.48% |  |  |  |  | -65.59% |  |  | -71.39% |  |  | -77.01% |  |  | -85.45% |  |  | -86.6% |  |  | -88.79% |  |  | -90.91% |  |  | -91.87% |  |  | -92.71% |  |  | -93.33% |  |  | -93.73%
[54 empty] | Total Paid/Total Release |  | 13.97%
Reconciles to ALRR |  |  |  | Yes |  |  | Yes | Yes | Yes | [5 empty] | Yes |  |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  |  | Yes |  | Yes |  |  | No

## Footnotes
Department of Financial Services
FY 2026 - 2027 Spend Plan Footnotes
Footnotes:
1 | Contractor hours were less than anticipated.
2 | Incurred amounts were less than anticipated due to the timing of a planned purchase or acceptance of deliverables.
3 | Incurred amounts were greater than anticipated due to the timing of a planned purchase or acceptance of deliverables.
4 | Contractor hours were greater than anticipated.
5 | Contractor hours projected and incurred amounts were greater than anticipated due to June 2026 hours being projected to be incurred in July 2026.

## SSI Detail
[7 empty] | July 2026 |  |  | Request Release Baseline Adjustment | August 2026 |  |  | September 2026 |  |  | October 2026 |  |  | November 2026 |  |  | December 2026 |  |  | January 2027 |  |  | February 2027 |  |  | March 2027 |  |  | April 2027 |  |  | May 2027 |  |  | June 2027 |  |  | CF 2026-27
|  | Description | Total Deliverable Cost FY 26-27 | Payment Terms | Contract Type | Disbursement Type | July Projection | July Accepted / Approved | July Paid |  | August Projection | August Accepted / Approved | August Paid | September Projection | September Accepted / Approved | September Paid | October Projection | October Accepted / Approved | October Paid | November Projection | November Accepted / Approved | November Paid | December Projection | December Accepted / Approved | December Paid | January Projection | January Accepted / Approved | January Paid | February Projection | February Accepted / Approved | February Paid | March Projection | March Accepted / Approved | March Paid | April Projection | April Accepted / Approved | April Paid | May Projection | May Accepted / Approved | May Paid | June Projection | June Accepted / Approved | June Paid | CF Incurred | CF Paid | Total Projection
Department of Financial Services
Florida PALM FY 2026 - 2027 SSI Contract Detail FYTD
Ref # | Deliverable Name
Implementation
670 | Completion of Payroll Parallel Testing | Implementation | 600000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [6 empty] | 600000 | [28 empty] | 600000
672 | Support of UAT Segment III | Implementation | 1976500 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | 1976500 | [32 empty] | 0 | 0 | 1976500
673 | Completion of Dry Run #2 | Implementation | 1500000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | 1500000 | [32 empty] | 0 | 0 | 1500000
674 | Completion of Penetration Testing | Implementation | 513400 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 513400 | [23 empty] | 0 | 0 | 513400
675 | Completion of Performance Testing | Implementation | 1480900 | Paid in Arrears | Fixed Fee | Encumbered | 1480900 |  |  | -1480900 | 1480900 | [32 empty] | 0 | 0 | 1480900
676 | Completion of Disaster Recovery Testing | Implementation | 550000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 550000 | [23 empty] | 0 | 0 | 550000
677 | Completion of Dry Run #3 | Implementation | 1500000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 1500000 | [23 empty] | 0 | 0 | 1500000
679 | Go-Live of Financials and Payroll Waves | Implementation | 2579733 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [18 empty] | 2579733 | [14 empty] | 0 | 0 | 2579733
680 | Hypercare Monthly Deliverable (Month 1) | Implementation | 2374000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [18 empty] | 2374000 | [14 empty] | 0 | 0 | 2374000
681 | Hypercare Monthly Deliverable (Month 2) | Implementation | 2374000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [21 empty] | 2374000 | [11 empty] | 0 | 0 | 2374000
682 | Hypercare Monthly Deliverable (Month 3) | Implementation | 2374000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [24 empty] | 2374000 | [8 empty] | 0 | 0 | 2374000
683 | Hypercare Monthly Deliverable (Month 4) | Implementation | 2374000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [27 empty] | 2374000 | [5 empty] | 0 | 0 | 2374000
684 | Post-Implementation Support Monthly Deliverable (Month 1) | Implementation | 736800 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [30 empty] | 736800 |  |  | 0 | 0 | 736800
707 | Support of UAT Segment IV | Implementation | 1976500 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 1976500 | [23 empty] | 0 | 0 | 1976500
708 | Completion of Dry Run #4 | Implementation | 1500000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [15 empty] | 1500000 | [17 empty] | 0 | 0 | 1500000
710 | Completion of Interface Testing Segment III | Implementation | 2081700 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 2081700 | [23 empty] | 0 | 0 | 2081700
711 | Completion of Performance Testing Segment II | Implementation | 1480900 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [9 empty] | 1480900 | [23 empty] | 0 | 0 | 1480900
712 | Go-Live of Financials and Payroll Waves (pre Cutover Activities) | Implementation | 1500000 | Paid in Arrears | Fixed Fee | Encumbered |  |  |  | 0 | [15 empty] | 1500000 | [17 empty] | 0 | 0 | 1500000
Production Support
Prod Supp | Monthly Facilities Expense | Prod Supp | 415692 | Advance Pay | Fixed Fee | Encumbered | 34641 | 34641 | 34641 | 0 | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 34641 |  |  | 0 | 0 | 415692
Prod Supp | AM Services | Prod Supp | 9311168 | Paid in Arrears | Fixed Fee | Encumbered | 590800 | 590800 | 590800 | 0 | 611478 |  |  | 611478 |  |  | 611478 |  |  | 611478 |  |  | 611478 |  |  | 611478 |  |  | 1010300 |  |  | 1010300 |  |  | 1010300 |  |  | 1010300 |  |  | 1010300 |  |  | 0 | 0 | 9311168
Prod Supp | IM Services (includes $3,715 SNow Credit) | Prod Supp | 1920518 | Paid in Arrears | Fixed Fee | Encumbered | 120085 | 120085 | 120085 | 0 | 124418 |  |  | 124418 |  |  | 124418 |  |  | 124418 |  |  | 124418 |  |  | 124418 |  |  | 210785 |  |  | 210785 |  |  | 210785 |  |  | 210785 |  |  | 210785 |  |  | 0 | 0 | 1920518
Prod Supp | Oracle OCI Costs | Prod Supp | 786485 | Paid in Arrears | Fixed Fee | Encumbered | 196131 | 196131 |  | 0 | 0 |  |  | 0 |  |  | 196131 |  |  | 0 |  |  | 0 |  |  | 196131 |  |  | 0 |  |  | 0 |  |  | 198092 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 786485
Prod Supp | Support Tools Maintenance | Prod Supp | 49205 | Advance Pay | Fixed Fee | Encumbered | 49205 | 49205 | 49205 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 49205
Prod Supp | Support Tools Purchase | Prod Supp | 336230 | Advance Pay | Fixed Fee | Encumbered | 409670 | 336230 | 336230 | -73440 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 336230
Prod Supp | Solution Software Support | Prod Supp | 23576.5 | Advance Pay | Fixed Fee | Encumbered | 32286 | 23576.5 | 23576.5 | -8709.5 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 23576.5
| Implementation Total: | [5 empty] | 1480900 | 0 | 0 |  | 4957400 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 8102500 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 4953733 | 0 | 0 | 2374000 | 0 | 0 | 2374000 | 0 | 0 | 2374000 | 0 | 0 | 736800 | 0 | 0 | 0 | 0 | 29472433
| Production Support Facilities Total: | [5 empty] | 34641 | 34641 | 34641 |  | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 34641 | 0 | 0 | 0 | 0 | 415692
| Production Support (No Facilities) Total: | [5 empty] | 1398177 | 1316027.5 | 1119896.5 |  | 735896 | 0 | 0 | 735896 | 0 | 0 | 932027 | 0 | 0 | 735896 | 0 | 0 | 735896 | 0 | 0 | 932027 | 0 | 0 | 1221085 | 0 | 0 | 1221085 | 0 | 0 | 1419177 | 0 | 0 | 1221085 | 0 | 0 | 1221085 | 0 | 0 | 0 | 0 | 12427182.5
Monthly Totals |  |  | 42315307.5 |  |  |  | 2913718 | 1350668.5 | 1154537.5 | -1563049.5 | 5727937 | 0 | 0 | 770537 | 0 | 0 | 1566668 | 0 | 0 | 8873037 | 0 | 0 | 770537 | 0 | 0 | 3966668 | 0 | 0 | 6209459 | 0 | 0 | 3629726 | 0 | 0 | 3827818 | 0 | 0 | 3629726 | 0 | 0 | 1992526 | 0 | 0 | 0 | 0 | 42315307.5
| Projected YTD | [5 empty] | 2913718 |  |  | 1350668.5 | 7078605.5 |  |  | 7849142.5 |  |  | 9415810.5 |  |  | 18288847.5 |  |  | 19059384.5 |  |  | 23026052.5 |  |  | 29235511.5 |  |  | 32865237.5 |  |  | 36693055.5 |  |  | 40322781.5 |  |  | 42315307.5
| Incurred YTD | [6 empty] | 1350668.5 |  |  |  | 1350668.5 |  |  | 1350668.5 |  |  | 1350668.5 |  |  | 1350668.5 |  |  | 1350668.5 |  |  | 1350668.5 |  |  | 1350668.5 |  |  | 1350668.5 |  |  | 1350668.5 |  |  | 1350668.5 |  |  | 1350668.5 |  | 1350668.5
| Paid YTD | [7 empty] | 1154537.5 |  |  |  | 1154537.5 |  |  | 1154537.5 |  |  | 1154537.5 |  |  | 1154537.5 |  |  | 1154537.5 |  |  | 1154537.5 |  |  | 1154537.5 |  |  | 1154537.5 |  |  | 1154537.5 |  |  | 1154537.5 |  |  | 1154537.5 |  | 1154537.5

## Oracle Summary
Department of Financial Services
Florida PALM FY 2026 - 2027 Oracle Summary FYTD
| Quantity/Months | Quote |  |  | Payment Terms | Contract Type | Disbursement Type | July 2026 |  |  |  | Request Release Baseline Adjustment | August 2026 |  |  |  | September 2026 |  |  |  | October 2026 |  |  |  | November 2026 |  |  |  | December 2026 |  |  |  | January 2027 |  |  |  | February 2027 |  |  |  | March 2027 |  |  |  | April 2027 |  |  |  | May 2027 |  |  |  | June 2027 |  |  |  | FY 2026-27 CF |  | Total
Program |  | Tech Support | Total Purchase/ Subscription | Total Projection |  |  |  | Projected | Incurred |  | Paid |  | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | Projected | Incurred |  | Paid | CF Incurred | CF Paid | Total Projected | Projected FYTD | Incurred FYTD | Paid FYTD
Current License Tech Support |  | 1442327.1126 | 0 | 1442327.1126 |  |  |  | 0 | 0 | #REF! | 0 | 0 | 353536.3702 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 359315.8757 | 0 | #REF! | 0 | 1265.9025 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 359315.8757 | 0 | #REF! | 0 | 1265.9025 | 0 | #REF! | 0 | 0 | 0 | #REF! | 0 | 359315.8757 | 0 | #REF! | 0 | 1265.9025 | 0 | #REF! | 0 | 359315.8757 | 0 | #REF! | 0 | 0 | 0 | 1794597.5803 | 28885.77 | 28885.77 | 28885.77
Assignment |  | 1442327.1126 | 0 | 1442327.1126 |  |  |  | 0 | 0 | 0 | 0 | 0 | 353536.3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359315.8757 | 0 | 0 | 0 | 1265.9025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359315.8757 | 0 | 0 | 0 | 1265.9025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359315.8757 | 0 | 0 | 0 | 1265.9025 | 0 | 0 | 0 | 359315.8757 | 0 | 0 | 0 | 0 | 0 | 1794597.5803 | 0 | 0 | 0
Micro Focus International LTD - Server Express COBOL for Unix for 1 Named User | 2 | 8673.05 |  | 8673.05 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 2150.57 | 0 |  | 0 | 0 | 0 |  | 0 | 902.36 | 0 |  | 0 | 1265.9025 | 0 |  | 0 | 0 | 0 |  | 0 | 902.36 | 0 |  | 0 | 1265.9025 | 0 |  | 0 | 0 | 0 |  | 0 | 902.36 | 0 |  | 0 | 1265.9025 | 0 |  | 0 | 902.36 | 0 |  | 0 |  |  | 9557.7175 | 0 | 0 | 0
Oracle Business Intelligence (Analytics) Server Administrator | 4 | 1539.36 |  | 1539.36 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 377.2959 | 0 |  | 0 | 0 | 0 |  | 0 | 384.84 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 384.84 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 384.84 | 0 |  | 0 | 0 | 0 |  | 0 | 384.84 | 0 |  | 0 |  |  | 1916.6559 | 0 | 0 | 0
Oracle Business Intelligence Management Pack | 4 | 3052.29 |  | 3052.29 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 748.11 | 0 |  | 0 | 0 | 0 |  | 0 | 763.0725 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 763.0725 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 763.0725 | 0 |  | 0 | 0 | 0 |  | 0 | 763.0725 | 0 |  | 0 |  |  | 3800.4 | 0 | 0 | 0
Oracle Business Intelligence Suite Foundation Edition | 4 | 79641.66 |  | 79641.66 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 19520.015 | 0 |  | 0 | 0 | 0 |  | 0 | 19910.415 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19910.415 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19910.415 | 0 |  | 0 | 0 | 0 |  | 0 | 19910.415 | 0 |  | 0 |  |  | 99161.675 | 0 | 0 | 0
Oracle Data Integrator Enterprise Edition | 20 | 39820.83 |  | 39820.83 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 9760.008 | 0 |  | 0 | 0 | 0 |  | 0 | 9955.2075 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9955.2075 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9955.2075 | 0 |  | 0 | 0 | 0 |  | 0 | 9955.2075 | 0 |  | 0 |  |  | 49580.838 | 0 | 0 | 0
Oracle Data Visualization | 4 | 26547.95 |  | 26547.95 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 6506.8489 | 0 |  | 0 | 0 | 0 |  | 0 | 6636.9875 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6636.9875 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6636.9875 | 0 |  | 0 | 0 | 0 |  | 0 | 6636.9875 | 0 |  | 0 |  |  | 33054.7989 | 0 | 0 | 0
Oracle Financial Analytics Fusion Edition (DW/BI) | 100 | 15398.03 |  | 15398.03 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 3774.0276 | 0 |  | 0 | 0 | 0 |  | 0 | 3849.5075 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3849.5075 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3849.5075 | 0 |  | 0 | 0 | 0 |  | 0 | 3849.5075 | 0 |  | 0 |  |  | 19172.0576 | 0 | 0 | 0
Oracle Managed File Transfer | 12 | 22236.79 |  | 22236.79 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 5450.1953 | 0 |  | 0 | 0 | 0 |  | 0 | 5559.1975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5559.1975 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5559.1975 | 0 |  | 0 | 0 | 0 |  | 0 | 5559.1975 | 0 |  | 0 |  |  | 27686.9853 | 0 | 0 | 0
Oracle Management Pack for Oracle Data Integrator | 16 | 7326.84 |  | 7326.84 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 1795.7954 | 0 |  | 0 | 0 | 0 |  | 0 | 1831.71 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1831.71 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1831.71 | 0 |  | 0 | 0 | 0 |  | 0 | 1831.71 | 0 |  | 0 |  |  | 9122.6354 | 0 | 0 | 0
Oracle SOA Management Pack Enterprise Edition | 14 | 21505.81 |  | 21505.81 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 5271.03 | 0 |  | 0 | 0 | 0 |  | 0 | 5376.4525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5376.4525 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5376.4525 | 0 |  | 0 | 0 | 0 |  | 0 | 5376.4525 | 0 |  | 0 |  |  | 26776.84 | 0 | 0 | 0
Oracle SOA Suite for Oracle Middleware | 14 | 49462.9 |  | 49462.9 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 12123.2575 | 0 |  | 0 | 0 | 0 |  | 0 | 12365.725 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12365.725 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12365.725 | 0 |  | 0 | 0 | 0 |  | 0 | 12365.725 | 0 |  | 0 |  |  | 61586.1575 | 0 | 0 | 0
Oracle WebLogic Server Management Pack Enterprise Edition | 26 | 19217.22 |  | 19217.22 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 4710.105 | 0 |  | 0 | 0 | 0 |  | 0 | 4804.305 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4804.305 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4804.305 | 0 |  | 0 | 0 | 0 |  | 0 | 4804.305 | 0 |  | 0 |  |  | 23927.325 | 0 | 0 | 0
Oracle WebLogic Suite | 26 | 72065.18 |  | 72065.18 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 17663.0316 | 0 |  | 0 | 0 | 0 |  | 0 | 18016.295 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 18016.295 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 18016.295 | 0 |  | 0 | 0 | 0 |  | 0 | 18016.295 | 0 |  | 0 |  |  | 89728.2116 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 92083 | 59347 |  | 59347 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 14545.8375 | 0 |  | 0 | 0 | 0 |  | 0 | 14836.7474 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14836.7474 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14836.7474 | 0 |  | 0 | 0 | 0 |  | 0 | 14836.7474 | 0 |  | 0 |  |  | 73892.8271 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 92083 | 38946.69 |  | 38946.69 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 9545.76 | 0 |  | 0 | 0 | 0 |  | 0 | 9736.6728 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9736.6728 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9736.6728 | 0 |  | 0 | 0 | 0 |  | 0 | 9736.6728 | 0 |  | 0 |  |  | 48492.451 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 92083 | 78819.28 |  | 78819.28 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 19318.45 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 |  |  | 98137.7354 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 92083 | 424696.86 |  | 424696.86 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 104092.3625 | 0 |  | 0 | 0 | 0 |  | 0 | 106174.2139 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 106174.2139 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 106174.2139 | 0 |  | 0 | 0 | 0 |  | 0 | 106174.2139 | 0 |  | 0 |  |  | 528789.2179 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 92083 | 55636.88 |  | 55636.88 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 13636.49 | 0 |  | 0 | 0 | 0 |  | 0 | 13909.2215 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13909.2215 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13909.2215 | 0 |  | 0 | 0 | 0 |  | 0 | 13909.2215 | 0 |  | 0 |  |  | 69273.3758 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 114800 | 49875.07 |  | 49875.07 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 12224.2825 | 0 |  | 0 | 0 | 0 |  | 0 | 12468.7675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12468.7675 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12468.7675 | 0 |  | 0 | 0 | 0 |  | 0 | 12468.7675 | 0 |  | 0 |  |  | 62099.3525 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 114800 | 60658.4 |  | 60658.4 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 14867.255 | 0 |  | 0 | 0 | 0 |  | 0 | 15164.6 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 15164.6 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 15164.6 | 0 |  | 0 | 0 | 0 |  | 0 | 15164.6 | 0 |  | 0 |  |  | 75525.655 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 92083 | 78819.28 |  | 78819.28 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 19318.45 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 |  |  | 98137.7354 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 92083 | 87165.48 |  | 87165.48 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 21364.09 | 0 |  | 0 | 0 | 0 |  | 0 | 21791.3694 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 21791.3694 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 21791.3694 | 0 |  | 0 | 0 | 0 |  | 0 | 21791.3694 | 0 |  | 0 |  |  | 108529.5678 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 92083 | 78819.28 |  | 78819.28 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 19318.45 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 | 0 | 0 |  | 0 | 19704.8213 | 0 |  | 0 |  |  | 98137.7354 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 92083 | 63054.9826 |  | 63054.9826 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 15454.6525 | 0 |  | 0 | 0 | 0 |  | 0 | 15763.7442 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 15763.7442 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 15763.7442 | 0 |  | 0 | 0 | 0 |  | 0 | 15763.7442 | 0 |  | 0 |  |  | 78509.6293 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Oracle Credits |  |  |  |  | Payment Terms | Contract Type | Disbursement Type | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Oracle Credits |  |  |  |  | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Analytics |  | 304163.95 | 0 | 304163.95 | Payment Terms | Contract Type | Disbursement Type | 0 | 0 | 0 | 0 | 0 | 76040.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76040.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76040.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76040.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304163.95 | 0 | 0 | 0
HR Analytics (DW/BI) | 200 | 56637.43 | 0 | 56637.43 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 14159.3575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14159.3575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14159.3575 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14159.3575 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 56637.43 | 0 | 0 | 0
Financial Analytics (DW/BI) | 3000 | 231567.78 | 0 | 231567.78 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 57891.945 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 57891.945 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 57891.945 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 57891.945 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 231567.78 | 0 | 0 | 0
Project Analytics (DW/BI) | 100 | 15958.74 | 0 | 15958.74 | Paid in Arrears | Fixed Fee | Encumbered | 0 | 0 |  | 0 | 0 | 3989.685 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3989.685 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3989.685 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3989.685 | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 15958.74 | 0 | 0 | 0
OCI |  | 0 | 334031 | 334031 | Payment Terms | Contract Type | Disbursement Type | 27835.9167 | 28885.77 | 0 | 28885.77 | 1049.8533 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 27835.9167 | 0 | 0 | 0 | 0 | 0 | 335080.8533 | 28885.77 | 28885.77 | 28885.77
OAC (DW/BI) - DEV: $53,219.00 - Test: $63,779.00 - DR: $94,238.00 - Production: $194,227.00 | 4 | 0 | 334031 | 334031 | Paid in Arrears | Fixed Fee | Encumbered | 27835.9167 | 28885.77 |  | 28885.77 | 1049.8533 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 | 27835.9167 | 0 |  | 0 |  |  | 335080.8533 | 28885.77 | 28885.77 | 28885.77
New License Purchase and Tech Support |  | 0 |  | 0 | Payment Terms | Contract Type | Disbursement Type | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Financials | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Treasury | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Expenses | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise eSettlements | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Contracts | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Grants | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Project Costing | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Supplier Contract Management | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Purchasing | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Human Resources | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Payroll | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PeopleSoft Enterprise Time and Labor | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 1746491.0626 | 334031 | 2080522.0626 |  |  |  | 27835.9167 | 28885.77 | #REF! | 28885.77 | 1049.8533 | 457413.2744 | 0 | #REF! | 0 | 27835.9167 | 0 | #REF! | 0 | 387151.7923 | 0 | #REF! | 0 | 105142.8067 | 0 | #REF! | 0 | 27835.9167 | 0 | #REF! | 0 | 387151.7923 | 0 | #REF! | 0 | 105142.8067 | 0 | #REF! | 0 | 27835.9167 | 0 | #REF! | 0 | 387151.7923 | 0 | #REF! | 0 | 105142.8067 | 0 | #REF! | 0 | 387151.7923 | 0 | #REF! | 0 | 0 | 0 | 2433842.3836 | 28885.77 | 28885.77 | 28885.77
Projected FYTD | [7 empty] | 27835.9167 |  |  |  | 28885.77 | 486299.0444 |  |  |  | 514134.961 |  |  |  | 901286.7533 |  |  |  | 1006429.56 |  |  |  | 1034265.4767 |  |  |  | 1421417.269 |  |  |  | 1526560.0757 |  |  |  | 1554395.9923 |  |  |  | 1941547.7846 |  |  |  | 2046690.5913 |  |  |  | 2433842.3836
Incurred FYTD | [8 empty] | 28885.77 |  |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77
Paid FYTD | [10 empty] | 28885.77 |  |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77 |  |  |  | 28885.77
[14 empty] | 457413.2744 |  | 457413.2744 |  | 485249.191 |  | 0 |  | 872400.9833 |  | 872400.9833 |  | 977543.79 |  | 977543.79 |  | 1005379.7067 |  | 1005379.7067 |  | 1392531.499 |  | 1392531.499 |  | 1497674.3057 |  | 1497674.3057 |  | 1525510.2223 |  | 1525510.2223 |  | 1912662.0146 |  | 1912662.0146 |  | 2017804.8213 |  | 2017804.8213 |  | 2404956.6136 |  | 2404956.6136

## Florida PALM-UAT
Department of Financial Services
Florida PALM FY 2026 - 2027 PALM Readiness Detail FYTD
[7 empty] | July 2026 |  |  | Request Release Baseline Adjustment | August 2026 |  |  | September 2026 |  |  | October 2026 |  |  | November 2026 |  |  | December 2026 |  |  | January 2027 |  |  | February 2027 |  |  | March 2027 |  |  | April 2027 |  |  | May 2027 |  |  | June 2027 |  |  | CF 2026-27 |  | Total
Item Description | Rate | Quantity | Total Projected | Payment Terms | Contract Type | Disbursement Type | Projected | Incurred | Paid |  | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Projected | Incurred | Paid | Incurred | Paid | Projected FYTD | Incurred FYTD | Paid FYTD
PALM Readiness Deliverables |  |  | 1210832.1 |  |  |  | 1210832.1 | 1062032.1 | 729854.7 | -148800 | 148800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062032.1 | 1062032.1 | 729854.7
UAT-QA D4 Report Providing Confirmation of Functional / Non-Functional Requirements and Agencies Ability to Comply with Financial Regulations |  |  | 729854.7 | Paid in Arrears | Fixed Fee | Encumbered | 729854.7 | 729854.7 | 729854.7 | 0 | [35 empty] | 729854.7 | 729854.7 | 729854.7
UAT-QA D5 Deployment of Streamline Testing Efforts and Regression Testing Automation |  |  | 332177.4 | Paid in Arrears | Fixed Fee | Encumbered | 332177.4 | 332177.4 |  | 0 | [35 empty] | 332177.4 | 332177.4 | 0
UAT-QA D6 Final Assessment Report |  |  | 148800 | Paid in Arrears | Fixed Fee | Encumbered | 148800 |  |  | -148800 | 148800 | [34 empty] | 0 | 0 | 0
Total |  |  | 1210832.1 |  |  |  | 1210832.1 | 1062032.1 | 729854.7 | -148800 | 148800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062032.1 | 1062032.1 | 729854.7
Projected FYTD | [6 empty] | 1210832.1 |  |  | 1062032.1 | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1 |  |  | 1210832.1
Incurred FYTD | [7 empty] | 1062032.1 |  |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  |  | 1062032.1 |  | 1062032.1
Paid FYTD | [8 empty] | 729854.7 |  |  |  | 729854.7 |  |  | 729854.7 |  |  | 729854.7 |  |  | 729854.7 |  |  | 729854.7 |  |  | 729854.7 |  |  | 729854.7 |  |  | 729854.7 |  |  | 729854.7 |  |  | 729854.7 |  |  | 729854.7 |  | 729854.7