## Development Group
| Time Estimation | Project Name/Remedy#: Requesting Division: Submitted By:
Phases and Tasks |  | Quantity # of Items | Baseline Hours | Time Estimations (Hours)
|  |  |  | Optimistic | Average | Pessimistic
3. Requirements Phase | Estimation Guidelines
Documentation | 8 hours per input screen or single batch process | 0 | 8 | 0 | 0 | 0
Diagrams | 8 hours per input screen or single batch process | 0 | 8 | 0 | 0 | 0
Meetings | Actual hours based on # of anticipated meetings | 0 | 0 | 0 | 0 | 0
Requirements Totals |  | 0 |  | 0 | 0 | 0
Person Weeks at full time |  |  |  | 0 | 0 | 0
4. Analysis/Design Phase | Estimation Guidelines
Research & Analysis | Estimate based on anticipated complexity |  | 0 | 0 | 0 | 0
Documentation | 8 hours per input screen or single batch process | 0 | 8 | 0 | 0 | 0
Diagrams | 8 hours per input screen or single batch process | 0 | 8 | 0 | 0 | 0
Design Prototype | 10 hours per input screen or single batch process | 0 | 10 | 0 | 0 | 0
Meetings | Actual hours based on # of anticipated meetings | 0 | 0 | 0 | 0 | 0
Analysis/Design Totals |  | 0 |  | 0 | 0 | 0
Person Weeks at full time |  |  |  | 0 | 0 | 0
5. Development Phase | Estimation Guidelines
New Website (Environment) | 1 hour per item | 0 | 1 | 0 | 0 | 0
New Database (Environment) | 1 hour per item | 0 | 1 | 0 | 0 | 0
New Report (Environment) | 1 hour per item | 0 | 1 | 0 | 0 | 0
New Security (Framework) | 1 hour per item | 0 | 1 | 0 | 0 | 0
New Navigation (Menus) | 4 hours per sub-menu | 0 | 4 | 0 | 0 | 0
New Screen | 8 hours w/prototype; 16 hours without prototype per 25 input fields | 0 | 8 | 0 | 0 | 0
New Crystal Report | 3 hours for every table involved and/or sub-report | 0 | 3 | 0 | 0 | 0
New Stored Procedure | 1 hour for every table involved | 0 | 1 | 0 | 0 | 0
New Table | 2 hours per every 25 columns | 0 | 2 | 0 | 0 | 0
New View | 2 hours per view | 0 | 2 | 0 | 0 | 0
New Batch Process (Job) | 3 hours per table/file per read write procedure | 0 | 3 | 0 | 0 | 0
New Security Restriction | 1 hour per input screen | 0 | 1 | 0 | 0 | 0
New Business Layer Component | 8 hours per every 25 data elements processed in the layer | 0 | 8 | 0 | 0 | 0
Updated Navigation (Menus) | 1 hour per sub-menu item updated | 0 | 1 | 0 | 0 | 0
Updated Screen | 4 hours w/prototype; 6 without prototype per 25 input fields | 0 | 4 | 0 | 0 | 0
Updated Crystal Report | 1 hour for every table involved and/or sub-report | 0 | 1 | 0 | 0 | 0
Updated Stored Procedure | 1 hour for every table involved | 0 | 1 | 0 | 0 | 0
Updated Table | 1 hour per every 5 columns modified or added | 0 | 1 | 0 | 0 | 0
Updated View | 1 hour per view | 0 | 1 | 0 | 0 | 0
Updated Batch Process (Job) | 1 hour per table/file per read write procedure | 0 | 1 | 0 | 0 | 0
Updated Security Restriction | 1 hour per input screen | 0 | 1 | 0 | 0 | 0
Updated Business Layer Component | 4 hours per every 25 data elements processed | 0 | 4 | 0 | 0 | 0
Data Conversion | 8 hours per 25 column table | 0 | 8 | 0 | 0 | 0
Version Control | 2 hours per deployment | 0 | 2 | 0 | 0 | 0
Meetings | Actual based on # of anticipated meetings | 0 | 0 | 0 | 0 | 0
Development Totals |  | 0 |  | 0 | 0 | 0
Person Weeks at full time |  |  |  | 0 | 0 | 0
6. Integration - Test - Acceptance Phase | Estimation Guidelines
Test Plan | 1 hour per input screen or batch process | 0 | 1 | 0 | 0 | 0
Test Cases | 1 hour per input screen or batch process | 0 | 1 | 0 | 0 | 0
UnitTesting | 1 hour per input screen or batch process | 0 | 1 | 0 | 0 | 0
Performance/Load Testing | 8 hours per input screen or single batch process | 0 | 8 | 0 | 0 | 0
User Acceptance Testing | Actual based on judgmental estimate | 0 | 0 | 0 | 0 | 0
Meetings | Actual based on # of anticipated meetings | 0 | 0 | 0 | 0 | 0
Integration, Test, Acceptance Totals |  | 0 |  | 0 | 0 | 0
Person Weeks at full time |  |  |  | 0 | 0 | 0
7. Implementation - Deployment Phase | Estimation Guidelines
Documentation | 1 hour per item | 0 | 1 | 0 | 0 | 0
Communication/Misc. | 1 hour per item | 0 | 1 | 0 | 0 | 0
Meetings | 1 hour per item | 0 | 1 | 0 | 0 | 0
Implementation - Deployment Totals |  | 0 |  | 0 | 0 | 0
Person Weeks at full time |  |  |  | 0 | 0 | 0
Grand Total |  | 0 |  | 0 | 0 | 0
Person Weeks at full time |  |  |  | 0 | 0 | 0
Total Cost |  |  |  | 0 | 0 | 0